## Slide 1: ERCOT Outage Scheduling
From the Viewpoint of a Generation Resource Entity, a Transmission & Distribution Service Provider and the ERCOT Outage Coordinators.
Click here
Notes: Welcome and introductions

## Slide 2: Michael W. Kinchen
Asset Manager
Texas Genco LLC
Notes: Michael W. Kinchen
Asset Manager/Asset Optimization
Texas Genco LLC
12301 Kurland Dr.
Houston, Texas 77034
(713) 945 – 8278
Michael-kinchen@txgenco.com

## Slide 3: Introduction
This presentation was designed to provide a general overview of the Outage Scheduling process as established by ERCOT Protocol Section 8 from the viewpoints of a Resource Entity a Transmission Service Provider and the ERCOT Schedulers. We will discuss generation resource variety and diversity, transmission system complexity, some basic planning methodologies, long and short term scheduling requirements and daily plan implementation. Finally, we will focus on handling changes to the plans while maintaining timely and accurate communications with all involved parties.
Notes: This presentation was designed to provide a general overview of the Outage Scheduling process as established by ERCOT Protocol Section 8 from the viewpoints of a Resource Entity a Transmission Service Provider and the ERCOT Coordinators.
We will discuss in general, generation resource variety and diversity, transmission system complexity, some of the basic planning methodologies, long and short term scheduling requirements and daily plan implementation.
Finally, we will focus on handling changes to the plans while maintaining timely and accurate communications with all involved parties.

## Slide 4: Objectives
At the completion of this part of the program, you will be able to:
Describe the general categories of Generation Resources with regards to fuel type and service provided.
Outline the basic protocol requirements for scheduling resource outages with ERCOT.
Detail the differences between the types of resource outages as described in the ERCOT protocols.
List the required QSE outage request and response notification time frames as described in the ERCOT protocols.
Notes: At the completion of this program, all attendee’s will be able to:
Describe the general categories of Generation Resources with regards to fuel type and service provided.
Outline the basic protocol requirements for scheduling resource outages with ERCOT.
Detail the differences between the types of resource outages as described in the ERCOT protocols.
List the required QSE outage request and response notification time frames as described in the ERCOT protocols.

## Slide 5: ERCOT Overview
  ERCOT is one of the nation’s largest power markets
  ERCOT represents approximately 85% of demand for power in Texas
  ERCOT ISO is responsible for monitoring reliable operations of the power supply system through a single control area
  The ERCOT market is not a centrally dispatched power pool; retail providers and other wholesale purchases procure and provide electric power to customers through bilateral contracts
  TGN’s generation facilities provide approximately 20% of ERCOT’s capacity
Notes: Brief overview of ERCOT and the role TGN plays as a Resource Entity:
  ERCOT is one of the nation’s largest power markets
  ERCOT represents approximately 85% of demand for power in Texas and has limited connection outside of this market
  ERCOT ISO is responsible for monitoring reliable operations of the power supply system through a single control area and is one of the nations largest single control areas
  The ERCOT market is not a centrally dispatched power pool; retail providers and other wholesale purchases procure and provide electric power to customers through bilateral contracts
  Texas Genco’s generation facilities provide approximately 20% of ERCOT’s total generating capacity

## Slide 6: Definitions and Terms
Generation Entity
Owner or controller of a Generation Resource used for generating electricity and electrically connected to the ERCOT System.
Generation Resources
Facilities that produce energy and are owned or operated by a Generation Entity.
Notes: General Definitions and Terms
Generation Entity
Owner or controller of a Generation Resource used for generating electricity and electrically connected to the ERCOT System.
Generation Resources
Facilities that produce energy and are owned or operated by a Generation Entity.

## Slide 7: Detail of Generation Resources in ERCOT
525 generators in Texas
which are powered by…
Natural Gas
Coal
Nuclear
Wind
Water (Hydro)
Serving more than 8 Million customers over a 200,000 Sq. mile area.
Notes: Generation Resource numbers in ERCOT broken down by the types and percentages of the energy provided to the customers.
Resource totals (Average);
Natural Gas 44.1%
Coal 39.8%
Nuclear 14.3%
Wind 1.1%
Water 0.3%
Other 0.5%
Diesel 0.0%
100.00%

## Slide 8: Texas Genco Portfolio Overview
  Currently a total net generating capacity of 14,153 MW located in ERCOT
  Efficient, low-cost, solid-fuel baseload portfolio
  Flexible, load following gas fleet
  In 2005, Application made to ERCOT to retire and take out of service, approximately 4,000 MW of Texas Genco’s older gas generation after having been “Mothballed” for over a year.
Notes: Typical Resource Entity Overview:
Texas Genco has a current net generation capacity of about 14,150 MW located in three of the five ERCOT Congestion Zones.
This fleet is comprised of about 70 generating units located in 9 different power plant sites and is made up of both efficient, low cost, Base Load solid fuels units and very flexible, load following gas units.
In 2005, Texas Genco has applied to ERCOT to retire and take out of service, approximately 4,000 MW of Texas Genco’s gas generation after having been “Mothballed” for over a year. This was based on the current supply and demand in the ERCOT market. These units can be returned to service should market conditions warrant.

## Slide 9
Notes: Generation Resource Diversity
This is only one of TGN’s power plants (Generating Facility)
At this one site there are 9 different generating units
Represented at this one site;
4 Baseload, coal fired, steam generating units
3 Cyclic, gas fired, steam generating units
1 Intermediate, gas fired, steam generating unit
1 Peaking, gas fired combustion turbine generating unit
that also serves as a Blackstart resource
All totaling approx. 3600 MW’s of generating capacity

## Slide 10: Resource Planning
Long term group
Maintains the 1, 3 & 5 year maintenance plans
Maintains rolling 12 month plan and sends updates to ERCOT
as outlined in the protocols (Section 8.1.3.2)
Mid term group
Maintains a working 8 to 30 day maintenance plan
Optimizes available unit mix for general economic and environmental planning purposes
Day ahead group
Maintains a “Rolling” 1-7 day operating plan
Optimizes available unit mix for scheduling purposes
Submits schedules for “Next Day” and coming week with ERCOT as outlined in the protocols (Section 8.4)
Notes: TGN uses typical management structure in our generating resource planning,
Our general process flow is as follows;
The Long term group
- Maintains the 1, 3 & 5 year outage plans
- Maintains rolling 12 month plan and updates to ERCOT
as outlined in the protocols, Section 8
The Mid term group
- Maintains a working 8 to 30 day outage plan
Optimizes available unit mix for general economic and environmental planning purposes
The Day ahead group
- Maintains a “Rolling” 1-7 day operating plan
- Optimizes available unit mix for short term scheduling purposes
- Submits schedules for “Next Day” and coming week with ERCOT as outlined in the protocols, Section 8

## Slide 11: Intra Day Operations
Genco QSE
Submits schedules for “Operating Period” with ERCOT
Coordinates start up & shut down of resources
Act as the “Single Point of Contact” as outlined in the Protocols (Section 8.2.1)
Generation Resources (Power Plants)
Satisfy the schedules set down by the QSE
Update availability and capability of the resources to the QSE on a day to day, hour to hour basis
All communications - Must flow in both directions between all involved entities if the plan is to be successful
Notes: As a QSE, TGN operates 24 hours a day, 365 days a year.
Normal routines include the following;
Hour by hour, interval by interval scheduling
- Submitting schedules for “Operating Period” to ERCOT
- Coordinating start up & shut down of generating resources
- Coordinating fuel contracts and schedules
Generation Resources (Power Plants)
- Must satisfy the schedules set down by the QSE
- Must update availability and capability of the resources to the QSE
Communications
Must flow both directions between all involved entities if the plan is to be successful
- Resources need to know ERCOT’S needs and requirements
- Ercot needs to know actual resource capabilities and limitations
- The QSE is the key figure in this communication flow path

## Slide 12: Resource Outage Plans
Outage - Removal of a Facility from service to perform maintenance, construction or repair on the Facility for a specified duration.
(Section 8.4.1)
Must be communicated to ERCOT
Must be approved by ERCOT
Resource must be identified by common name
Reason or cause must be detailed
Capability or limitation must be defined
Times and Dates must accurately reflect the outage
Acceptable schedule deviation must be estimated
Notes: ERCOT Protocol Section 8 defines Resource Outages as;
Removal of a Facility from service to perform maintenance, construction or repair on the Facility for a specified duration.
Information concerning these resource outages or limits;
- Must be communicated to ERCOT in a timely manner
- Must be approved by ERCOT within the stated time frame
- Reason or cause must be detailed
- Times and Dates must accurately reflect the outage
- Capability or limitation must be defined

## Slide 13: Outage Definitions
Planned Outage – Any major or minor Transmission Facility or Resource Facility equipment maintenance that is planned and scheduled in advance as submitted to ERCOT. (Accepted by ERCOT upon receiving)
Forced Outage - An Outage initiated by protective relay, or manually in response to an observation by personnel or the System Operator that the condition of equipment could lead to an event, or potential event that poses a threat to people, equipment or public safety. (ERCOT accepts these immediately)
Maintenance Outage – Removing Transmission Facility or Resource Facility equipment from service to perform work on specific Facility components that could not be postponed until the next Planned Outage.
Level 1 Maintenance Outage - Equipment that must be removed from service within twenty-four (24) hours to prevent a potential Forced Outage. (8 hour response by ERCOT)
Level II Maintenance Outage - Equipment that must be removed from service within two (2) to seven (7) days to prevent a potential Forced Outage. (24 hour response by ERCOT)
Level III Maintenance Outage - Equipment that must be removed from service within eight (8) to thirty (30) days to prevent a potential Forced Outage. (72 hour response by ERCOT)
Notes: ERCOT Outage Definitions
Forced Outage - An Outage initiated by protective relay, or manually in response to an observation by personnel or the System Operator that the condition of equipment could lead to an event, or potential event that poses a threat to people, equipment or public safety.
ERCOT acknowledges the outage after receiving the notice
Level 1 Maintenance Outage - Equipment that must be removed from service within twenty-four (24) hours to prevent a potential Forced Outage
ERCOT must respond within 8 hours of the request to confirm or deny
Level II Maintenance Outage - Equipment that must be removed from service within two (2) to seven (7) days to prevent a potential Forced Outage
ERCOT must respond within 48 hours of the request to conform or deny
Level III Maintenance Outage - Equipment that must be removed from service within eight (8) to thirty (30) days to prevent a potential Forced Outage
ERCOT must respond within 96 hours of the request to confirm or deny

## Slide 14: Outage Definitions Cont’d.
Reliability Must Run (RMR) Service
The provision of generation capacity and/or energy resources from Reliability Must Run Unit or a Synchronous Condenser Unit.
Reliability Must Run (RMR) Unit
A Generation Resource unit operated under the terms of an Agreement with ERCOT that would not otherwise be operated except that they are necessary to provide voltage support, stability or management of localized transmission constraints under first contingency criteria where Market Solutions do not exist.
ERCOT shall approve or reject each RMR Outage request in accordance with the stated time lines. If the amount of time between a Request for approval of a proposed Planned Outage and the scheduled start date of the proposed Outage is No less than thirty (30) days then ERCOT will approve or reject no later than Fifteen (15) days prior to start of the proposed Outage or Greater than forty-five (45) days then ERCOT will respond within Thirty (30) days prior to the start of the proposed Outage
Notes: Reliability Must Run (RMR) Service
The provision of generation capacity and/or energy resources from Reliability Must Run Unit or a Synchronous Condenser Unit.
Reliability Must Run (RMR) Unit
A Generation Resource unit operated under the terms of an Agreement with ERCOT that would not otherwise be operated except that they are necessary to provide voltage support, stability or management of localized transmission constraints under first contingency criteria where Market Solutions do not exist.
ERCOT shall approve or reject each RMR Outage request in accordance with the following time lines. If the amount of time between a Request for approval of a proposed Planned Outage and the scheduled start date of the proposed Outage is:
No less than thirty (30) days then ERCOT will approve or reject no later than Fifteen (15) days prior to start of the proposed Outage or
Greater than forty-five (45) days then ERCOT will respond within Thirty (30) days prior to the start of the proposed Outage

## Slide 15: Plan Changes
Planned Outages move and/or change
Scope growth/extends duration
Scope shrink/ shortens duration
Unplanned Outage Incidents occur
“As Needed” Maintenance Outages
Forced Outages
Deratings
Notes: When dealing with long term plans on a wide diversity of equipment under infinitely variable conditions, one must be able to adapt to change.
In the long and mid term time frames,
Planned Outage movement occurs
- Market demands or seasonal requirements sometimes dictate the changing of established schedules
- Scope growth/extended duration situations occur when problems are encountered after outages begin which leads to delays
- Scope shrink/shorter duration situations occur when job progress is achieved ahead of schedule leading to early returns
In the day to day operation of the system,
Unplanned Outage Incidents
- Maintenance issues arise that must be addressed in the near future
- Forced Outages occur when equipment fails or systems do not work properly
- Deratings must be applied when equipment or systems do not perform as expected or designed

## Slide 16: Navigation on Outage Summary Page
Notes: Once the ERCOT Outage Scheduler application is accessed, a summary screen is displayed.
Resources can only see their own resource outages.
TDSP’s can see transmission and resource outages.
The summary starts with the current date but a custom date filter can be applied and other time frames can be viewed.
Multiple pages are available and can be viewed by selecting “Page Up” or “Page Down”.
Show key points of the ERCOT Outage Scheduler
Create New Outage Button
Print Current List Button
Create Custom Filter Button
Resource Station and Unit Name/Identification
Outage Type
ERCOT Status
Start and End Dates
Generation Capacities

## Slide 17: Create New Outage Display Page
Select Create New Outage
Select Type of Outage
Select Continue
Notes: Selecting the “Create New Outage” on the Summary Page will display the “New Outage Request” Menu.
Based upon the type of outage request being submitted, the entry type can be selected and the appropriate page will be displayed.
This menu allows the user to select from the different types of outages depending on their needs.
Derating
Forced
Maint Level 1
Maint. Level 2
Maint. Level 3
Planned

## Slide 18: Planned Outage Entry Example
Notes: When the Outage Entry page is displayed, the type of outage being requested is detailed at the top of the page.
Information includes
Resource identified by common name
* Reason or cause of outage detailed
* Capability or limitation must be defined
* Times and Dates accurately reflect the outage time frame
* Acceptable schedule deviation is estimated if possible

## Slide 19: Forced Outage Example
Notes: Forced Outage and Maintenance Outage requests generate a slightly different entry page but the request entry process is basically the same
Information includes
Resource identified by common name
* Reason or cause of outage detailed
* Capability or limitation must be defined
Times and Dates accurately reflect the outage time frame
Possible end dates are requested

## Slide 20: Maintenance Level 1 Example
Notes: Forced Outage and Maintenance Outage requests generate a slightly different entry page but the request entry process is basically the same
Information includes
Resource identified by common name
* Reason or cause of outage detailed
* Capability or limitation must be defined
Times and Dates accurately reflect the outage time frame
Possible start and end dates are requested
NOTE – If a specific date is known or needed, the requestor can enter the request as a “Planned Outage” for that date. ERCOT can then evaluate the request and approve or deny it as appropriate for the system.
If a Maintenance Outage is requested and a time frame is defined, then ERCOT can evaluate the request and specify the outgae date as best suits the system requirements.

## Slide 21: Maintenance Level 1 Outage Acknowledgement
Notes: When Outage Requests are submitted, an acknowledgement window pops up.
The requestor is asked to verify they are within the protocols guidelines for this outage request and if the request is valid.

## Slide 22: Planned Extension Example
Notes: If a current outage is scheduled to end and it is known that the time frame is going to extend, an extension can be submitted for that outage.
This action effectively ends the current planned outage as of that time and creates a new, extended outage with the new projected date for completion.
This can only b e done within 24 hours of the planned end date/time.

## Slide 23
Bottom Line -
Resource Entities must provide ERCOT a written Planned Outage and Maintenance Outage program for the next twelve (12) months, in an ERCOT provided format updated for a rolling twelve (12) month period.
Planned Outage and Maintenance Outage scheduling data for Resource Facilities shall be kept current.
Updates shall identify any changes to previously proposed Planned Outages or Maintenance Outages and any additional Planned Outages or Maintenance Outage anticipated over the next twelve (12) months.
Forced Outages shall be communicated a quickly and accurately as possible.
Notes: Review of ERCOT Mandates;
Resource Entities must provide ERCOT a written Planned Outage and Maintenance Outage program for the next twelve (12) months, in an ERCOT provided format updated for a rolling twelve (12) month period.
Planned Outage and Maintenance Outage scheduling data for Resource Facilities shall be kept current.
Updates shall identify any changes to previously proposed Planned Outages or Maintenance Outages and any additional Planned Outages or Maintenance Outage anticipated over the next twelve (12) months.
Forced Outages shall be communicated a quickly and accurately as possible

## Slide 24
Questions
?
?