## RMS
Summary of Protocol Boxed Language & Associated PRRs
March 2005 Protocols
PIP/ |  | Protocol |  | Date | Project | [5 empty] | Priority |  |  |  |  | PWG Priority
PRR | PRR Subject | Section | Sponsor | Approved | No. | Status | Sub | Rec | Priority | Rank | 2005 | 2004 | 2003 | 2002 | PWG Comments | 2006
106 | Direct Load Control--no description available | 6.3.2, 18.2.1, 18.7.2 |  |  | ? |  | RMS |  |  |  | 3.3 |  |  |  | keep unfunded until market interest | 3.3
385 | DLC Implementation. This PRR will allow the DLC programs to be appropriately profiled and ERCOT systems to properly process DLC programs. | 18.7.2 | Reliant Energy for Profiling WG | 5/20/03 Approved | No impact (clarifies what the 'DLC project' will do) |  | RMS | With PIP106 |  |  | n/a | n/a | n/a | n/a | keep unfunded until market interest | 3.3
478 | Use of Lagged Dynamic Samples for New Load Profiles. This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. | 18.2.2, 18.2.7 | Reliant | 2/17/04 Approved | 40056 | Unfunded | RMS |  |  |  | 2.2 | 2.1 | n/a | n/a | keep unfunded until market interest | 3.3
PPL Line Items with a PRR that isn't included above
241 | UFE Analysis. 1) Revises the beginning date for UFE analysis in Section 11.5.1 to January 2002. 2) Modifies the language in 11.5.2.1 to accommodate a December 1, 2001 implementation timeline. 3) Adds language in 11.5.2.1 to require TDSPs to leave "old control area" boundary meters in place until UFE analysis zones are defined. Definition of zones to take place after June 1, 2001 but supporting December 1, 2001 deadline. |  |  |  | 30022 | Unfunded | RMS |  |  |  | 3.2 | 3.3 | 2.1 | n/a | Per the UFE Task Force meeting minutes of 9/14/2005, COPS had an action item to revise this area of Protocols. | 1.1
SCRs
PPL Line Items without PRR or SCR
| Mass Customer Transition--project to automate and enhance mass Customer transtions in the market place. |  |  |  | 40038 | Unfunded | RMS |  |  |  | 3.3 | 1.2 | n/a | n/a
| Fix Retail XML Transaction Format to MPs--no description available |  |  |  | 30133 | Unfunded | RMS |  |  |  | 3.3 | 3.3 | 3.3 | n/a
SCR734 | CSA Report for CRs--Provide CR’s with an on-demand extract capability to retrieve CSA (Continuous Service Agreement) data for their DUNS via the ERCOT Portal |  |  |  | 50057 | Unfunded | COPS |  |  |  | 2.1 | n/a | n/a | n/a
SCR737 | Estimated Meter Read Data--Create a calendar month, summary report to be presented at RMS that will provide Market Participants with estimated meter reading information broken-down by TDSP territory and indicating customer class. This report will also indicate the degree to which meter reads occur consecutively across two or more months and the degree to which estimates may straddle Move-Ins and Move-In/Forced Outs. |  |  |  | 50091 | Unfunded | COPS |  |  |  | 3.1 | n/a | n/a | n/a | Estimated meter reads can add to UFE. | 2.1
SCR736 | TML ESIID TXN Portal Flag--Append a data Flag of “P” to the Transaction Type number to indicate when a displayed transaction was generated and transmitted through the Texas Market Link portal by Market Participants, rather than being generated by Market Participant’s system and transmitted in the Market via GISB. |  |  |  | 50100 | Unfunded | COPS |  |  |  | 3.2 | n/a | n/a | n/a
| Retail Enhancements to TML - Phase 4 |  |  |  | 50058 | Unfunded | COPS |  |  |  | 2.1 | n/a | n/a | n/a
| ERCOT Outage Evaluation and Resolution (TDTWG)--project to improve availability and reduce outages in key retail commercial applications. |  |  |  |  | Unfunded | NEW
SCR742 | Automated Retail Transaction Verification-- Build interface to existing Market Certification environment This option involves building automation and an integrated user interface to the existing market certification environment. |  |  |  |  | Unfunded | NEW
| Texas Set 2.2 including Terms and Comnditions reuirements--This is a place holder for new TxSet version 2.2 for 2006 which also includes revisons required to transactions that may be passed in conjunction with T&C rule making. |  |  |  |  | Unfunded | NEW
| Performance Measures Reporting Requirements (changes to Project 24462)--expected project needed to enhance reporting systems as a result of T&Cs requirements effecting PUCT Performance Measures Project 24462 |  |  |  |  | Unfunded | NEW
| System Improvements required by elimination of mulitple ESI ID at single service address--enhancements to market systems to handle multiple services addresses and multiple esiids at an address single |  |  |  |  | Unfunded | NEW
SCR738 | Enhancement to FasTrak Tools--FasTrak is the retail transaction issue resolution tool. However, the system currently in place does not include the capability to track issues by variables such as ESI ID or TDSP, and does not allow determination of issue aging. In addition, the tool cannot be queried and interfacing with the tool is somewhat cumbersome. The FasTrak tool needs to be made more user friendly and enhanced with features that will allow issues to be better tracked and manipulated by Market Participants for purposes of better managing the retail transaction issue resolution process. |  |  |  | 50007 | Planning |  |  | 1.1 | n/a | n/a | n/a
SCR739 | Potential Load Loss--Provide CR’s with a daily extract of customer loss notifications based on ERCOTs receipt of a TDSPs accepted response to a transaction that would cause a CR to lose the customer (and their associated load). The extract would be available via the ERCOT Portal. |  |  |  | 50023 | Not Yet Started |  |  | 1.2 | n/a | n/a | n/a
SCR740 | Enhancements to SCR727--Suggested modifications include, but are not limited to: • Providing usage to CRs for backdated LSE Relationship Changes • Including a file name or number in order to identify the order in which SCR727 files should be loaded by the MP • Auditing capabilities to allow MPs the function to confirm the accuracy of their extracts • Ability to link a dB change back to the source of the change (i.e. FasTrak issue, batch processing) |  |  |  | 50024 | Planning |  |  | 1.2 | n/a | n/a | n/a
565 | Calculation of Losses for Settlement | [13 empty] | BOD approved 5/17. Projects are available to perform work on smaller efforts. Requirements will be reviewed to determine the amount of work. | assume 2005 completion
572 | Weather Sensitivity Classification | [13 empty] | TAC approved 5/5 | assume 2005 completion
536 | Lower IDR Mandatory Installation Threshold | [13 empty] | BOD 12/14/04. Effective 1/1/05. | assume 2005 completion
488 | Weather Responsiveness Determination | [13 empty] | BOD approved. Code completed for 488 however PRR572 changed some threshold values that will require code modifications. Once the PRR572 is approved by the Board, coding may begin on 572. | assume 2005 completion
514 | 12 Month Window for Non-IDR Scaling | [13 empty] | BOD approved. Does not require code modifications but does require data modifications to existing factor values. Due to the significance of the factor values that will be modified, testing needs to be performed before we make the changes in Production. Scheduled for testing in June. | assume 2005 completion
544 | 12 Month Window for Scaling NIDR to IDR | [13 empty] | BOD approved. Does not require code modifications but does require data modifications to existing factor values. Due to the significance of the factor values that will be modified, testing needs to be performed before we make the changes in Production. Scheduled for testing in June. | assume 2005 completion