## Slide 1: TNT TAC Update
Jim Galvin
May 5, 2005

## Slide 2: Disclaimer
The following is ERCOT’s Program Management approach for a project that will incorporate changes to the ERCOT Wholesale Market Design. Since a decision has not been made to determine the Wholesale Market Design requirements, ERCOT will monitor the rulemaking process and prepare for a range of possible market design solutions. A timeline and fine-tuning of the procedures necessary for the implementation of a new market design will be made once a decision is reached at the PUCT.

## Slide 3: Approach
ERCOT will follow internal Program Management procedures to implement the market redesign effort from Planning to Implementation to Execution
ERCOT managed, not vendor managed
Emphasis on touch-points with Market Participants for transparency and knowledge transfer

## Slide 4: Implementation Timeline
The following slides provide a schematic view of a high-level Project Plan outlining the phases discussed in this presentation
Length of time for each phase is not defined in this schematic as requirements are at this time unknown
Project Plan is flexible and subject to change based on input from Market Participants and/or vendors

## Slide 5: Implementation Timeline
Initiation
Prepare project documentation
Scope & staffing
Justification
Approvals
Planning
Extract requirements from the Protocols
Provide requirements to MPs for review
Preliminary requirements
Finalize requirements
MP review of Final requirements
RFP preparation
Vendor demos
Vendor selection
Conceptual Design
MP review of Conceptual Design
Environment Plan
Requirements Development
Finalize Requirements
Provide Conceptual Design to MPs
Issue RFP
Provide requirements to MPs for review
Preliminary Requirements identified
Conceptual Design/Environment Plan
Vendor demos: 10/03 to 11/01
Vendor Selection
MP comments to final requirements due
RFP Process
Doc prep
MP comments to Conceptual Design due

## Slide 6: Implementation Timeline
Execution
Technical Design & Coding
Market Operations (MO)
System Operations (SO)
Enterprise Data Warehouse (EDW)
Unit Test
P-Test
I-Test
Migration Plan
Environment Plan
Market
Training
Trial
Technical Design & Coding/Testing
MO coding complete
MO: Unit Test complete
Begin P-Test
Begin Unit Testing for MO, SO, & EDW
MO: P-Test complete
Begin technical design & coding
SO coding complete
EDW coding complete

## Slide 7: Implementation Timeline
Execution
Technical Design & Coding
Commercial Operations (CO)
System Operations (SO)
Enterprise Data Warehouse (EDW)
Unit Test
P-Test
I-Test
Migration Plan
Environment Plan
Market
Training
Trial
Migration Plan/Environment Configuration
Finalize Environment configuration
Launch
EDW: Unit Test complete Begin P-Test
SO: Unit Test complete Begin P-Test
SO: P-Test Complete
Begin Market Trial
Begin Market Training
Market Training & Trial
Coding & Testing
EDW: P-Test Complete
Begin I-Test for MO, SO & EDW
Complete I-Test for MO, SO & EDW
Finalize Migration Plan

## Slide 8: Market Participant touch-points
Review of:
  Preliminary Requirements
  Final Requirements
  Conceptual Design
Market Training
Market Trials
  Multi-month effort to synchronize communications between MPs & ERCOT.
  Will be a multiple day simulation.

## Slide 9: Initiation Phase
This is the Administrative phase where staff prepares documentation for project start, includes project scope description and justification
Obtain management approvals.
Develop high-level cost & time estimates
Review staffing requirements for project Core Team
Begin Planning Stage

## Slide 10: Planning Phase
Preliminary Requirements
  ERCOT Staff identifies requirements stated in the Nodal Protocols
  Market Participants review and comment on Preliminary Requirements identified by ERCOT
  Complete Statement of Work (SOW) from approved Preliminary Requirements for the RFP process

## Slide 11: Planning Phase (cont’d)
Request for Proposals
  Use preliminary requirements to develop RFP to meet SOW.
  Review vendor(s) proposals and solutions.
  Identify vendor pool to implement appropriate solutions in the areas of System Operations (SO), Market Operations (MO) and Enterprise Data Warehouse (EDW)
  Select appropriate vendors in SO, MO and EDW areas for consideration.

## Slide 12: Planning Phase (cont’d)
Final Requirements
  Final Requirements incorporate vendor solutions and provide additional detail to Preliminary Requirements.
  Market Participants review and comment on Final Requirements.
  Market Participants and ERCOT staff ensure Final Requirements meet SOW requirements.
  Select appropriate vendors for SO, MO and EDW
  Begin Execution

## Slide 13: Planning Phase (cont’d)
Conceptual Design
  ERCOT Staff and selected vendors develop software design based on the Final Requirements.
  Market Participants review and comment on Conceptual Design.
Environment Plan
  An internal ERCOT effort that will evaluate hardware needs and interface impacts.

## Slide 14: Execution Phase
Technical Design & Coding
  Market Operations (MO) – will have substantial internal support from leveraging current systems with vendor assistance
  System Operations (SO) – more than likely vendor driven with internal support & project management
  Enterprise Data Warehouse (EDW) – will have substantial internal support from leveraging current systems with vendor assistance
MO & SO coding can take place concurrently
EDW development will shadow and complete after SO and MO development.

## Slide 15: Execution Phase (cont’d)
Unit Test
  Testing of software during the development stage.
Product Testing (P-test)
  Testing of the completed code.
Integration Testing (I-Test)
  Testing of the completed code as integrated with other systems.

## Slide 16: Execution Phase (cont’d)
Migration Plan
  Develop plan for code migration into the systems.
  Configure system environment for the migration.
  Migration Plan is tested during I-test.