## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of April 4, 2005
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – Starting August ’05
Implementation – Goal December ‘05
Closing – Starting December ‘05
Recent:
Developing process diagrams & an “as is” document with internal users
Next steps:
Meet with MPs in April to verify process flows
Start finalizing detailed requirements, after process diagrams completed
Meet with MPs in May to finalize detailed business requirements
Select enhancement method (upgrade current tool, Siebel or AIM)
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of April 4, 2005
Page 2

## Slide 3
** All target dates will become firm after design is complete and project plan finalized
Requirements – June ’05
Design (published document) – July ’05
Internal Testing – August/November ’05
External Testing – August/November ‘05
Internal Training – November/December ’05
External Training – November/December ‘05
Production (Go live) – December ‘05
High level timeline
PR-50007 Enhancements to FasTrak
As of April 4, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of April 4, 2005
Page 4