## Slide 1
Objectives:
Upgrade Siebel to a supported application
Upgrade Oracle database to current version
Deliver all existing user functionality with no degradation in performance
Scope:
Upgrade Siebel software v6.3 to v7.7
Upgrade Oracle database 8i to 9i
Maintain all existing Siebel functionality from v6.3
Maintain all existing functionality to interfaces (L*, Reports/Extracts, ETS (internal))
Allow developers to more easily enhance system functionality going forward
Deploy thin-client for external Settlement Disputes & Service Requests
Dependencies:
None
Scope / Why is this important?
PR-40066_03 Siebel 7 Upgrade

## Slide 2
Phase:
Initiation – Completed in Sept ‘04
Planning – Completed in January ‘05
Execution – In Progress – Scheduled Implementation April 15-17 ‘05
Closing – Goal to complete early June ‘05
Recent:
Completed internal user training
Began Market Notification of iTest results
Completed Migration Plan including Contingency “Fall-back” options
Next steps:
Complete testing
Begin production migration and data conversion
Summary of Project Status
PR-40066_03 Siebel 7 Upgrade

## Slide 3
Requirements (pens down) – Completed early January ‘05
Final Design (Internal document) – Completed mid February ’05
Build – Completed late February ‘05
Testing – Goal to complete mid April ‘05
Internal Training – Completed mid March ’05
MP Training – Web Cast conducted for Settlement Disputes prior to Deployment
Production (Go live) – April 15-17 ‘05
High level timeline
PR-40066_03 Siebel 7 Upgrade

## Slide 4
Bus Lead: John Kassel
Phone: (512) 248-6516
Email: jkassel@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 15 Program Area: RO
What prompted the project:
This project was a CASUP recommendation approved by ERCOT Executive committee and the ERCOT Board of Directors
Vendor support expired for existing version of Siebel and Oracle in 2004 – cost to maintain becomes significant if major problems arise
Siebel is the Registration system for all ERCOT’s Customers
Current version has limited Portal interaction capabilities
Additional Information
PR-40066_03 Siebel 7 Upgrade

## Slide 5
NOT CHANGING
  Transaction management of all 814 and 867 transactions
  Current workflow of service orders and service instances
  Contact administration and relationship management
  Reports and Extracts
CHANGING
  Service Requests functionality and screen design (Wholesale and Retail)
  Settlement Disputes functionality and screen design (Wholesale)
External Functionality
PR-40066_03 Siebel 7 Upgrade

## Slide 6
At this time, ERCOT anticipates the outage timeframe below for the April Maintenance Retail Release
The timeframe is subject to change and confirmation will be provided prior to the release
Friday, April 15, 2005 through Sunday, April 17, 2005.
During the outage:
All transactions sent to ERCOT WILL be held at the Paperfree server during the outage
867 transactions WILL be forwarded during the outage
NAESB EDM and ANSI responses WILL be sent during the outage (i.e. This includes 997 Functional Acknowledgements)
USA functionality will NOT be available
Retail components of the TML and API will NOT be available (i.e. This includes Find ESI, Find Transaction and Submit Transactions)
Settlement Disputes and Service Requests will NOT be available
ERCOT System Outage Overview
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 7
The shutdown times listed will be strictly adhered to unless prior notice is given to all MPs
All MPs should submit transactions well in advance of the shutdown time so that large transaction volumes are not experienced just prior to shutdown
  (i.e. if you run batch jobs, schedule them throughout the day)!!!
All MPs will have the opportunity to call-in to each conference call during the implementation if they wish to hear a progress update – a roll call will be taken during the calls
All times listed are Central Prevailing Time
Shutdown Procedure
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 8
Friday, April 15th @ 4:00 a.m.
ERCOT will…
  Keep up NAESB and Paperfree
  Shut down XML Mover (for 814 & 824 transactions) and 867 Upload
  Shut down Retail TML components (Find ESI, Find Transaction)
  Shut down TML component for Settlement Disputes – for QSEs
  Shut down TML component for Service Requests
This will isolate TCH processing…
    Inbound MP transactions will be held at Paperfree
        NAESB EDM Response
      ANSI Responses
Held transactions will be converted to XML and staged for TCH
After inbound shut down, all in-flight transactions will continue to be processed and corresponding outbound transactions will be delivered until 8:00 a.m. when outbound processing will be shut down.
Transaction Processing - Inbound
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
ERCOT will continue to send…

## Slide 9
Friday, April 15th @ 8:00 a.m.
ERCOT will…
    Stop sending 814 & 824 transactions
    Begin Siebel code migration and data conversion
Transaction Processing - Outbound
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 10
Saturday, April 16th by 10:00 p.m.
ERCOT will…
  Complete Siebel Migration
  Complete Data Archive Migration
  Complete TML Migration
  Complete EAI Migration
  Technical Verification for all areas
Go / No-Go check points will occur at various times throughout the day
Upgrade Activities
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 11
Sunday, April 17th by 6:00 p.m.
ERCOT will…
  Perform Production Verification
  Identify any remaining activities
  Mitigate any outstanding issues
  Take periodic “Go Live” Check Points
Go Live…
  Turn on all Inbound and Outbound processing
  Begin monitoring transaction flows
Upgrade Activities
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 12
Sunday, April 17th starting @ 8:00 p.m. (if necessary)
High Level Back out Plan…
  Convert Database back from Oracle 9i to Oracle 8i
  Restore Siebel data from April 15th tape back up
  Convert Siebel application servers from v7.7 back down to v6.3
  Restore TML upgrade for Siebel
  Restore TCH/EAI upgrade for Siebel
  Re-initiate settlement disputes with old portal
  Functional Verification of Back out
Upgrade Activities
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 13
Monday (4/11) & Wednesday (4/13) 2:00 p.m. Retail Market Calls
  ERCOT discussion of upcoming shut-down schedule
    (Call-in number 1-800-373-0950 Pass Code 123316)
  CRs & TDSPs to provide status of transaction volumes throughout the week
Friday April 15th @ 8:00 a.m.
Call In #: 1-888-205-5513 Pass code: 159497
  ERCOT transaction processing update
    “in queue”
    “in process”
    Overall system health
Friday April 15th @ 4:00 p.m.
  ERCOT Siebel migration Status report
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Conference Calls

## Slide 14
Saturday April 16th @ 10:00 a.m. & 8:00 p.m.
  ERCOT Siebel migration Status report
  Issues
  Go / No-Go Decision
Sunday April 17th @ 10:00 a.m.
  ERCOT Siebel migration Status report
  Issues
  Go / No-Go Decision
Sunday April 17th @ 8:00 p.m.
  ERCOT Siebel migration Status report
  Issues
  Final Go / No-Go Decision (with possible back out)
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Conference Calls

## Slide 15
Below is the status to-date of the Siebel v7.7 Testing Efforts as of 4/01/2005 in anticipation of the 04/17/2005 roll-out.
  ERCOT has run 96 of 118 v7.7 Test Cases with all applications in iTest for Phase 1 (GUI / CRM / eService / Reporting)
  ERCOT has run 230 of 396 v7.7 Test Cases with all applications in iTest for Phase 2 (Retail Transactions)
  ERCOT has run 627 v7.7 Test Cases to date
ERCOT currently has 15 open defects out of a total of 187 logged…
Note: To date only 16 issues reported required code changes
  0 - Documentation and Script errors or Data
  9 - Bugs (Coding errors requiring application level changes)
  2 - System or Environment related
  4 - Unknown (Root cause not reported or still in analysis)
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Testing Results

## Slide 16
Test Description UAT Performance Retest (Regression)
Transaction Processing 58% (396 scripts) 100% complete NA
eService 100% (11 scripts) 0% complete 50% (43 scripts)
CRM 100% (25 scripts) 0% complete 88% (57 scripts)
GUI 100% (10 scripts) NA 100% (13 scripts)
Retail Metrics Reporting 100% (4 scripts) 0% complete NA
Data Archive Reporting 100% (1 script) NA NA
Internal EDIM Processes 80% (67 scripts) NA NA
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Testing Results