## Slide 1: RMS Lodestar Upgrade UPDATE

## Slide 2: Migration Plan
Approximately 250 migration tasks were completed on Saturday, March 19, for the upgrade.
25 check-points identified, monitored and communicated throughout Saturday.
Upgrade procedure started at 6:30am Saturday (as scheduled)
Upgrade procedure completed at 7:30pm Saturday (2½ hours ahead of schedule)
  Batch for Saturday initiated at 8:30pm
  Roll back option scheduled for 10:00pm Saturday (as needed)
  Drop dead completion time scheduled for 2:00am Sunday
    814_20 Outage was scheduled to end at 2:00am Sunday
    9:30pm Saturday night, Market was notified that Outage was complete.
5 Market calls scheduled (two optional for Sunday, March 20)
  One participant called Sunday, March 20.

## Slide 3: Batch Performance Metrics
PRELIMINARY RESULTS:
  Generate Settlements Statements executed three to four hours earlier than previously experienced.
    Generate usually runs about 1 hour per trade day
    Generate ran for 30 minutes per trade day
  Three trade days executed in 4 hours vs. three trade days in 6.5 hours

## Slide 4: SCR-725 Reporting Issue:
Load Count and Load Volume Report
  Informational report providing information on ESI-ID settlement: actual, historical estimate, default
  One report for the 09/20/04 True-up settlement did not generate and is unrecoverable.
  Now, the reports are processing as expected.
    ERCOT has developed a manual work-around for fall-back purposes.

## Slide 5: Questions/Comments ?
SUCCESS !