## Slide 1: Flight 0405 Update

## Slide 2: Last Flight
Flight 0105
Flight completed on time as scheduled with all testing completed successfully

## Slide 3: Flight 0405 Update
Flight manifest
9 New REPs – 32 New Relationships
6 New Umbrella DUNS – 24 New Relationships
1 Existing REP testing in new territory – 1 New Relationships
0 Existing REP testing new functionalities
2 Existing REPs changing Service Providers
4 Existing REPs changing Banks
1 TDSP changing Banks
About 8000 Tasks total

## Slide 4: Flight 0405 Update
Progress
Flight sign-up deadline was March 9th
Final Test Matrix was sent out March 10th
Test beds were due April 4th
Connectivity Testing began March 15th
Connectivity over 90% complete – on schedule
Readiness for April 11th -- We are a go!

## Slide 5: Flight 0405 Next Steps
Flight Takeoff
Daily kick off call Friday April 8th
Transactions start to flow Monday 4/11 at 8:00 am
Daily status calls - MANDATORY
By May RMS (5/10/05)
Market scheduled to be on Day 22 of Flight 0405
  Connectivity should be complete
  Flight scheduled to be 75.6% complete
By June RMS (6/15/05)
Flight 0405 scheduled to complete on 6/10