## Slide 1
Objectives:
Upgrade Siebel to a supported application
Upgrade Oracle database to current version
Deliver all existing user functionality with no degradation in performance
Scope:
Upgrade Siebel software v6.3 to v7.7
Upgrade Oracle database 8i to 9i
Maintain all existing Siebel functionality from v6.3
Maintain all existing functionality to interfaces (L*, Reports/Extracts, ETS (internal))
Allow developers to more easily enhance system functionality going forward
Deploy thin-client for external Settlement Disputes & Service Requests
Dependencies:
None
Scope / Why is this important?
PR-40066_03 Siebel 7 Upgrade

## Slide 2
Phase:
Initiation – Completed in Sept ‘04
Planning – Completed in January ‘05
Execution – Completed April 18 ‘05
Closing – Goal to complete early June ‘05
Recent:
Completed testing
Migrated all components to Production except eService (new Service Requests and Settlement Disputes functionality)
Next steps:
Continue to monitor transaction processing
Migrate eService component for Service Requests and Settlement Disputes
Summary of Project Status
PR-40066_03 Siebel 7 Upgrade

## Slide 3
Requirements (pens down) – Completed early January ‘05
Final Design (Internal document) – Completed mid February ’05
Build – Completed late February ‘05
Testing – Completed mid April ‘05
Internal Training – Completed mid March ’05
MP Training – Web Cast for Settlement Disputes Completed April 15 ‘05
Production (Go live) – Phase 1 completed April 15-17 ‘05
        Phase 2 scheduled for May 21 ‘05
High level timeline
PR-40066_03 Siebel 7 Upgrade

## Slide 4
Bus Lead: John Kassel
Phone: (512) 248-6516
Email: jkassel@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 15 Program Area: RO
What prompted the project:
This project was a CASUP recommendation approved by ERCOT Executive committee and the ERCOT Board of Directors
Vendor support expired for existing version of Siebel and Oracle in 2004 – cost to maintain becomes significant if major problems arise
Siebel is the Registration system for all ERCOT’s Customers
Current version has limited Portal interaction capabilities
Additional Information
PR-40066_03 Siebel 7 Upgrade

## Slide 5
Below is the status of the Siebel v7.7 Testing Efforts
  ERCOT has run 118 of 118 v7.7 Test Cases with all applications in iTest for Phase 1 (GUI / CRM / eService / Reporting)
  ERCOT has run 396 of 396 v7.7 Test Cases with all applications in iTest for Phase 2 (Retail Transactions)
  ERCOT has run 675 v7.7 Test Cases to date
At the end of UAT, 0 open defects remained out of 209 defects logged… Note: only 19 issues reported required code changes
  8 GUI Post Implementation tests performed
  4 Internal EDIM Post Implementation tests performed
PR-40066_03 Siebel 7 Upgrade
Implementation Results
Testing Results

## Slide 6
Below is the status of the Siebel v7.7 Migration Efforts
  ERCOT executed 34 Upgrade Planning Preparation Tasks
  ERCOT executed 33 Pre-Upgrade Tasks
  ERCOT executed 53 Upgrade Tasks
  ERCOT executed 64 Post-Upgrade Tasks
  ERCOT executed 26 Functional Verification Tasks
There was 1 technical error logged and 1 issue reported throughout the migration (related to TML connectivity to Siebel)…
  30 people from Operations, Networks, DBAs, Infrastructure, and IT Development worked approximately 800 man hours over a 74 hour span, from 4am Friday through 6am Monday, in support of the Migration effort
PR-40066_03 Siebel 7 Upgrade
Implementation Results
Migration Tasks

## Slide 7
Below is the status of the Siebel v7.7 Production Verification Efforts
  ERCOT Transaction Processing executed 30 Scripts
  ERCOT Retail Client Services executed 16 Scripts
  ERCOT Wholesale Client Services executed 28 Scripts
  Approximately 20 people from Transaction Processing, RCS, and WCS worked roughly 250 total man hours in support of the Production Verification effort
8 Conference Calls were scheduled throughout the Migration weekend. Saturday & Sunday Friday & Monday
CRs: 1 3
TDSPs: 3 4
Service Providers: 1(2 CRs) 2 (15 CRs)
PR-40066_03 Siebel 7 Upgrade
Implementation Results
Production Verification

## Slide 8
eService application implementation to be rescheduled (5/21/05)
Tighter firewall security policies created constraints (eService is Web-based)
Finishing testing the resolution
Next Steps…
  Conversion process will begin after normal business hours
  Service Request and Settlement Dispute data will be migrated into Siebel
  TML will be pointed to new database
  eService module will be instantiated
  Production Verification will be performed by RCS and WCS
  Notice will be sent to Market Participants
  Will have no impact on transaction processing
PR-40066_03 Siebel 7 Upgrade
Implementation Update
eService Application