## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of May 3, 2005
Page 1

## Slide 2: Enhancements to FasTrak History
Submit SCR 732
Creation of project team to develop detailed system requirements for an enhanced FasTrak process
June ‘04
Aug ‘04
May ‘04
Jan ‘04
Nov ‘04
Feb ‘05
Met With MPs to Gather Requirements
Met with 14 MPs
Met with MPs to finalize requirements
Initiate PR 50007 & Met with MPs to prioritize requirements
April ‘05
MP Meeting to Review Requirements
MP Meeting to Review Requirements
Submit SCR 738
Creation of project to implement the system requirements for an enhanced FasTrak process as defined in SCR 732
MP meeting to finalize process flows & discuss project implementation date

## Slide 3
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – Starting August ’05
Implementation – January/February ‘06
Closing – February ‘06
Recent:
Developed process diagrams
Start creating “as is” document
Finalizing detailed business requirements
Met with MPs April 27th to verify process flows
Met with MPs to finalize implementation date – January/February 2006
  13 MPs (Q1 ’06), 2 MPs (Dec ’05), 1 MP (Nov ’05)
Next steps:
Meet with MPs in May to finalize detailed business requirements
Select enhancement method (upgrade current tool, Siebel or AIM)
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of May 3, 2005
Page 2

## Slide 4: Retail Ops 2005 Release Plans
Release RO 5.1
PR-40066_03 Siebel Upgrade (1.1)
PR-40019 Retail Testing Website (1.1)
Retail Transaction Process Data Transparency and Rptg
EDIM Retail Market Services
Retail Client Services Retail Market Reporting
ESI ID Retail – WS Sync
Retail Market Testing
Siebel
EAI (SeeBeyond/TIBCO)
TCH
PaperFree
Market Testing
Stakeholders
Systems
Q2 ‘05
Q3 ‘05
Q1 ‘05
Q4 ‘04
Q4 ‘05
Q1 ‘06
Release RO 5.3
Release RO 5.2
PR-40106 ERCOT.com (1.1)
ER-50026 SIR Enhancements (1.2)
PR-40034 Texas SET 2.1 (1.1)
Release 5.3
PR-50007 SCR 738 (1.1) Enhancements to Fast Trak
MR-50023 Potential Load Loss (1.2)
Release RO 5.1
Release RO 5.2
Release RO 6.0 SOA
Release RO 6.0
PR-50121 Service Oriented Architecture (1.1)
Including sub-projects of PR-50121
  PR-50121_03 Market Information Distribution
  PR-50121_04 Framework Services
  PR-50121_05 CSA

## Slide 5
** All target dates will become firm after design is complete and project plan finalized
Requirements – June ’05
Design (published document) – July ’05
Internal Testing – December ’05 – January ’06
External Testing – December ’05 – January ‘06
Internal Training – January ‘06
External Training – January ‘06
Production (Go live) – January/February ‘06
High level timeline
PR-50007 Enhancements to FasTrak
As of May 3, 2005
Page 3

## Slide 6
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of May 3, 2005
Page 4