## Slide 1: Flight 0405 Update

## Slide 2: Flight 0405 Update
Flight manifest
9 New REPs – 32 New Relationships
6 New Umbrella DUNS – 24 New Relationships
1 Existing REP testing in new territory – 1 New Relationships
0 Existing REP testing new functionalities
2 Existing REPs changing Service Providers
4 Existing REPs changing Banks
1 TDSP changing Banks
About 8000 Tasks total

## Slide 3: Flight 0405 Update
Progress
Flight sign-up deadline was March 9th
Final Test Matrix was sent out March 10th
Test beds were due April 4th
Connectivity complete
As of 4/29 – Flight is 47.6% complete
Week 1 complete
Week 2 99.5% complete
Week 3 90.3% complete

## Slide 4: Flight 0405 Next Steps
By June RMS (6/15/05)
Flight 0405 scheduled to complete on 6/10
Next Flight - 0705
Orientation Meeting June 1st, 2005
Flight Deadline – June 8th, 2005
Connectivity Kick-off – June 14th, 2005
Flight Kick-off – June 24th, 2005