## Slide 1
EXECUTION
Site Acceptance Testing in progress
INITIATION TO PLANNING WITH NO CAPITAL BUDGET YET APPROVED
Project Scope/Deliverables
Timeline
Issues / Actions
Financial Milestones as of 2/28/05
Executive Summary of Status
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Activity | Frcstd. Completion Date | % Complete | Status
Scope Lock | 5/28/04 | 100% | Complete
Detail Design | 10/29/04 | 100% | Complete
Build and Unit Test | 12/3/04 | 100% | Complete
Pre-FAT | 1/24/05 | 100% | Complete
Factory Acceptance Test | 3/11/05 | 100% | Complete
Site Acceptance Test | 4/4/05 thru 5/13/05 | 70% | In progress
User Acceptance Test | 5/16/05 thru 5/20/05 | 0% | Not Started
Market Participant Test | 5/18/05 thru 6/1/05 | 0% | Not Started
Production Migration | 6/9/05 | 0% | Not started
Sponsor: Saathoff
Bus Lead: Patterson
Last Update
This Update
Bus Align/ Scope Risk
Technical Risk
Schedule Risk
Staffing Risk
Financial Risk
Overall
G
Y
G
G
G
R
G
G
G
G
 | Approved Budget |  |  | Current Forecast / Actual |  | 
 | Capital | Expense | Total | Total Forecast | Committed to Date | Actual to Date
Labor |  |  |  |  |  | 
AREVA Labor |  |  |  |  |  | 
HW |  |  |  |  |  | 
SW |  |  |  |  |  | 
Other |  |  |  |  |  | 
Total |  |  | 7,657,633 |  |  | 
X
Updated
G
G
G
10 major deliverables from AREVA (MOS–5, POS-4, PUCT-1) + 7 internal sub projects (4 Billing & Settlements, 3 DA/DW)
Billing & Settlements development underway. OOM Tool Enhancements planning near completion.
DA/EDW planning completed.
XML Specifications released 2/2/05.
Market Participant Test
Test Preparation Survey [5/9/05-5/13]
Confirm Test URL/IP addresses
MP “Test” Listeners Connectivity
Release 4 XML Testing
G
Y

## Slide 2: Deliverables
Market # | Project # | Project Title
PIP137 PRR211 | PR-20130 | PIP137/PRR211 Association of BE Bids with RPRS
PRR413 | PR-30161 | PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process
 | PR-30085 | Special Protection Schemes
PRR359 | PR-30131 | Resource Plan Improvement (Phase II)
PRR342 PRR414 | PR-30140 | AS Simultaneous Selection
PRR423 | PR-30162 | PRR423 - Dispatch of Generation Resources Below Minimum Operating Level
PRR422 | PR-30163 | PRR422 - OOM Zonal Dispatch Instructions
 | PR-40049* | Improve Data Elements for Local Constraints & OOMs
 | PR-40095 | Enhancement to OOM tools for congestion management
 | PR-40048 | EMMS Parameters Capture for MMS Reclear Fidelity
PRR485 | PR-40050 | Unit Specific Bid Limits based on Generic Costs
 | PR-40051 | OOM Participation in Providing Ancillary Services
 | PR-40062 | PUCT Upgrade SPD
 | PR-40072 | PUCT Add Corrected MCPEs to the MOS dbase and pass to MMS
 | PR-40092 | Improve Power System Model Maintenance via Database Archive Comparison
 | PR-40096 | Improvements to VSA/DSA
Notes: |  | 
* A Business Process will be put in place to address standardization of Constraint Names. |  | 

## Slide 4
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 9 – 13: Test Preparation Survey
MAY 16 – 20: Confirm Test URL/IP addresses
MP “Test” Listeners Connectivity
MAY 18 – 20: Unstructured Testing on MOTE
MAY 23 – JUNE 1: Release 4 XML Testing
Structured Notification Tests
Unstructured Testing on MOTE
MP Test Plan

## Slide 5
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 9 – 13: Test Preparation Survey
MP Test Plan
INFORMATION REQUEST
Testing QSE
Primary Test Lead [Name, phone, cell#, email]
Secondary Test Contact [Name, phone, cell#, email]
Name of Product [in-house or product name]
Confirm Test Digital Certificate is current
Test Sender URL/IP Address
Test Listener URL/IP Address for those requesting to receive notifications
List Release 4 changes intending to test
List OOM notifications interested in testing
Resource ID for OOME Notification Test

## Slide 6
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 9 – 13: Distribute Example XML
MP Test Plan
Sample OOM Deployments
Sample RPRS Bid and Award.

## Slide 7
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 16 – 20: Confirm Test URL/IP addresses
MP “Test” Listeners Connectivity
MP Test Plan
Schedule test of QSE’s TEST listener with ERCOT Account Manager.
Test will be scheduled on internal test calendar.
Contact information for ERCOT test lead will be provided to QSE Test Lead.
Problems with connectivity with ERCOT MOTE needs to be addressed starting with ERCOT Help Desk.

## Slide 8
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 18 – 20: Unstructured Testing on MOTE
[ 08:00 – 17:00 CPT ]
MP Test Plan
QSE’s who have confirmed connectivity with ERCOT MOTE may begin testing on Release 4.
ERCOT Release 4 TEST LAB will NOT be manned during this time.
Problems with connectivity with ERCOT MOTE needs to be addressed starting with ERCOT Help Desk.
Questions regarding Release 4 XML specification may be addressed to ERCOT Account Manager.

## Slide 9
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MAY 23 – JUNE 1: Release 4 XML Testing
[ 08:00 – 17:00 CPT ]
Structured Notification Tests & Unstructured Testing
MP Test Plan
QSE’s who have confirmed connectivity with ERCOT MOTE may test Release 4 (Unstructured Testing).
ERCOT Release 4 TEST LAB WILL be manned during this time.
Structured Notification testing will be scheduled and performed through contact with the TEST LAB.
Problems with connectivity with ERCOT MOTE needs to be addressed starting with ERCOT Help Desk.

## Slide 10
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MP Test Plan