## Slide 1: Customer Transition Activity Report to RMS
June 15, 2005

## Slide 2: Topic Outline
Goals of Transition Process:
  Minimize the impact to the affected customers and the Market Participants
  Transition customers to a new REP or POLR as soon as possible
Rules Guiding Customer Transition
Timeline of events involved in customer transition.
Opportunities for improvement in the transition process.

## Slide 3: Rules
PUCT Substantive Rule §25.43(d)(2)(B) states:
  the Provider of Last Resort (POLR) will serve as the provider to “[a]ny customer not receiving service from its selected REP for any reason other than non-payment who is automatically assigned to the POLR.”
Protocol Section 15.1.2.9 states:
  Certain circumstances may arise during the course of business in the Texas retail electric market that may necessitate the transition of ESI IDs from one CR to another in quantities and on a time frame that is not completely supported by standard market transactions or business processes. For a detailed outline of the business process and responsibility of all Entities involved in the transition, refer to the approved RMS Retail Customer Transition procedures documented in the Retail Market Guide.
Retail Market Guide contains a document entitled, “Retail Customer Transition Business Process” which sets forth the transition process when such an event occurs.

## Slide 4: Timeline for Customer Transition
Thursday, May 5th
Qualified Scheduling Entity (QSE) gave ERCOT the required Five (5) Business Day notice to terminate its relationship with a Retail Electric Provider (REP). (Protocol Section 16.2.4.3)
REP required to identify new QSE or post collateral with ERCOT. (Protocol Section 16.2.13.3)
Wednesday, May 11th
Deadline for REP to post collateral with ERCOT passed.

## Slide 5: Timeline for Mass Transition
Thursday, May 12th
With permission and participation of affected REP and PUCT, ERCOT initiated a discussion with all affected Providers of Last Resort (POLRs) and Transmission and/or Distribution Service Providers (TDSPs) about a possible Mass Transition event.
ERCOT began working with REP to validate ESI ID population.
REP indicated there were discussions with another REP to acquire percentage of their existing ESI IDs.
ERCOT requested that the REP provide information regarding the population of ESI IDs to be dropped to the POLR as early as possible May 16.
As of midnight, affected REP was no longer represented by a QSE.

## Slide 6: Timeline for Mass Transition
Friday, May 13th
Affected REP was no longer represented by a QSE.
  REP in default of LSE agreement with ERCOT.
    Pursuant to contract, REP has Three (3) Business Days to cure.
  REP’s Load becomes Unaccounted for Energy (UFE) by allocating it across QSEs’ Adjusted Meter Load, using the UFE allocation methodology. (Protocol Section 11.4.6)
    Load approximately 350 MWhs per day
    Total number of ESI IDs involved is less than 3,000.
ERCOT continued transition discussions with PUCT, REP, all POLRs and TDSPs.
ERCOT worked with TDSPs to validate ESI ID population.

## Slide 7: Timeline for Mass Transition
Monday, May 16th
REP confirmed template to provide ERCOT the list of ESI IDs to transition to another REP and to POLRs
  REP confirmed will provide information needed by POLRs to submit off-cycle switch transactions.
  REP confirmed information would be provided by End of Day.
ERCOT began facilitating daily calls and checkpoints with PUCT and impacted TDSPs and POLRs.

## Slide 8: Timeline for Mass Transition
Tuesday, May 17th
ERCOT received customer information to pass along to POLRs from the REP early AM.
  Data issues prevented the REP from providing entire list.
ERCOT provided each POLR its first list of the ESI IDs and information provided from REP by noon.
POLRs began submitting off-cycle switches to gain ESI IDs.
ERCOT received final customer information lists from REP early PM.
ERCOT provided each POLR its second list of additional ESI IDs by 4:30pm.
ERCOT provided a list of ESI IDs to each affected TDSP for its monitoring/planning purposes.

## Slide 9: Timeline for Mass Transition
May 17th - June 9th
POLRs submit off-cycle Switches to gain ESI IDs.
  One POLR utilized Move-In transactions.
  POLR submission times:
    Three POLRs submitted same or next day as receipt of lists.
    One POLR submitted within 3 – 4 business days.
    One POLR submitted within 4 – 5 business days.
ERCOT has facilitated daily check-points with PUCT, POLRs, TDSPs, and other REPs.
Continuous monitoring by all parties involved.
ESI IDs transitioning away from Defaulting REP.

## Slide 10: Current Status
Transition Complete:
All ESI IDs have transitioned away from defaulting REP to POLR or another REP.
100% of ESI IDs were transitioned away by June 9th.

## Slide 11: Transition Timeline
QSE
Notice
Th 05/12
Th 5/5
REP must post collateral
M 05/16
Tu 05/17
Th 06/09
Transition completed
Transition of Customers
Provide list of affected ESI IDs; POLRs begin submitting transactions
W 5/11
QSE representation ends
F 05/13
W 06/01
Load becomes UFE; ERCOT continues to work with involved parties
Daily checkpoints
begin
99.4% of ESI IDs scheduled to have transitioned

## Slide 12: Opportunities for Improvement
Through this event, the following issues with the process have been identified:
Clarity of responsibility of transition tasks and timelines to complete tasks
Clarity of timeline, including defining the trigger point and an effective date for the transition
Timeline for QSE notice of termination of LSE
Timeline could extend dramatically depending on holidays, weekends or other “non-business” days
Review of market rules for Settlement of load, contribution of to UFE, and UFE allocation
Need cooperation of losing REP for process to work smoothly
  REP has Three (3) business days to cure default under LSE agreement
  REP possesses all the important customer data

## Slide 13: Timeline
QSE
Notice
Th 05/12
Th 5/5
REP must post collateral
M 05/16
Tu 05/17
Th 06/09
Transition completed
Transition of Customers
Provide list of affected ESI IDs; POLRs begin submitting transactions
W 5/11
QSE representation ends
F 05/13
W 06/01
Load becomes UFE; ERCOT continues to work with involved parties
Daily checkpoints
begin
99.4% of ESI IDs scheduled to have transitioned
Clarity of timeline (includes trigger point) and QSE notification review
Clarity of responsibility of transition tasks & timelines to complete tasks (includes effective date of transition)

## Slide 14: Joint Task Force
TAC at its June 2nd meeting, created a Joint Task Force between RMS and WMS to review through Market Participant Default and customer transition issues.
Market Participant Default Joint Task Force Meeting:
  Thursday, June 23, 2005
  9:30 am – 2:30 pm
  Comfort Suites

## Slide 15: Questions