## Slide 1: Flight 0705 Update

## Slide 2: Last Flight
Flight 0405
Flight completed on time as scheduled with all testing completed successfully

## Slide 3: Flight 0705 Update
Flight manifest
2 New REPs – 7 New Relationships
3 New Umbrella DUNS – 13 New Relationships
5 Existing REP testing in new territory – 5 New Relationships
1 Existing REP testing new functionalities
1 Existing REPs changing Service Providers
3 Existing REPs changing Banks
About 4800 Tasks total

## Slide 4: Flight 0705 Update
Progress
Flight sign-up deadline was June 8th
Test Matrix was sent out June 10th
Test beds are due June 20th
Connectivity Testing will begin June 14th
Readiness for June 27th -- We are a go!

## Slide 5: Flight 0705 Next Steps
Flight Takeoff
Connectivity begins June 14th
Daily kick off call Friday June 27th
Transactions start to flow Monday June 30th at 8:00 am
Daily status calls - MANDATORY
By July RMS (7/13/05)
Market scheduled to be on Day 13 of Flight 0705
  Connectivity should be complete
By August RMS (8/10/05)
Market scheduled to be on Day 33 of Flight 0705
Flight 0705 scheduled to complete on 8/11