## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of June 9, 2005
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – August 17, 2005
Implementation – January/February ‘06
Closing – February ‘06
Recent:
Met with MPs 3 times to finalize business requirements
Schedule vendor demonstrations for June 13th – 22nd
Finalized detailed business requirements on June 10th
Next steps:
Finalize product selection (June 24th)
Finalize conceptual design (Mid July)
Finalize detailed design (August 17th)
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of June 9, 2005
Page 2

## Slide 3
** All target dates will become firm after design is complete and project plan finalized
Requirements – June ’05
Design (published document) – July ’05
Internal Testing – December ’05 – January ’06
External Testing – December ’05 – January ‘06
Internal Training – January ‘06
External Training – January ‘06
Production (Go live) – January/February ‘06
High level timeline
PR-50007 Enhancements to FasTrak
As of June 9, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of June 9, 2005
Page 4