## Slide 1: Residential Survey Task Force
Update to RMS
June 15, 2005

## Slide 2: Survey Update
Completed:
  Approval of Survey at May TAC meeting.
  Bilingual versions of the cover letter and survey.
  ERCOT website content and coding. Website posted.
  Procurement activities with the firm to provide names for sampled addresses.
  Procurement activities with selected Market Research firm.
  Survey population (stratified by profile type and weather zone) has been identified and addresses are being validated against databases.
  Files delivered to Market Research firm for Pilot.

## Slide 3: Survey Update
In Progress:
  Code development to validate responses regarding heating type.
Other:
  June 9 is the anticipated mailing date for the Pilot. Survey results are expected 4 weeks after the mailings.
  During the Phase I, the contact number provided on the survey form and website will direct respondents to ERCOT’s Load Profiling staff.
Next Steps:
  Analyze results from Phase I Pilot Survey
  Recommend a Go/No-Go decision based upon accuracy, required response rate and budget constraints

## Slide 4: Projected Residential Survey Timeline
Conduct Pilot Survey
RSTF/RMS Review
TAC Review
Conduct Full Survey
Responses provided to ERCOT
ERCOT analysis of survey responses
PWG review of analysis
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC