## Slide 1: Project Updates to DEWG
Jackie Ashbaugh
ERCOT
June 16, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Project Updates
PR 50007 - FasTrak
PR 40106 - ERCOT.com
PR 50024 - Enhancements to SCR 727 (SCR 740 Web Service for ESIID data)
PR 40007 - SCR727 move from Data Archive to ODS
PR 30026 - EPS Meter Data Extract/Resource ID Extract
PR 40042_06 - Lodestar Batch Extracts
2005 Upcoming Projects
TBD
Necessary Project Updates?
TBD
Projects
ERCOT Project Updates
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
PR-50007 Enhancements to FasTrak
  Planning Phase
  Implementation scheduled for 1st Qtr. 2006 – Market Decision for delivery
  Met with Market Participants three times in May/June
    Completed a review of FasTrak process flows & enhancements
  Vendor demos scheduled for 06/13 - 06/22
  Product selection will occur after requirements are finalized
  Finalizing detailed business requirements for signoff on 06/20
  Next Steps:
    Finalize Product Selection by 06/24
    Finalize Conceptual Design mid July
    Finalize Detailed Design by 08/17
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
PR-40106 ERCOT.com
  Planning phase
  Selected Serena Software’s CMS product & Google Appliance search
    Google Search Appliance and TIBCO are independent of one another. They could work together, but at ERCOT they will not be working together.
  Finalized contracts with CIBER who began work at ERCOT on 06/06
  Began purchase process for Google Search Appliance
  Implemented Serena’s CMS product
  Next Steps:
    Install Google Search Appliance
    Begin Execution phase
      Start work on resigning ERCOT’s public website
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
PR-50024 Enhancements to SCR 727
  Execution phase
  Finalizing business and development analytical design for phase 1 (Business Intelligence Layer – query logic)
  Developing design of Queuing Theory for web service request prioritization
  Drafting analytical design for phase 2 (Services – architecture)
  Implementation date: 02/2006
  Next Steps:
    Build for phase 1 & 2
    Begin developing test scenarios
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Internal ERCOT Projects to move Lodestar Extracts to ODS
  Extracts included:
    SCR 727 ESIID Extract
    EPS Meter Data Extract aka Resource ID Extract
    Load Extract
    Generation Extract
    Settlements & Billing Extract
    Settlement Input Data Extract
    Public Reference Data Extract
    Shadow Pricing Extract
  ERCOT design recommendation for data time frame and creation timings for all the Lodestar extracts presented to DEWG 5/12/2005 and COPS 5/24/2005
    Design updated after meeting with COPS
  Goal is to implement all Lodestar Extracts out of the ODS environment by the end of 2005
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
Updated Lodestar Extracts Timeline
  Same impact to dispute timeline as the current extract timeline
  Improved impact to dispute timeline for trade dates with backouts/reruns
  Repeatable process
  Daily extracts posted everyday
  Compliant with existing protocols
  Extracts include complete, approved trade date data that correspond to Settlement Statements
  Synchronized postings for SCR 727 and RID extracts to Load, Generation, and Settlements & Billing extracts
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
PR-40007 SCR 727 Phase 2
  SCR 727 ESIID Extract, Public Reference Data Extract
  Execution phase
  Develop a market level data extract called Public Reference Data Extract to include all non-interval market data provided in RID, SCR 727, Load, Generation, and Settlements & Billing Extracts
  Developing Analytical Design; incorporate extract timeline
  Market question for MRE/TDSP:
    Currently, market participants that are MREs, but not the TDSPs of an ESIID receive a separate MRE extract. With the move to the ODS, ERCOT would like to propose that the MRE and TDSP extracts be merged to provide one extract file per DUNs number.
  Next Steps:
    Complete Analytical Design and Detailed Design
    Start the build
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
PR-30026 EPS Meter Data Extract/Resource ID Extract
  RID Extract
  Execution phase
  Testing data ownership logic
  Developing the timing logic for when to run and what data to include in each extract
  Next Steps:
    Develop/Complete the updates for the extract creation and delivery timings
    Add necessary test cases and retest extract
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11
PR-40042_06 Lodestar Batch Extracts
  Load, Generation, Settlements & Billing, Settlement Input Data and Shadow Pricing
  Execution phase
  Redefining business requirements to meet the needs of providing complete, approved batch of trade dates on a daily basis
  Incorporate extract timelines into design
  Development of Initial and daily extracts logic process
  Develop a Settlement Input Data Extract to include the Settlement data that is not related to the batch runs being provided in the Settlement & Billing Extract aka day after operating day data
  Next Steps:
    Complete business requirements changes
    Develop all extract timing logic triggers
Notes: <number>
<footer>
<header>
<date/time>