## Slide 1
COPS UPDATE / ACTION ITEMS
PRR 568 Implementation Plan
Migrate Initial Settlements from 17 to 10 Days
June 28, 2005
(Action Item Slides noted in top left corner)

## Slide 2: PRR 568 Implementation Plan
Analysis period to determine expected impact when initial settlements are reduced from 17 to 10 days
  Credit Impact (next several slides)
  Market participant impact (ref. Implementation Schedule slide)
Determine market consensus on threshold that would suggest recommendation to TAC to stop the migration to day 10
Initial Settlement Statement publication begins reducing from 17 days to 10 days over a seven week period starting during the week of 2/1/06
Seven (7) weekly invoices published beginning on 2/9/06 will contain eight (8) initial Settlement Statements instead of the current seven (7)

## Slide 3: PRR 568 – Credit Impact Analysis
ERCOT staff provided impact analysis on collateral requirements when initial settlements are reduced from 17 to 10 days (after any interim steps)
Reductions in collateral will be realized as long as the quality of data utilized for the credit calculations is substantially the same as the current quality
Estimated Aggregate Liability (EAL)
  Initials
  True-ups
  Finals
  Outstanding Invoices

## Slide 4: PRR 568 – Credit Impact Analysis EAL Collateral Requirements
Reduce EAL calculation by 7 days
  When PRR 568 is implemented, EAL initials will be reduced from 40 to 33 days
Reduce Aggregate Net Load Imbalance Liability and Net Resource Imbalance Liability (NLRI) calculation by 7 days
  When PRR 568 is implemented, NLRI will be reduced from 28 to 21 days

## Slide 5: PRR 568 – Credit Impact Analysis EAL Calculation

## Slide 6: PRR 568 – Credit Impact Analysis Collateral Requirements
During the transition period, adjustments will be made to EAL and NLRI credit calculations as needed
Adjustments will be made to TNT Protocols Section 16 credit calculations

## Slide 7: PRR 568 Implementation Plan Schedule
Analysis Period: | ERCOT begins provides Ch 0 cuts for Load and Generation Extracts 1st 30 day run in Aug 2005 2nd 30 day run Sept 15 to Oct 15, 2005 Ch 0 is a day 8 aggregation, the data that would be used for day 10 settlement ERCOT provides reporting similar to Report provided at COPS Feb 2005 mtg Market Participants exchange ideas observations of Ch 0 cuts in conference calls every 2 weeks The 1st call to occur approximately 20 days after the first date Ch 0 data was made available
Nov 15, 2005 | Market Participants end Ch 0 analysis
Dec 1, 2005 | COPS recommendation to TAC if desired to change the Jan 15, 2006 implementation schedule for PRR568
Jan 17, 2006 | Trade Date to Start the migration to Day 10 Initial Settlement, Publication of binding Settlement Statement for this date would be February 1, 2006
Task Force Recommends the following Schedule for COPS Vote:
ACTION

## Slide 8: PRR 568 Implementation Plan
ACTION
The following Metrics have been discussed by the Task Force and require COPS decision:
  Review Market Wide UFE comparing Day 10 to Day 17 results - Suggestion to make this limit ???%
  Review difference in number of meters Market Wide that would be estimated at Initial Settlement – Suggestion to make this limit ???%
  Any Individual Market Participant shift in settlement impact would not exceed ???%
COPS Discussion and Action needed for setting Triggers that would lead to recommendation for TAC to authorize stopping the migration to Day 10 Initial Settlement

## Slide 9: PRR 568 Proposed Settlement Statement Calendar
Operating Day | Initial Statement Publication Date | Days from Operating Day to initial Statement | Invoice Date
1/13 | 1/30 | 17 | 2/9
1/14 | 1/31 | 17 | 2/9
1/15 | 2/01 | 17 | 2/9
1/16 | 2/02 | 17 | 2/9
1/17 | 2/02 | 16 | 2/9
1/18 | 2/03 | 16 | 2/9
1/19 | 2/06 | 18 | 2/9
1/20 | 2/06 | 17 | 2/9
1/21 | 2/06 | 16 | 2/16
1/22 | 2/07 | 16 | 2/16
1/23 | 2/08 | 16 | 2/16
1/24 | 2/09 | 16 | 2/16
1/25 | 2/09 | 15 | 2/16
1/26 | 2/10 | 15 | 2/16
1/27 | 2/13 | 17 | 2/16
1/28 | 2/13 | 16 | 2/16
Task Force Recommends the following Calendar for COPS Vote:
ACTION

## Slide 10
Operating Day | Initial Statement Publication Date | Days from Operating Day to initial Statement | Invoice Date
1/29 | 2/13 | 15 | 2/23
1/30 | 2/14 | 15 | 2/23
1/31 | 2/15 | 15 | 2/23
2/1 | 2/16 | 15 | 2/23
2/2 | 2/16 | 14 | 2/23
2/3 | 2/17 | 14 | 2/23
2/4 | 2/20 | 16 | 2/23
2/5 | 2/20 | 15 | 2/23
2/6 | 2/20 | 14 | 3/2
2/7 | 2/21 | 14 | 3/2
2/8 | 2/22 | 14 | 3/2
2/9 | 2/23 | 14 | 3/2
2/10 | 2/23 | 13 | 3/2
2/11 | 2/24 | 13 | 3/2
2/12 | 2/27 | 15 | 3/2
2/13 | 2/27 | 14 | 3/2
PRR 568 – Proposed Settlement Statement Calendar (Continued)
ACTION

## Slide 11: PRR 568 – Proposed Settlement Statement Calendar (Continued)
Operating Day | Initial Statement Publication Date | Days from Operating Day to initial Statement | Invoice Date
2/14 | 2/27 | 13 | 3/9
2/15 | 2/28 | 13 | 3/9
2/16 | 3/01 | 13 | 3/9
2/17 | 3/02 | 13 | 3/9
2/18 | 3/02 | 12 | 3/9
2/19 | 3/03 | 12 | 3/9
2/20 | 3/06 | 14 | 3/9
2/21 | 3/06 | 13 | 3/9
2/22 | 3/06 | 12 | 3/16
2/23 | 3/07 | 12 | 3/16
2/24 | 3/08 | 12 | 3/16
2/25 | 3/09 | 12 | 3/16
2/26 | 3/09 | 11 | 3/16
2/27 | 3/10 | 11 | 3/16
2/28 | 3/13 | 13 | 3/16
3/1 | 3/13 | 12 | 3/16
ACTION

## Slide 12: PRR 568 – Proposed Settlement Statement Calendar (Continued)
Operating Day | Initial Statement Publication Date | Days from Operating Day to initial Statement | Invoice Date
3/2 | 3/13 | 11 | 3/23
3/3 | 3/14 | 11 | 3/23
3/4 | 3/15 | 11 | 3/23
3/5 | 3/16 | 11 | 3/23
3/6 | 3/16 | 10 | 3/23
3/7 | 3/17 | 10 | 3/23
3/8 | 3/20 | 12 | 3/23
3/9 | 3/20 | 11 | 3/23
3/10 | 3/20 | 10 | 3/30
3/11 | 3/21 | 10 | 3/30
3/12 | 3/22 | 10 | 3/30
3/13 | 3/23 | 10 | 3/30
3/14 | 3/24 | 10 | 3/30
3/15 | 3/27 | 12 | 3/30
3/16 | 3/27 | 11 | 3/30
ACTION

## Slide 13
Operating Day | Initial Statement Publication Date | Days from Operating Day to initial Statement | Invoice Date
3/17 | 3/27 | 10 | 4/6
3/18 | 3/28 | 10 | 4/6
3/19 | 3/29 | 10 | 4/6
3/20 | 3/30 | 10 | 4/6
3/21 | 3/31 | 10 | 4/6
3/22 | 4/03 | 12 | 4/6
3/23 | 4/03 | 11 | 4/6
PRR 568 – Proposed Settlement Statement Calendar (Continued)
ACTION