## Slide 1
EXECUTION
Site Acceptance Testing continues.
INITIATION TO PLANNING WITH NO CAPITAL BUDGET YET APPROVED
Project Scope/Deliverables
Timeline
Issues / Actions
Financial Milestones as of 5/31/05
Executive Summary of Status
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Activity | Frcstd. Completion Date | % Complete | Status
Scope Lock | 5/28/04 | 100% | Complete
Detail Design | 10/29/04 | 100% | Complete
Build and Unit Test | 12/3/04 | 100% | Complete
Pre-FAT | 1/24/05 | 100% | Complete
Factory Acceptance Test | 3/11/05 | 100% | Complete
Site Acceptance Test | 4/4/05 thru 8/2/05 | 50% | In progress
User Acceptance Test | 8/3/05 thru 8/9/05 | 0% | Not Started
Market Participant Test | 8/10/05 thru 8/23/05 | 0% | Not Started
Production Migration – EMS | 6/15/05 | 0% | Testing
Production Migration - MMS | 8/25/05 | 0% | Not started
Sponsor: Saathoff
Bus Lead: Patterson
Last Update
This Update
Bus Align/ Scope Risk
Technical Risk
Schedule Risk
Staffing Risk
Financial Risk
Overall
G
Y
G
G
G
R
G
G
G
G
 | Approved Budget |  |  | Current Forecast / Actual |  | 
 | Capital | Expense | Total | Total Forecast | Committed to Date | Actual to Date
Labor |  |  |  |  |  | 
AREVA Labor |  |  |  |  |  | 
HW |  |  |  |  |  | 
SW |  |  |  |  |  | 
Other |  |  |  |  |  | 
Total |  |  |  |  |  | 
X
Updated
G
G
G
10 major deliverables from AREVA (MOS–5, POS-4, PUCT-1) + 7 internal sub projects (4 Billing & Settlements, 3 DA/DW)
Billing & Settlements development underway. OOM Tool Enhancements planning near completion.
DA/EDW planning completed.
XML Specifications released 2/2/05.
Market Participant Test
Client Relations will re-establish timeline.
G
Y

## Slide 2: Deliverables
Associated PRR # | Project Title
PRR211 | Association of BE Bids with RPRS
PRR413 | Optimization for the Whole Operating Day in RPRS Procurement Process
PRR359 | Resource Plan Improvement (Phase II)
PRR485 | Unit Specific Bid Limits based on Generic Costs
PRR342 PRR414 | AS Simultaneous Selection
PRR423 | Dispatch of Generation Resources Below Minimum Operating Level
PRR422 | OOM Zonal Dispatch Instructions
 | Enhancement to OOM tools for congestion management
 | Improve Data Elements for Local Constraints & OOMs
 | EMMS Parameters Capture for MMS Reclear Fidelity
 | OOM Participation in Providing Ancillary Services
 | PUCT Add Corrected MCPE’s
 | PUCT Upgrade SPD
 | Special Protection Schemes
 | Improve Power System Model Maintenance via Database Archive Comparison
 | Improvements to VSAT/TSAT

## Slide 3: Issues Impacting Schedule
Poor quality delivery from AREVA
  OOM SAT uncovered over 30 new critical or high software problems (SPR’s)
  198 SAT SPR’s identified (18 Crit’s, 85 High’s, 39 Med’s, 56 Low’s)
  AREVA’s fix of SAT SPR’s created new ones
  Continued Break/Fix process surrounding OOM
ERCOT changes
  18 approved CCM’s submitted between start of FAT (February) and now
Aggressive Schedule
  Not enough time scheduled to fix FAT/SAT SPR’s
Unplanned Events
  3rd iteration to correct SPR’s (April 29th, May 24th and June 22nd)