## Slide 1: TX SET V2.1 Market Coordination Team

## Slide 2
Objectives:
To implement all approved Change Controls as identified by the TX SET Working Group for market-wide use
Provide coordination, clarification of issues, and documentation for v2.1 Change Controls through the Market Coordination Team (MCT) efforts
Scope:
Support the MOU/EC entrance into the Texas deregulated market
Address Disconnect for Non-Pay processes
Communicate additional billing determinants to the Market
Dependencies:
Completion of Market Requirements from TX SET Working Group
PR-40034/TX SET V2.1

## Slide 3
Phase:
Initiation – Completed March 28 ‘05
Planning – Goal to complete mid May ‘05
Execution – Goal to complete early December ’05
Closing – Goal to complete late December ‘05
Recent:
Project Charter sign-off
Finalized V2.1 Market Requirements – sign off on April 7th
Completion of Internal Requirements Document
Complete Planning Schedule including resource list and cost estimates
Next steps:
Obtain Sign off on Internal Requirements Document
Review Internal Conceptual Designs
Prepare to enter next phase (Execution)
PR-40034/TX SET V2.1

## Slide 4
Requirements (pens down) – Completed April 7th, 2005
Design (internal document) – Completion goal of May 18th, 2005
Build – Completion goal of July 7th, 2005
Internal Testing – Completion goal of September 21st, 2005
Market Testing – Completion goal of November 23th, 2005
Internal Training – Completion goal of September 9th, 2005
Production (Go live) – December 4th, 2005
PR-40034/TX SET V2.1

## Slide 5
Business lead: Suzette Wilburn
Phone number: (512) 248-3991
Email address: swilburn@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 6 Program Area: RO
What prompted the project:
  MOU/EC Entrance to Texas Deregulated Market
  Market Efficiency
  Identified Transactional Gaps
Supporting business drivers:
  More efficient transaction processing
  Business process solidification
PR-40034/TX SET V2.1

## Slide 6
Market Participant Contact List
  Email sent to RMS, TDSP and CR Primary list serves on Tuesday, April 26th
  Contact person will be responsible for providing status on Design, Development, Internal Testing
  Status will be presented to RMS in June, July, August, and September
  Progress report will be similar to previous market releases (MIMO, V1.5)
  Progress report is due 10 days prior to the RMS meeting each month
V2.1 MCT Updates

## Slide 7
Implementation Date
  MCT requests approval for the implementation of TX SET V2.1 over the December 3rd weekend.
V2.1 MCT Updates

## Slide 8
Next Steps
  Meeting in New Orleans, May 18th and 19th
  Developing the V2.1 Implementation Plan
  Identifying RMG and Protocols changes
V2.1 MCT Updates