## Merged List
2006 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Src Doc | Project | Proj. No. | Priority | Level 2 Sort | Rank | CBA Score | Net Benefit | 2006 Cost | 2006 Running Total
PUCT | SO |  | Enhancements to MOMS ISR | 50002 | 1 | 1 | 1 | 23 | -363069 | $100k-$500k | <$2M
PUCT | SO |  | Enhancements to MOMS Study Market Clearing Engines | 50003 | 1 | 1 | 2 | 23 | -277874 | $100k-$500k | <$2M
Market | RMS | SCR738 | Enhancement to FasTrak Tools--FasTrak is the retail transaction issue resolution tool. The system currently in place does not include the capability to track issues by variables such as ESI ID or TDSP, and does not allow determination of issue aging. In addition, the tool cannot be queried and interfacing with the tool is somewhat cumbersome. The FasTrak tool needs to be made more user friendly and enhanced with features that will allow issues to be better tracked and manipulated by Market Participants for purposes of better managing the retail transaction issue resolution process. | 50007 | 1 | 2 | 3 | 20 | 18301584 | $100-$500k | <$2M
Market | RMS | SCR739 | Potential Load Loss--Provide CR’s with a daily extract of customer loss notifications based on ERCOTs receipt of a TDSPs accepted response to a transaction that would cause a CR to lose the customer (and their associated load). The extract would be available via the ERCOT Portal. | 50023 | 1 | 2 | 4 | 11 | 895240 | $100k-$500k | <$2M
Market | RMS | SCR740 | Enhancements to SCR727--Suggested modifications include, but are not limited to: • Providing usage to CRs for backdated LSE Relationship Changes • Including a file name or number in order to identify the order in which SCR727 files should be loaded by the MP • Auditing capabilities to allow MPs the function to confirm the accuracy of their extracts • Ability to link a dB change back to the source of the change (i.e. FasTrak issue, batch processing) | 50024 | 1 | 2 | 5 | 15 | 3532131 | $500k-$1M | <$2M
Market | RMS | PRR312 | Enhance ESIID Lookup Function | 50025 | 1 | 2 | 6 | 14 | 726865 | <$100k | <$2M
ERCOT | IO |  | 2005 Storage to Support Ongoing Operations | ER-50125 | 1 | 3 | 7 | 23 | 4630932 | <$100k | <$2M
ERCOT | RO |  | SOA consolidated Retail Transactions | PR-50121 | 1 | 3 | 8 | 21 | 3244060 | $100k-$500k | $2M-$4M
ERCOT | RO |  | TX SET 2.1 | PR-40034 | 1 | 3 | 9 | 15 | -4786014 | 0 | $2M-$4M
ERCOT | SO |  | Operator Training Simulator/Testing Simulation Environment | PR-40090 | 1 | 3 | 10 | 18 | 1426448 | >$3M | $6M-$8M
ERCOT | SO |  | CSC Thermal & Volt Limits Calculations/Posting | PR-30084 | 1 | 3 | 11 | 18 | 22486 | <$100k | $6M-$8M
ERCOT | SO | PRR425 | Outage Scheduler Enhancements Phase II | PR-40084 | 1 | 3 | 12 | 19 | 916617 | <$100k | $6M-$8M
ERCOT | SO |  | Incident Report | PR-40086 | 1 | 3 | 13 | 17 | -95351 | <$100k | $6M-$8M
ERCOT | IO |  | Capacity True Up | ER-50013 | 1 | 3 | 14 | 18 | -172477 | 0 | $6M-$8M
ERCOT | IO |  | EDW BI Reporting Tool | PR-50004 | 1 | 3 | 15 | 24 | 15276127 | <$100k | $6M-$8M
ERCOT | IO |  | Altiris DC Implementation | ER-50028 | 1 | 3 | 16 | 20 | 8321 | $100k-$500k | $6M-$8M
ERCOT | IO |  | EDW EMMS Reports | PR-50005 | 1 | 3 | 17 |  | 0 | 0 | $6M-$8M
ERCOT | IO |  | Lodestar Extracts | PR-40042_06 | 1 | 3 | 18 |  | 0 | 0 | $6M-$8M
ERCOT | CO |  | Intrusion Detection/Intrusion Protection | ER-50132 | 1 | 3 | 19 | 26 | -298222 | 0 | $6M-$8M
ERCOT | CO |  | Collateral Calculation | ER-50017 | 1 | 3 | 20 | 17 | 26954 | 0 | $6M-$8M
ERCOT | CO |  | Lawson SIR - Time Tracking | 50015_01 | 1 | 3 | 21 | 18 | 63910 | 0 | $6M-$8M
PUCT | SO |  | Increase Number of Seats for Study Market Clearing Engines | New | 1.1 | 1 | 22 | 23 | -224062 | $100k-$500k | $6M-$8M
PUCT | SO |  | Enhancements to MOMS Metrics and Reports | New | 1.1 | 1 | 23 | 23 | -500000 | $100k-$500k | $6M-$8M
Market | COPS |  | TML Phase 3 - Wholesale Enhancements | 40103 | 1.1 | 2 | 24 | 18 | 11145103 | $500k-$1M | $8M-$10M
Market | RMS | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--project to improve availability and reduce outages in key retail commercial applications. | New | 1.1 | 2 | 25 | 24 | In Progress | $1M-$3M | $10M-$12M
Market | RMS |  | Performance Measures Reporting Requirements (changes to Project 24462)--expected project needed to enhance reporting systems as a result of T&Cs requirements effecting PUCT Performance Measures Project 24462 | New | 1.1 | 2 | 26 | 18 | -1000000 | $1M | $10M-$12M
Market | RMS |  | Terms and Conditions requirements, not limited to Texas SET changes | New | 1.1 | 2 | 27 | 17 | -500000 | $500k | $10M-$12M
ERCOT | IO |  | 2006 Minor Capital | New | 1.1 | 3 | 28 |  | 0 | $1M-$3M | $12M-$14M
ERCOT | RO |  | SOA Extend Footprint | New | 1.1 | 3 | 29 | 21 | 3226908 | $1M-$3M | $14M-$16M
ERCOT | SO |  | DC Tie Automation & Scheduling | PR-40036 | 1.1 | 3 | 30 | 23 | 52677463 | $1M-$3M | $16M-$18M
ERCOT | MO |  | Replace Maestro | New | 1.1 | 3 | 31 | 22 | 380296 | $100k-$500k | $18M-$20M
ERCOT | CO |  | Iron Mail Implementation | New | 1.1 | 3 | 32 | 17 | -51131 | $100k-$500k | $18M-$20M
ERCOT | RO |  | Enhance Digital Certificate Program | New | 1.1 | 3 | 33 | 15 | 4074838 | $100k-$500k | $18M-$20M
ERCOT | SO |  | Network Model Management System (NMMS) | NEW | 1.1 | 3 | 34 | 24 | 852954 | $1M-$3M | $20M-$22M
ERCOT | SO |  | Topology Estimation System | PR-40061 | 1.1 | 3 | 35 | 16 | 1190876 | $500k-$1M | $20M-$22M
ERCOT | CO |  | Risk Management (incl Security Auditing and Monitoring SW) | New | 1.1 | 3 | 36 | 27 | -349170 | $100k-$500k | $20M-$22M
ERCOT | SO | PRR525 | SCE Performance and Monitoring | PR-50130 | 1.1 | 3 | 37 | 23 | 6382530 | $100k-$500k | $20M-$22M
ERCOT | MO |  | MV90 Upgrade Part 2 - Installation of S/W | PR-50033_02 | 1.1 | 3 | 38 | 14 | 46011 | <$100k | $20M-$22M
ERCOT | CO |  | Lawson Legal System (Contracts DB) | ER-50111 | 1.1 | 3 | 39 | 21 | -254403 | $100k-$500k | $22M-$24M
ERCOT | RO |  | ESI ID account table split | New | 1.1 | 3 | 40 | 18 | 835672 | $100k-$500k | $22M-$24M
ERCOT | MO |  | DC Tie Automation (Pk2 Only) | PR-50018 | 1.1 | 3 | 41 | 19 | 25041 | $100k-$500k | $22M-$24M
ERCOT | CO |  | Host Intrusion Detection System | New | 1.1 | 3 | 42 | 26 | -298222 | $100k-$500k | $22M-$24M
ERCOT | RO |  | EDW Siebel Transition | ER-50059 | 1.1 | 3 | 43 | 23 | 448938 | $500k-$1M | $22M-$24M
ERCOT | RO |  | EDW TCH Transition | ER-50060 | 1.1 | 3 | 44 | 23 | 743338 | $100k-$500k | $22M-$24M
ERCOT | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | ER-50061 | 1.1 | 3 | 45 | 23 | 743338 | $100k-$500k | $24M-$26M
ERCOT | RO |  | ETS Transition to EDW | ER-50088 | 1.1 | 3 | 46 | 21 | 1185671 | $500k-$1M | $24M-$26M
ERCOT | SO |  | Operations Support Study environment/Disaster Recovery Test environment | PR-50052 | 1.1 | 3 | 47 | 18 | 329414 | $500k-$1M | $24M-$26M
ERCOT | MO |  | Lodestar 4.0 Upgrade | PR-40066_04 | 1.1 | 3 | 48 | 19 | 26444 | $100k-$500k | $26M-$28M
ERCOT | SO |  | Integrate Risk Based Transmission Reliability Analysis Tool into RT and Study Mode | NEW | 1.1 | 3 | 49 | 16 | 3744643 | $100k-$500k | $26M-$28M
ERCOT | CO |  | Forensics and Investigations | New | 1.1 | 3 | 50 | 26 | -253828 | $100k-$500k | $26M-$28M
ERCOT | IO |  | Windows Domain Restructuring | New | 1.1 | 3 | 51 | 21 | 122841 | $100k-$500k | $26M-$28M
ERCOT | SO |  | Operator Interface Enhancements | NEW | 1.1 | 3 | 52 | 18 | 713028 | $100k-$500k | $26M-$28M
ERCOT | SO |  | Breaker to Breaker One Lines/System Map | PR-50083 | 1.1 | 3 | 53 | 18 | -732819 | $500k-$1M | $26M-$28M
ERCOT | CO |  | Log and Event Management | New | 1.1 | 3 | 54 | 27 | -655320 | $100k-$500k | $28M-$30M
ERCOT | CO |  | Email Encryption | New | 1.1 | 3 | 55 | 29 | -346746 | $100k-$500k | $28M-$30M
ERCOT | IO |  | Firewall Modules | New | 1.1 | 3 | 56 | 28 | -132651 | $100k-$500k | $28M-$30M
ERCOT | SO |  | EMMS Production Support Process Automation | PR-50065 | 1.1 | 3 | 57 | 17 | 92451 | $100k-$500k | $28M-$30M
ERCOT | CO |  | Lawson 8.1 Upgrade | New | 1.1 | 3 | 58 | 19 | 177090 | $100k-$500k | $28M-$30M
ERCOT | SO |  | Replace DSM6 High-Speed Frequency Recorder | PR-30021 | 1.1 | 3 | 59 | 24 | -92757 | <$100k | $28M-$30M
ERCOT | IO |  | User Provisioning | ER-50034 | 1.1 | 3 | 60 |  | 0 | $100k-$500k | $28M-$30M
ERCOT | CO |  | Document Management | ER-50123 | 1.1 | 3 | 61 | 24 | 8370569 | $100k-$500k | $28M-$30M
ERCOT | IO |  | Lodestar Decommission | ER-50030 | 1.1 | 3 | 62 |  | 0 |  | $28M-$30M
ERCOT | IO |  | EDW EMMS Decommission | ER-50031 | 1.1 | 3 | 63 |  | 0 | <$100k | $28M-$30M
ERCOT | IO |  | EIS Reporting Tool II | New | 1.1 | 3 | 64 | 24 | 14054788 | $1M-$3M | $30M-$32M
ERCOT | CO |  | Lawson SIR - Process Flow | 50015_02 | 1.1 | 3 | 65 | 19 | 145389 | $100k-$500k | $30M-$32M
ERCOT | IO |  | IPC Line Networking | New | 1.1 | 3 | 66 | 19 | -137394 | $100k-$500k | $30M-$32M
ERCOT | SO |  | EMMS Software upgrade - OSI PI, OAG | NEW | 1.1 | 3 | 67 | 18 | -160250 | $100k-$500k | $30M-$32M
ERCOT | CO |  | Computer Aided Facilities Mgmt | New | 1.1 | 3 | 68 | 22 | 24100 | <$100k | $30M-$32M
ERCOT | SO |  | Improvements to Voltage and Transient Stability Studies (VSA/TSA) Phase II | PR-50029 | 1.1 | 3 | 69 | 19 | -266337 | $100k-$500k | $30M-$32M
ERCOT | IO |  | Austin QA Buildout | ER-40070 | 1.1 | 3 | 70 |  | 0 | $500k-$1M | $32M-$34M
ERCOT | IO |  | Disk Based Backup | ER-50027 | 1.1 | 3 | 71 |  | 0 | $100k-$500k | $32M-$34M
ERCOT | IO |  | EDW BI Foundation P2 - Repl Reserves Market Ad-hoc Reporting | PR-50001_03 | 1.1 | 3 | 72 |  | 0 |  | $32M-$34M
ERCOT | IO |  | EDW BI Foundation P2 - Ad-hoc Access to QSE Rpt Data | PR-50001_04 | 1.1 | 3 | 73 |  | 0 |  | $32M-$34M
ERCOT | IO |  | EIS BI Foundations III | New | 1.1 | 3 | 74 | 25 | -195455 | $100k-$500k | $32M-$34M
ERCOT | IO |  | EIS Conformed Data Warehouse Foundations | New | 1.1 | 3 | 75 | 29 | 48620154 | $1M-$3M | $32M-$34M
ERCOT | IO |  | TCC Data Center Virtualization | New | 1.1 | 3 | 76 | 25 | 0 | >$3M | $36M-$38M
ERCOT | IO |  | EIS CDW Data Marts | New | 1.1 | 3 | 77 | 25 | 24350470 | $500k-$1M | $36M-$38M
ERCOT | IO |  | Market Facing Redundancy | New | 1.1 | 3 | 78 | 21 | 2281129 | $500k-$1M | $38M-$40M
ERCOT | SO |  | EMS Archive Comparison Tool Phase II | PR-50039 | 1.1 | 3 | 79 | 16 | 1029079 | $100k-$500k | $38M-$40M
Market | RMS |  | Mass Customer Transition--project to automate and enhance mass Customer transtions in the market place. | 40038 | 1.2 | 2 | 80 | 16 | 2642217 | $1M-$3M | $40M-$42M
Market | COPS | SCR743 | Settlement Disputes Extract | New | 1.2 | 2 | 81 | 19 | 662292 | <$100k | $40M-$42M
Market | COPS | PRR577 | TDSP Load Extract | New | 1.2 | 2 | 82 | 17 | 67205 | <$100k | $40M-$42M
Market | WMS | PRR590 | Update Unit Telemetry Requirement | New | 1.2 | 2 | 83 | In progress | In progress | <$100k | $40M-$42M
Market | COPS |  | Extract/Report Enhancements | New | 1.2 | 2 | 84 | 10 | 0 | $100k-$500k | $42M-$44M
ERCOT | SO |  | SO-SIR Enhancements | NEW | 1.2 | 3 | 85 | 14 | -140237 | $100k-$500k | $42M-$44M
ERCOT | MO |  | SIR Enhancement Projects - 3 Releases | New | 1.2 | 3 | 86 | 15 | -210000 | $100k-$500k | $42M-$44M
ERCOT | RO |  | SIR enhancements | New | 1.2 | 3 | 87 |  | 0 | $500k-$1M | $42M-$44M
ERCOT | CO |  | Continuous Monitoring Software | New | 1.2 | 3 | 88 | 15 | -194924 | $100k-$500k | $42M-$44M
ERCOT | SO |  | Automate AS Qualification Testing | PR-30073 | 1.2 | 3 | 89 | 16 | 128370 | $100k-$500k | $42M-$44M
ERCOT | MO |  | REC Program Modifications | New | 1.2 | 3 | 90 | 19 | -389860 | $100k-$500k | $44M-$46M
ERCOT | RO |  | Web services that integrate L* and Siebel data for MPs | New | 1.2 | 3 | 91 | 16 | 12039169 | $100k-$500k | $44M-$46M
ERCOT | CO |  | Enterprise Document Management | New | 1.2 | 3 | 92 | 15 | 5684673 | $100k-$500k | $44M-$46M
ERCOT | MO |  | Lodestar Web Services | New | 1.2 | 3 | 93 | 20 | 1604295 | $100k-$500k | $44M-$46M
ERCOT | RO |  | Enhancements to RTW | New | 1.2 | 3 | 94 | 12 | 499742 | $100k-$500k | $44M-$46M
ERCOT | CO |  | NERC Tracking Database | New | 1.2 | 3 | 95 | 21 | -44482 | <$100k | $44M-$46M
ERCOT | SO |  | Security Constrained Power Flow for Feasible Generation for Outage Evaluation | PR-50048 | 1.2 | 3 | 96 | 16 | 157285 | $100k-$500k | $44M-$46M
ERCOT | RO |  | Commercial Apps - calendar consolidation | New | 1.2 | 3 | 97 | 23 | 32821 | $100k-$500k | $46M-$48M
ERCOT | CO |  | Business Function Automation/MSPS Time Mgt Integration | New | 1.2 | 3 | 98 | 8 | 6648962 | $500k-$1M | $46M-$48M
ERCOT | IO |  | Tools and Strategy for Information Lifecycle Management | New | 1.2 | 3 | 99 | 19 | 2763458 | $1M-$3M | $46M-$48M
ERCOT | SO | PRR428 | RMR Process Automation | PR-40087 | 1.2 | 3 | 100 | 19 | 2699772 | $500k-$1M | $48M-$50M
ERCOT | CO |  | Generator Database Automation | ER-50038 | 1.2 | 3 | 101 | 21 | -31568 | <$100k | $48M-$50M
ERCOT | IO |  | Network Analysis | New | 1.2 | 3 | 102 | 24 | -241464 | $100k-$500k | $48M-$50M
ERCOT | SO |  | Voltage Scheduler | PR-40091 | 1.2 | 3 | 103 | 11 | -313377 | $100k-$500k | $48M-$50M
ERCOT | IO |  | Exchange 2003 Implementation | New | 1.2 | 3 | 104 | 22 | 29345 | $100k-$500k | $48M-$50M
ERCOT | SO |  | SPS Modeling Enhancements | PR-50035 | 1.2 | 3 | 105 | 11 | -124791 | $100k-$500k | $48M-$50M
ERCOT | IO |  | System Dev Lifecycle | ER-50075 | 1.2 | 3 | 106 |  | 0 |  | $48M-$50M
ERCOT | SO |  | Performance Monitoring for ERCOT, TDSP, & QSE | PR-40085 | 1.2 | 3 | 107 | 20 | -593125 | $500k-$1M | $50M-$52M
ERCOT | IO |  | IT Systems Map | New | 1.2 | 3 | 108 | 19 | 1269302 | <$100k | $50M-$52M
ERCOT | SO |  | Governor Analysis Enhancements | PR-50071 | 1.2 | 3 | 109 | 21 | 0 | <$100k | $50M-$52M
ERCOT | IO |  | Network Response | New | 1.2 | 3 | 110 | 27 | -120323 | $100k-$500k | $50M-$52M
Market | RMS | SCR737 | Estimated Meter Read Data--Create a calendar month, summary report to be presented at RMS that will provide Market Participants with estimated meter reading information broken-down by TDSP territory and indicating customer class. This report will also indicate the degree to which meter reads occur consecutively across two or more months and the degree to which estimates may straddle Move-Ins and Move-In/Forced Outs. | 50091 | 1.3 | 2 | 111 | 7 | 450952 | $100-$500k | $50M-$52M
ERCOT | CO |  | TCC Physical Security Enhancements | ER-50107 | 1.3 | 3 | 112 | 24 | -162355 | $100k-$500k | $50M-$52M
ERCOT | IO |  | Nortel PBX Upgrade | New | 1.3 | 3 | 113 | 19 | -227002 | $100k-$500k | $50M-$52M
ERCOT | RO |  | 867 inbound map rewrite | New | 1.3 | 3 | 114 | 11 | 215743 | $100k-$500k | $50M-$52M
ERCOT | SO |  | Outage Sensitive Factor Screening Technique | PR-30056 | 1.3 | 3 | 115 | 14 | 93757 | $100k-$500k | $50M-$52M
ERCOT | CO |  | Budgeting Tool | ER-40029 | 1.3 | 3 | 116 | 16 | 162056 | <$100k | $50M-$52M
ERCOT | RO |  | 814 inbound XML rewrite | New | 1.3 | 3 | 117 | 17 | 314843 | $100k-$500k | $50M-$52M
ERCOT | SO |  | Entity Name Change in ERCOT Applications | PR-50056 | 1.3 | 3 | 118 | 11 | -836494 | $500k-$1M | $52M-$54M
ERCOT | IO |  | WAN Equipment Upgrade | New | 1.3 | 3 | 119 | 9 | -495666 | $100k-$500k | $52M-$54M
ERCOT | CO |  | Benefits Data Transmission | New | 1.3 | 3 | 120 | 12 | -62055 | <$100k | $52M-$54M
ERCOT | RO |  | Enhancements to ERCOT.com (enhancements not included in PR-40106) | New | 1.3 | 3 | 121 | 18 | 950476 | $100k-$500k | $52M-$54M
ERCOT | SO |  | Automatic Generation of One-line Diagrams | PR-30171 | 1.3 | 3 | 122 | 10 | -239382 | $500k-$1M | $52M-$54M
ERCOT | IO |  | Switch Consolidation | New | 1.3 | 3 | 123 | 24 | -347514 | $100k-$500k | $54M-$56M
ERCOT | SO |  | Line Naming Convention | PR-40080 | 1.3 | 3 | 124 | 11 | -80682 | $100k-$500k | $54M-$56M
ERCOT | CO |  | Security Camera Enhancements | ER-50106 | 1.3 | 3 | 125 | 26 | -234135 | $100k-$500k | $54M-$56M
ERCOT | SO |  | Satellite Communications for Black Start suppliers | PR-50050 | 1.3 | 3 | 126 | 19 | -85403 | <$100k | $54M-$56M
ERCOT | IO |  | Alcatel MDR8000 SNMP Upgrade | New | 1.3 | 3 | 127 | 16 | -55022 | <$100k | $54M-$56M
ERCOT | SO |  | Remodel Control Room Console Configuration | PR-50051 | 1.3 | 3 | 128 | 12 | 0 | $500k-$1M | $54M-$56M
ERCOT | IO |  | VM Development Implementation | New | 1.3 | 3 | 129 | 9 | 104708 | $100k-$500k | $54M-$56M
ERCOT | SO |  | ICCP Security Enhancements | NEW | 1.3 | 3 | 130 | 16 | -146594 | $100k-$500k | $54M-$56M
Market | RMS |  | Texas Set 2.2 --This is a place holder for new TxSet version 2.2 for 2006 | New | 2.1 | 2 | 131 | 15 | 3862239 | $500k-$1M | $56M-$58M
Market | WMS | PRR409 | Voltage Support Service. The current Protocols allow for excessive reactive dispatching on the part of TSPs without compensation to generation owners. This PRR changes the power factor envelope from +-.95 to +-.98, and allows for payment to generators. | 30032 | 2.1 | 2 | 132 | 14 | -1099000 | $1M-$3M | $56M-$58M
ERCOT | RO |  | Web based ERCOT 101 training | New | 2.1 | 3 | 133 |  | 0 | $500k-$1M | $58M-$60M
ERCOT | MO |  | Uninstructed Deviation Calc for Uncontrollable Renewable Resource | PR-50015 | 2.1 | 3 | 134 | 15 | 38178 | <$100k | $58M-$60M
ERCOT | SO |  | Outage Coordination Statistical Reports | PR-50093 | 2.1 | 3 | 135 | 20 | 0 | $100k-$500k | $58M-$60M
ERCOT | CO |  | Integrated MW Telemetry Validation Against EPS Meter Readings | ER-50098 | 2.1 | 3 | 136 | 20 | -75332 | <$100k | $58M-$60M
ERCOT | IO |  | System Engineering Metrics | ER-50077 | 2.1 | 3 | 137 |  | -131183 | $500k-$1M | $58M-$60M
ERCOT | RO |  | L* Retail POC | New | 2.1 | 3 | 138 | 15 | -602009 | $500k-$1M | $58M-$60M
ERCOT | CO |  | Voltage/Reactive Compliance Management Database | ER-50055 | 2.1 | 3 | 139 | 21 | -112639 | $100k-$500k | $58M-$60M
ERCOT | RO |  | MP automation of Manual cancels | New | 2.1 | 3 | 140 |  | 0 | <$100k | $58M-$60M
ERCOT | IO |  | TCC Modular Storage/Additional Office Space | NEW | 2.1 | 3 | 141 | 22 | -708911 | $500k-$1M | $60M-$62M
ERCOT | CO |  | SIR Tool Replacement | New | 2.1 | 3 | 142 | 12 | 26303 | <$100k | $60M-$62M
ERCOT | RO |  | Sieble GUI based data validation improvements | New | 2.1 | 3 | 143 |  | 0 | <$100k | $60M-$62M
ERCOT | IO |  | Console Operations Area | New | 2.1 | 3 | 144 | 25 | -443271 | $1M-$3M | $62M-$64M
ERCOT | CO |  | Project Portfolio Management System | New | 2.1 | 3 | 145 | 13 | -644026 | $500k-$1M | $62M-$64M
ERCOT | RO |  | Name to DUNS conversion | New | 2.1 | 3 | 146 | 14 | -25320 | $100k-$500k | $62M-$64M
ERCOT | CO |  | Unit Testing - Electronic Submittal via Web | ER-50070 | 2.1 | 3 | 147 | 21 | -369884 | $100k-$500k | $62M-$64M
ERCOT | RO |  | MP configuration table | New | 2.1 | 3 | 148 | 18 | -3351 | $100k-$500k | $62M-$64M
ERCOT | RO |  | Publish / subscribe self services / communications | New | 2.1 | 3 | 149 |  | 0 | $500k-$1M | $64M-$66M
Market | WMS | SCR720 | Zone Forecast and Actual Generation - ERCOT will provide real-time posting of Forecasted Net Zonal Energy and Actual Zonal Generation as an interim means of making a portion of the QSE data requirements available between now and the time that real-time XM | 20126 | 2.2 | 2 | 150 | 17 | -80000 | <$100k | $64M-$66M
Market | WMS | SCR728 | Display ERCOT Deployments - Display ERCOT total aggregated balancing energy deployment, total aggregated responsive deployment, total aggregated non-spin deployment, ERCOT SCE and ERCOT responsive reserve on the ERCOT public website | 20126 | 2.2 | 2 | 151 | 17 | -80000 | <$100k | $64M-$66M
Market | RMS |  | Retail Enhancements to TML - Phase 4 | 50058 | 2.2 | 2 | 152 | 16 | -960000 | $500k-$1M | $64M-$66M
ERCOT | SO |  | Enhancement to Market Analyst Interface for Ancillary Service Schedule Monitoring | PR-40082 | 2.2 | 3 | 153 | 11 | 16493 | <$100k | $64M-$66M
ERCOT | RO |  | EDI Transaction logging | New | 2.2 | 3 | 154 | 14 | -99482 | $100k-$500k | $64M-$66M
ERCOT | CO |  | Compliance Web Page Enhancements |  | 2.2 | 3 | 155 | 17 | -55243 | <$100k | $64M-$66M
ERCOT | SO |  | Web Posting for Market Transparency-Rollover | PR-20126 | 2.2 | 3 | 156 | 17 | 0 |  | $64M-$66M
ERCOT | CO |  | Metal/Explosives Detectors | ER-50105 | 2.2 | 3 | 157 | 18 | -118792 | $100k-$500k | $64M-$66M
Market | RMS | SCR742 | Automated Retail Transaction Verification-- Build interface to existing Market Certification environment This option involves building automation and an integrated user interface to the existing market certification environment. | New | 2.3 | 2 | 158 | 13 | 3436738 | $500k-$1M | $66M-$68M
Market | RMS | SCR734 | CSA Report for CRs--Provide CR’s with an on-demand extract capability to retrieve CSA (Continuous Service Agreement) data for their DUNS via the ERCOT Portal | 50057 | 2.3 | 2 | 159 | 8 | 150206 | $100k-$500k | $66M-$68M
ERCOT | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | New | 2.3 | 3 | 160 |  | 0 | $100k-$500k | $66M-$68M
ERCOT | CO |  | Lawson Expense Management | New | 2.3 | 3 | 161 | 14 | -55641 | <$100k | $66M-$68M
ERCOT | RO |  | Unified Member account management view | New | 2.3 | 3 | 162 |  | 0 | $100k-$500k | $66M-$68M
ERCOT | CO |  | Electronic Turnstyle | ER-50103 | 2.3 | 3 | 163 | 15 | -311784 | $100k-$500k | $66M-$68M
Market | WMS | PRR454 | OOME Off-line. When a generation unit receives an OOME instruction that would force it off-line, ERCOT must provide OOME instructions until the unit was scheduled to come off-line, or an OOMC instruction when the unit is requested to return. | 30193 | 3.1 | 2 | 164 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
ERCOT | SO |  | Resource Plan Improvement Phase II (EMMS Release 5) | PR-50074 | 3.1 | 3 | 165 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
ERCOT | RO |  | Automate Internal Surveys | New | 3.1 | 3 | 166 | n/a | n/a (3.x priority) |  | >$68M
ERCOT | CO |  | Resource Plan Metric Automation | ER-50095 | 3.1 | 3 | 167 | 21 | -53360 | <$100k | >$68M
ERCOT | IO |  | PowderHorn Tape Library Redundancy | New | 3.1 | 3 | 168 | 14 | -191098 | $100k-$500k | >$68M
ERCOT | IO |  | TML Port to Solaris | ER-50062 | 3.1 | 3 | 169 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
ERCOT | RO |  | Outage notification system & storage facility (centralized) | New | 3.1 | 3 | 170 | n/a | n/a (3.x priority) |  | >$68M
ERCOT | IO |  | MET Center Remediation | ER-50082 | 3.1 | 3 | 171 | n/a | n/a (3.x priority) | <$100k | >$68M
Market | RMS | PRR241 | UFE Analysis. 1) Revises the beginning date for UFE analysis in Section 11.5.1 to January 2002. 2) Modifies the language in 11.5.2.1 to accommodate a December 1, 2001 implementation timeline. 3) Adds language in 11.5.2.1 to require TDSPs to leave "old control area" boundary meters in place until UFE analysis zones are defined. Definition of zones to take place after June 1, 2001 but supporting December 1, 2001 deadline. | 30022 | 3.2 | 2 | 172 | n/a | n/a (3.x priority) | $1M-$3M | >$68M
Market | RMS | SCR736 | TML ESIID TXN Portal Flag--Append a data Flag of “P” to the Transaction Type number to indicate when a displayed transaction was generated and transmitted through the Texas Market Link portal by Market Participants, rather than being generated by Market Participant’s system and transmitted in the Market via GISB. | 50100 | 3.2 | 2 | 173 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | COPS |  | TCR Synchronization of Credit Payment with Settlement Invoices | 30103 | 3.3 | 2 | 174 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | RMS | PRR385 | DLC Implementation. This PRR will allow the DLC programs to be appropriately profiled and ERCOT systems to properly process DLC programs. |  | 3.3 | 2 | 175 | n/a | n/a (3.x priority) |  | >$68M
Market | RMS | PRR478 | Use of Lagged Dynamic Samples for New Load Profiles. This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. | 40056 | 3.3 | 2 | 176 | n/a | n/a (3.x priority) | $500k-$1M | >$68M
Market | WMS | PIP112 | DLC for BULs | 50108 | 3.3 | 2 | 177 | n/a | n/a (3.x priority) | $1M-$3M | >$68M
Market | WMS | PRR311 | DLC to BUL Transition. Permits load control or load management programs involving small energy consumers (under 1 MW) to provide a balancing-up load (BUL) without the requirement that interval data recorders (IDRs) be installed on all of the participatin | 50108 | 3.3 | 2 | 178 | n/a | n/a (3.x priority) | Included with PR50108 | >$68M
Market | WMS | PRR484 | Changes for Implementation of Direct Load Control (DLC). The requested changes will facilitate and specify how DLC programs participate in the BUL market. | 50108 | 3.3 | 2 | 179 | n/a | n/a (3.x priority) | Included with PR50108 | >$68M
Market | WMS | PIP128 | Synchronous Condenser Compensation | 30034 | 3.3 | 2 | 180 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | WMS | PIP210 | Block Bidding for Reserve Services - Related to PRR496 | 50046 | 3.3 | 2 | 181 | n/a | n/a (3.x priority) | <$100k | >$68M
Market | WMS | PRR307 | Controllable Resources. This revision defines Load which can provide Regulation Service. | 30039 | 3.3 | 2 | 182 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | WMS | PRR426 | URC for Uncontrollable Resources. Defines an Uncontrollable Renewable Resource and allows wind resource to elect to use their Renewable Production Potential in lieu of their schedule as the basis for URC charges and OOME Down payments. | 40057 | 3.3 | 2 | 183 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | WMS | PRR355 | BLT OOME - Allows availability of Block Load Transfers for OOME deployment | 30132 | 3.3 | 2 | 184 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | WMS | SCR729 | Unit Status Information - Modify the ERCOT market clearing engine to allocate RRS to hydro units operating in synchronous condenser mode | 20126 | 3.3 | 2 | 185 | n/a | n/a (3.x priority) | <$100k | >$68M
Market | WMS |  | TGR (Trading piece) | 50110 | 3.3 | 2 | 186 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
Market | WMS | SCR735 | Include Hydro Units in Synchronous Condenser Mode in SPD RRS Allocation | 50120 | 3.3 | 2 | 187 | n/a | n/a (3.x priority) | <$100k | >$68M
Market | WMS | PRR496 | Block Bidding and Deployment of LaaRs providing Responsive Reserve Service and Non-Spinning Reserve Service. Include provisions for LaaRs to have the option to bid Responsive Reserve Service and Non-Spinning Reserve Service as a block. | 50046 | 3.3 | 2 | 188 | n/a | n/a (3.x priority) | <$100k | >$68M
Market | WMS | PRR436 | Enhance LaaR/BUL Ability to Participate in Balancing Energy Up Service, Non-Spinning Reserve Service, and Responsive Reserve Service Markets. This PRR would include the changes proposed by the Demand Side Working Group to clarify the role of Loads in the Ancillary Service and BUL markets. | 30191 | 3.3 | 2 | 189 | n/a | n/a (3.x priority) | <$100k | >$68M
ERCOT | SO |  | Include Hydro Units in Synchronous Condenser Mode in SPD RRS Allocation | PR-50120 | 3.3 | 3 | 190 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
ERCOT | RO |  | Market Meeting Electronic Voting | New | 3.3 | 3 | 191 | n/a | n/a (3.x priority) |  | >$68M
ERCOT | CO |  | Lawson eRecruiting | New | 3.3 | 3 | 192 | 0 | -115862 | $100k-$500k | >$68M
ERCOT | SO |  | For Responsive Reserve & Non-Spinning Reserve Services; Block Deployment (for Responsive & Non-Spin) | PR-50046 | 3.3 | 3 | 193 | n/a | n/a (3.x priority) | $100k-$500k | >$68M
ERCOT | RO |  | Administration of Enrollment notifications | New | 3.3 | 3 | 194 | n/a | n/a (3.x priority) |  | >$68M
Market | RMS | PRR565 | Calculation of Losses for Settlement | New | [5 empty] | <$100k | >$68M

## Summary
Count of 2006 Cost2 | Source
Priority | ERCOT | Market | PUCT | Grand Total
1 | 15 | 4 | 2 | 21
1.1 | 52 | 4 | 2 | 58
1.2 | 26 | 5 |  | 31
1.3 | 19 | 1 |  | 20
2.1 | 17 | 2 |  | 19
2.2 | 5 | 3 |  | 8
2.3 | 4 | 2 |  | 6
3.1 | 7 | 1 |  | 8
3.2 |  | 2 |  | 2
3.3 | 5 | 16 |  | 21
Grand Total | 150 | 40 | 4 | 194
Priority | PUCT | Market | ERCOT | Grand Total
1 | 256228 | 1425713 | 4835236.4 | 6517177.4
1.1 | 724062 | 4297225 | 27665710.9 | 32686997.9
1.2 |  | 3130000 | 8533049.4 | 11663049.4
1.3 |  | 150000 | 4804004.6 | 4954004.6
2.1 |  | 1750000 | 6897759.75 | 8647759.75
2.2 |  | 1040000 | 430890.75 | 1470890.75
2.3 |  | 850000 | 964089.9 | 1814089.9
3.1 |  | 0 | 816986.25 | 816986.25
3.2 |  | 0 |  | 0
3.3 |  | 0 | 613110.6 | 613110.6
Grand Total | 980290 | 12642938 | 55560838.55 | 69184066.55
Priority | PUCT | Market | ERCOT | Grand Total
1 | 2 | 4 | 15 | 21
1.1 | 2 | 4 | 52 | 58
1.2 |  | 5 | 26 | 31
1.3 |  | 1 | 19 | 20
2.1 |  | 2 | 17 | 19
2.2 |  | 3 | 5 | 8
2.3 |  | 2 | 4 | 6
3.1 |  | 1 | 7 | 8
3.2 |  | 2 |  | 2
3.3 |  | 16 | 5 | 21
Grand Total | 4 | 40 | 150 | 194