## Slide 1: Commercial Operations Sub-Committee Update to RMS
July 13, 2005

## Slide 2: COPS Update
  COPS attendees desire to have Voting structure similar to PRS
  Questions relating to Day Ahead Market short pay protocol language were passed to TNT
  ERCOT presented findings concerning storage space required for keeping Zero Charge settlement data – Market needs more time to study individual impacts
  Consensus was reached that continued effort is needed in addressing Dispute and ADR processes in protocols
Notes:     What entities are exposed to the uplift associated with a DAM participant’s failure to pay?
    Questions from COPS discussion:
    Is the 180 day uplift in the draft Nodal Protocols correct?

## Slide 3
COPS Recommendation
PRR 568 Implementation Plan
Migrate Initial Settlements from 17 to 10 Days
TAC VOTING ITEM

## Slide 4: PRR 568 Implementation Plan
Allow for an Analysis period to review load extracts for Day 10 aggregation to determine expected impact when initial settlements are reduced from 17 to 10 days
  Market Participant effects (individual analysis)
    Individual Load Change
    Resource Imbalance Change
  ERCOT Analysis of Market effects
    Credit Impact Analysis
    UFE
    Total Load
Market consensus on threshold needed to stop the migration to Day 10 is that set points are not likely to be known until analysis period data is available
Initial Settlement Statement publication begins reducing from 17 days to 10 days over a seven week period starting with Invoices published during the week of 2/9/06
  Seven (7) weekly invoices published beginning on 2/9/06 will contain eight (8) initial Settlement Statements instead of the current seven (7)

## Slide 5: PRR 568 – Credit Impact Analysis Collateral Requirements
During the transition period, adjustments will be made to Estimated Aggregate Liability (EAL) and Net Load and Resource Imbalance (NLRI) credit calculations as needed
Adjustments will be made to TNT Protocols Section 16 credit calculations
Implementation Analysis period will provide additional time to determine full effect to credit
Preliminary credit analysis shows reductions in collateral realized as long as the quality of data utilized for the credit calculations is substantially the same as the current quality

## Slide 6: PRR 568 – Credit Impact Analysis EAL Calculation

## Slide 7: PRR 568 Implementation Plan Schedule
Analysis Period: August to mid November | ERCOT begins providing Ch 0 cuts for Load and Generation Extracts 1st 30 day run for Aug 1 to Aug 31 2nd 30 day run Sept 15 to Oct 15, 2005 Ch 0 is a day 8 aggregation - the data that would be used for day 10 settlement ERCOT provides reporting similar to Report provided at COPS Feb 2005 Market Participants exchange ideas and observations of Ch 0 cuts in conference calls every 2 weeks. The 1st call to occur approximately 20 days after the first date Ch 0 data was made available
Nov 14, 2005 | Market Participants end Ch 0 analysis COPS presentation discussion on Analysis results Prepare recommendation for TAC Vote
Dec 1, 2005 | TAC meeting COPS report of Ch 0 analysis results Possible VOTING ITEM to change the implementation plan
Jan 17, 2006 | 1st Trade Date to Start the migration to Day 10. Binding Settlement Statement would be published on February 2, 2006.
7 weeks – 8 day Settlement Invoices | Feb 9, 16, 23, Mar 2, 9, 16, 23
TIMELINE: Market Participant and ERCOT Analysis

## Slide 8: PRR 568 Implementation Plan
The following Metrics have been discussed by COPS for setting Triggers that would lead to recommendation for TAC to authorize stopping the migration to Day 10 Initial Settlement
  Review Market Wide UFE comparing Day 10 to Day 17 results – to understand if there is a material change
  No material change in Load or settlement impact of a market participant caused by changing initial settlement to Day 10
Notes: COPS suggests criteria to halt migration to Day 10 Initial would be subject to materially adverse changes in Credit, Load, Resource or UFE.
COPS Discussion, Action and Recommendation to TAC needed for setting Triggers would be derived from the Analysis Period results

## Slide 9: PRR 568 Implementation Plan
COPS RECOMMENDATION
TAC to recommend Board approval of PRR 568 with the Implementation Plan as Outlined
Implementation Plan Outline
  Analysis period from August through mid November
  Recommendation if necessary from COPS to halt migration
  Recommendation to halt would be supported by Facts from the Analysis based on materially adverse Credit, Load, Resource or UFE impacts
  Initial Settlement would begin with Trade Dates on Invoices published February 9
  7 Week Implementation period where Settlement invoices would contain 8 trade days