## Slide 1: Flight 0705 Update

## Slide 2: Flight 0705 Update
Flight manifest
2 New REPs – 7 New Relationships
3 New Umbrella DUNS – 13 New Relationships
4 Existing REP testing in new territory – 4 New Relationships
1 Existing REP testing new functionalities
1 Existing REPs changing Service Providers
5 Existing REPs changing Banks
About 5000 Tasks total

## Slide 3: Flight 0705 Update
Progress
Flight sign-up deadline was June 8th
Connectivity Testing began June 14th
Connectivity Testing completed July 1st
Testing Kick-off call - June 24th
Flight began Jun 27th

## Slide 4: Flight 0705 Next Steps
Flight Takeoff
Transactions start to flow Monday June 27th at 8:00 am
Daily status calls – MANDATORY
Status as of Day 4 (June 30th)– Flight 17.1% complete – on schedule
By July RMS (7/13/05)
Market scheduled to be on Day 13 of Flight 0705
  Connectivity is complete
By August RMS (8/10/05)
Market scheduled to be on Day 33 of Flight 0705
Flight 0705 scheduled to complete on 8/11