## Slide 1: PRR 568 Implementation Plan Schedule
Analysis Period: August to mid November | ERCOT begins providing Ch 0 cuts for Load and Generation Extracts 1st 30 day run for Aug 1 to Aug 31 2nd 30 day run Sept 15 to Oct 15, 2005 Ch 0 is a day 8 aggregation - the data that would be used for day 10 settlement ERCOT provides reporting similar to Report provided at COPS Feb 2005 Market Participants exchange ideas and observations of Ch 0 cuts in conference calls every 2 weeks. The 1st call to occur approximately 20 days after the first date Ch 0 data was made available
Nov 14, 2005 | Market Participants end Ch 0 analysis COPS presentation discussion on Analysis results Prepare recommendation for TAC Vote
Dec 1, 2005 | TAC meeting COPS report of Ch 0 analysis results Affirmative VOTE by TAC to move toward Day 10 Initial Settlements
Jan 17, 2006 | 1st Operating Date to Start the migration to Day 10. Binding Settlement Statement would be published on February 2, 2006. Unbox PRR568 and provide 10 days notice to the Market
7 weeks – 8 day Settlement Invoices | Feb 9, 16, 23, Mar 2, 9, 16, 23
TIMELINE: Market Participant and ERCOT Analysis

## Slide 2: PRR 568 Implementation Plan
COPS RECOMMENDATION
TAC to recommend Board approval of PRR 568 with the Implementation Plan as Outlined
Implementation Plan Outline
  Analysis period from August through mid November
  Recommendation from COPS to TAC to go forward with implementation of moving Initial Settlement toward Day 10
  Affirmative VOTE would be required by TAC to move forward toward Day 10 Initial Settlements. Recommendation to move forward would be supported by Facts from the Analysis based on no materially adverse Credit, Load, Resource or UFE impacts.
  Initial Settlement would begin with Operating Dates on Invoices published February 9
  7 Week Implementation period where Settlement invoices would contain 8 Operating days