## Slide 1: TX SET V2.1 Market Coordination Team

## Slide 2
Objectives:
To implement all approved Change Controls as identified by the TX SET Working Group for market-wide use
Provide coordination, clarification of issues, and documentation for v2.1 Change Controls through the Market Coordination Team (MCT) efforts
Scope:
Support the MOU/EC entrance into the Texas deregulated market
Address Disconnect for Non-Pay processes
Communicate additional billing determinants to the Market
Dependencies:
Completion of Market Requirements from TX SET Working Group
PR-40034/TX SET V2.1

## Slide 3
Phase:
Initiation – Completed March 28 ‘05
Planning – Completed May 27th, 2005
Execution – Goal to complete early December ’05
Closing – Goal to complete late December ‘05
Recent:
Obtained sign off for Conceptual Designs
Reviewed Detail Designs
Obtained Sign off on Detail Designs
Entered Execution Phase
Began Development
Next steps:
Obtain Sign off on ETS and Reprocessing Detail Designs
Develop Internal Training Materials
PR-40034/TX SET V2.1

## Slide 4
Requirements (pens down) – Completed April 7th, 2005
Design (internal document) – Completed May 27th, 2005
Build – Completion goal of July 22nd, 2005
Internal Testing – Completion goal of September 21st, 2005
Market Testing – Completion goal of November 23th, 2005
Internal Training – Completion goal of September 9th, 2005
Production (Go live) – December 4th, 2005
PR-40034/TX SET V2.1

## Slide 5
Business lead: Suzette Wilburn
Phone number: (512) 248-3991
Email address: swilburn@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 6 Program Area: RO
What prompted the project:
  MOU/EC Entrance to Texas Deregulated Market
  Market Efficiency
  Identified Transactional Gaps
Supporting business drivers:
  More efficient transaction processing
  Business process solidification
PR-40034/TX SET V2.1

## Slide 6
Progress Update
Completed Implementation Plan
Reviewed Scripts developed by TTPT Script Sub team
Updated the following Implementation Guides based on issues identified by MCT
  814_20: Guide did not accurately reflect MCT agreement on Requirement 33
  650_01: CC2004-629 inadvertently removed an ANSI required data element
  Changes were reposted to the website
V2.1 MCT Updates

## Slide 7
Market Participant Progress Report
All Market Participants were requested to provide their progress on Design/Code/Test of TX SET V2.1 and identify any risks that would delay Flight 1005 or Implementation
Progress will be reported through September RMS
Progress Reports for August RMS status are due COB July 29th, 2005
  Non response will default to previous month’s status
V2.1 MCT Updates

## Slide 8
July Progress - REPs

## Slide 9
July Progress - REPs

## Slide 10
July Progress - REPs

## Slide 11
July Progress – TDSPs/ERCOT

## Slide 12
Next Steps
July Meeting scheduled for July 26th, Tulsa OK
Continue Market Participant Progress Tracking
Request issues be sent to Suzette Wilburn (swilburn@ercot.com)
by COB July 19th, 2005 for July MCT Meeting
V2.1 MCT Updates