June Report

To

Technical Advisory Committee

Reliability and Operations Subcommittee

Prepared by ERCOT Transmission Services

Transmission Project Summaries

Major transmission projects completed

| Project Title | Project Description | Transmission Owner | Actual In-Service Date | Service Level kV |
| --- | --- | --- | --- | --- |
| Eagle Mountain 345 kV breakers | Install two 345 kV breakers | TXU Electric Delivery | Apr-05 | 345 |
| Roanoke Switch 345/138 kV autotransformer | Install (2nd) 345/138 kV autotransformer (600 MVA) at Roanoke Switch | TXU Electric Delivery | Mar-05 | 345 |
| Watermill - Tricorner 345 kV line | Upgrade Watermill - Tricorner 345 kV line | TXU Electric Delivery | Feb-05 | 345 |
| Obrien 345/138 kV autotransformer | Added third 345/138 kV, 400MVA autotransformer (A3) @Obrien | CNP | Jan-05 | 345 |

Status of major transmission projects

| Project Title | Project Description | Transmission Owner | Projected In-Service Date | Service Level kV | Location County |
| --- | --- | --- | --- | --- | --- |
| Anna 345/138 kV autotransformer | Install a (2nd) 345/138 kV autotransformer (600 MVA) at Anna | TXU Electric Delivery | May-05 | 345 | COLLIN |
| Lake Creek second 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer | TXU Electric Delivery | May-05 | 345 | MCLENNAN |
| Martin Lake 345 kV breakers | Install two 345 kV bus tie breakers | TXU Electric Delivery | May-05 | 345 | RUSK |
| Monticello 345 kV breaker | Install one 345 kV bus tie breaker | TXU Electric Delivery | May-05 | 345 | TITUS |
| Watermill - Cedar Hill (2nd) 345 kV circuit | Install Watermill - Cedar Hill (2nd) 345 kV circuit | TXU Electric Delivery | May-05 | 345 | DALLAS |
| Cedar Bayou 345/138 kV autotransformer | Add fourth 345/138 kV, 800MVA autotransformer (A4) @Cedar Bayou and reconnect third auto (A3) to the west bus, parallel to A1 & A2 | CNP | Jun-05 | 345 | HARRIS |
| Salem 345/138 kV autotransformer upgrade | Upgrade Salem 345/138 kV autotransformer capacity to 672 MVA | LCRA | Jun-05 | 345 | WASHINGTON |
| Kendall 345/138 kV autotransformer # 2 | Install a second 345/138 kV autotransformer at the Kendall substation | LCRA | Jun-05 | 345 | KENDALL |
| Watermill - W. Levee (2nd) 345 kV circuit | Install Watermill - W. Levee (2nd) 345 kV circuit | TXU Electric Delivery | Oct-05 | 345 | DALLAS |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A1) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A4) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| Rio Hondo, add 345/138 kV auto | Rebuild La Palma to Rio Hondo 138 kV with 2-795 ACSS, double circuit capable and add 345/138 kV autotransformer at Rio Hondo | AEP/TCC | Apr-06 | 345 | CAMERON |
| Pecan Creek 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at Pecan Creek | TXU Electric Delivery | May-06 | 345 | BELL |
| Venus - Sherry 345 kV line | Construct Venus - Sherry 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| W. Levee - Norwood 345 kV line | Construct W. Levee - Norwood 345 kV line | TXU Electric Delivery | May-06 | 345 | DALLAS |
| Venus - Liggett 345 kV line | Construct Venus - Liggett 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| Venus - Johnson Switch 345 kV line | Upgrade existing 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| Valley 345/138 kV autotransformer | Replace existing 450 MVA 345/138 kV autotransformer with a 600 MVA autotransformer | TXU Electric Delivery | May-06 | 345 | FANNIN |
| Jewett - TH Wharton 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU Electric Delivery | May-06 | 345 | LEON |
| Jewett - Tomball 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU Electric Delivery | May-06 | 345 | LEON |
| T.H.Wharton - Jewett ckt.1 | Upgrade tie lines from TH Wharton to TXU tie point to increase thermal ratings to 1450 MVA by raising conductors and upgrading limiting equipment at TH Wharton | CNP | May-06 | 345 | HARRIS |
| Nelson Sharpe, add 345/138 kV autotransformer | Construct Nelson Sharpe 345/138 kV substation in the Lon Hill to Rio Hondo 345 kV line and add a phase-shifting transformer at Nelson Sharpe in Davis 138 kV line | AEP/TCC | May-06 | 345 | KLEBERG |
| Zorn Auto | Replace the 600MVA Zorn Auto 2 with a 478MVA auto (7045-7180) | LCRA | Jun-06 | 345 | GUADALUPE |
| Clear Springs | Add a new 345/138 kV 478 MVA auto-transformer at the Clear Springs substation(7050). The existing 345 kV bus at the Clear Springs will be converted from a ring bus configuration to a double-bus double-breaker configuration. Upgrade the 7.2-mile Clear Springs(7680)-Geronimo(7604)-Seguin(7228) 138 kV transmission line (T-264) from 336 ACSR to Bundled 795 ACSR double circuit capable. Upgrade the 7.2-mile Clear Springs(7680)-Freiheit(7462)-Hortontown(7175)-Comal(7176) 138 kV transmission line (T-264, T-394, and T-119) from 336 ACSR to Bundled 795 ACSR double circuit capable. | LCRA | Jun-06 | 345 | GUADALUPE |
| Kendall-CPS Cagnon 345-kV line | Construct a 345 kV bundled 1590 ACSR line (approximately 45 miles) between Kendall (7046) and Cagnon (5056) | LCRA / CPS | Jun-06 | 345 | BEXAR |
| Skyline - Replace 345kV Autotransformer #2 & #4 | Replace the two 480 MVA autotransformers(#2 & #4) with one 600 MVA autotransformer. | CPS | Jul-06 | 345 | BEXAR |
| Elm Creek Substation | Install new 345 kV switching station at the intersection of the existing 345kV lines from STP-Skyline, STP-Hill Country, and both lines from Marion to San Miguel. | CPS | Oct-06 | 345 | GUADALUPE |
| Jacksboro Switch - W. Denton 345 kV line | Construct Jacksboro Switch - W. Denton 345 kV line | TXU Electric Delivery | Dec-06 | 345 | JACK |
| Sandow 345/138 kV autotransformer | Install second 345/138 kV autotransformer | TXU Electric Delivery | Dec-06 | 345 | MILAM |
| Odessa EHV 345/138 kV 300 MVA autotransformer replacement | Replace existing 300 MVA 345/138 kV autotransformer with a 450 MVA autotransformer | TXU Electric Delivery | Dec-06 | 345 | ECTOR |
| Sandow 345/138 kV autotransformer | Install second 345/138 kV autotransformer | TXU Electric Delivery | Dec-06 | 345 | MILAM |
| Paris Switch - Anna 345 kV line | Construct Paris Switch - Anna 345 kV line | TXU Electric Delivery | Dec-06 | 345 | LAMAR |
| WAP 345 kV sub. | Upgrade fault duty rating of WAP 345 kV to at least 56 kA | CNP | Dec-06 | 345 | FORT BEND |
| Smithers 345 kV sub. | Upgrade fault duty rating of Smithers 345 kV to at least 52 kA | CNP | Dec-06 | 345 | FORT BEND |
| STP - Dow ckt.18 and ckt.27 | Replace 2000 Amp equipment on both circuits from STP to DOW. | CNP | Dec-06 | 345 | MATAGORDA |
| DeCordova - Benbrook 345 kV line upgrade | Upgrade capacity of line | TXU Electric Delivery | May-07 | 345 | HOOD |
| DeSoto 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at DeSoto | TXU Electric Delivery | May-07 | 345 | DALLAS |
| Plano Tennyson 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at Plano Tennyson | TXU Electric Delivery | May-07 | 345 | COLLIN |
| Trinidad - Richland 345 kV line | Upgrade Trinidad - Richland 345 kV line | TXU Electric Delivery | May-07 | 345 | HENDERSON |
| Venus - Cedar Hill 345 kV line | Upgrade existing 345 kV line | TXU Electric Delivery | May-07 | 345 | ELLIS |
| Spruce to Skyline 345kV 2nd Circuit | Build 2nd 345 kV line from Spruce to Skyline substation | CPS | Jun-07 | 345 | BEXAR |
| Second Whitney 345/138 Autoitransformer | Install second 450MVA 345/138KV auto at Whitney | Brazos | Jun-08 | 345 | BOSQUE |
| Hillje Switching Station | Build a new 345 kV Hillje substation. Loop ckt.1 STP-Holman into the new substation. | CNP | Dec-08 | 345 | WHARTON |
| STP - Hillje ckt. | Build new 345 kV line from STP to Hillje. | CNP | Dec-08 | 345 | MATAGORDA |
| WAP - Hillje ckt. | Build new 345 kV double circuit line from WA Parish to Hillje. | CNP | Dec-08 | 345 | FORT BEND |
| Increase CNP 345/138 kV autotransformer capacity | Add several 800 MVA autotransformers in the CNP transmission system | CNP | Dec-08 | 345 | HARRIS/CHAMBERS/FORT BEND/GALVESTON/BRAZORIA |
| WA Parish - Bellaire ckt 50 | Raise conductors to increase thermal ratings | CNP | Dec-08 | 345 | FORT BEND |
| Smithers - Bellaire ckt.98 | Raise conductors to increase thermal ratings | CNP | Dec-08 | 345 | FORT BEND |
| West Denton - NW Carrollton 345 kV circuit | Add second Circuit from West Denton to NW Carrollton | TXU Electric Delivery/TMPA | May-09 | 345 | DENTON |
| Skyline - Install a third 345kV Autotransformer | Install one 600 MVA autotransformer. | CPS | May-09 | 345 | BEXAR |
| Second Concord 345/138 Autotransformer | Install second 300MVA 345/138KV auto at Concord | Brazos | Jun-09 | 345 | JOHNSON |
| Cagnon to Hillcountry 345kV 2nd Circuit | Build 2nd 345 kV line from Cagnon to Hill Country substation | CPS | Jun-09 | 345 | BEXAR |
| Hill Country to Skyline 345 kV 2nd Circuit | Build 2nd 345 kV line from Hillcountry to Skyline substation | CPS | Jun-09 | 345 | BEXAR |
| Dansby to Twin Oak 345 kV | Design and build a double circuit 345 that will tie into the existing TMPA Gibbons to Twin Oaks line | BTU | Jul-09 | 345 | BRAZOS |
| 2nd Lewisville Auto | Install (2nd) 345/138 kV autotransformer at Lewisville station | Brazos | Dec-09 | 345 | DENTON |
| Laredo Lobo, build 345 kV for 675MVA autotransformer | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/TCC | Mar-10 | 345 | WEBB |
| Laredo Lobo to San Miguel, build 345 kV line | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/STEC | May-10 | 345 | WEBB |
| Liggett - Trinity Switch 345 kV line | Construct Liggett - Trinity 345 kV line | TXU Electric Delivery | May-10 | 345 | DALLAS |
| Trinity Switch 345/138 kV autotransformer | Create Trinity Switch and install a 600 MVA 345/138 kV autotransformer | TXU Electric Delivery | May-10 | 345 | TARRANT |
| Hutto Switch - Salado Switch 345 kV line | Construct Hutto Switch - Salado Switch 345 kV line | TXU Electric Delivery | May-10 | 345 | WILLIAMSON |
| Hutto Switch 345/138 kV autotransformer | Create 345 kV switching station and install a 345/138 kV autotransformer | TXU Electric Delivery | May-10 | 345 | WILLIAMSON |
| Zorn/Clear Springs-Harris Branch-Hutto Switch 345-kV line | Construct a 345 kV DC 2x1590 ACSR line between Zorn/Clearsprings and Hutto Switch and other ONCOR and AE projects | LCRA | Jun-10 | 345 | WILLIAMSON |
| Harris Branch 345/138kV autotransformer | Install a 345/138kV autotransformer at Harris Branch substation | Austin Energy | Dec-10 | 345 | TRAVIS |
| Harris Branch 345/138kV autotransformer & Harris Branch 138kV circuit to East and Techridge Substation. | Install a 345/138kV autotransformer at Harris Branch substation. Cut-in the existing East to Techridge 138kV circuit to establish the 138kV East to Harris and 138kV Harris to Techridge circuits | Austin Energy | Dec-10 | 345 | TRAVIS |
| Frontera, add SS with 345/138 kV autotransformer | Addition North Edinburg to Frontera to South McAllen 345 kV line with bundled 1590 ACSR conductor and double circuit capable structures and 345/138 kV substation at Frontera | AEP/TCC | May-11 | 345 | HIDALGO |
| Laredo Lobo to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Frontera to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Rio Bravo, 138 kV SS with 345/138 kV autotransformer | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| North McCamey to Twin Buttes 345 kV Line | 12/02 plan recommends the construction of a 345kV 2x1590 ACSR line between North McCamey and Twin Buttes | LCRA/AEP | Jan-12 | 345 | UPTON |
| North McCamey - Odessa 345 kV Line | 12/02 plan recommends the construction of a 345 kV 2x1590 ACSR line between North McCamey and Odessa and 2x600 MVA autotransformers at North McCamey | LCRA/AEP | Jan-12 | 345 | UPTON |
| North McCamey 345/138 kV autotransformer | Recommends the addition of a 345/138kV autotransformer North McCamey | LCRA/AEP | Jan-12 | 345 | UPTON |
| Frontera to South McAllen 345 kV line | Construct a 345 kV transmission line from Frontera to South McAllen. | LCRA/AEP | May-15 | 345 | HIDALGO |
| Rio Hondo to Ranchito, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345 kV line | AEP/TCC |  | 345 | CAMERON |
| Ranchito, new SS with 345/138 kV autotransformer | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| Ranchito to South McAllen, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| South McAllen, new SS with 345/138 kV autotransformer | Construct a 345 kV substation south of South McAllen cut into the South McAllen to Hidalgo 138 kV line and install a 345/138 kV autotransformer | AEP/TCC |  | 345 | HIDALGO |
| Loma Alta - Ranchito or la Palma 345-kV line | Install 345-kV line from Loma Alta to La Palma or Ranchito | BPUB |  | 345 | CAMERON |
| Loma Alta - Rio Hondo 345-kV line | Install 345-kV line from Loma Alta to Rio Hondo | BPUB |  | 345 | CAMERON |
| Loma Alta 345kV station and autotransformer | Construct a 345 substation and connect to the existing Loma Alta 138 substation. | BPUB |  | 345 | CAMERON |
| Sandow - Temple Switch 345 kV line | Upgrade Sandow - Temple Switch 345 kV line | TXU Electric Delivery |  | 345 | MILAM |

Status of active generation interconnection requests

| PUBLIC PROJECTS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | SiteName | County |  | Region | Fuel | In Service Date | MW into Grid | Notes |
| 05INR0014 | Sun Substation | Scurry |  | West | Gas | May-05 | 0 |  |
| 04INR0015 | Buffalo Gap 1 and 2 | Taylor |  | West | Wind | Sep-05/Nov-06 | 240 | 120 MW in 2005, 120 MW in 2006 |
| 04INR0020 | WKN Wind 1 Snyder | Scurry |  | West | Wind | Dec-05 | 61 |  |
| 05INR0010 | Jack County Generation Facility | Jack |  | North | Gas | Dec-05 | 700 | testing 6/1/05, commercial 12/1/05 |
| 06INR0008 | Big Spring Carbon Plant | Howard |  | West | Waste heat | Apr-06 | 12 |  |
| 03INR0034 | Silver Star Project | Erath |  | West | Wind | Jun-06 | 225 | 60 MW in 12/05; 165 later |
| 05INR0018 | Horse Hollow | Taylor |  | West | Wind | Jun-06 | 347 | 220 MW by 7/1/05, 127 MW by 6/1/06 |
| 05INR0015 | Gulf Wind | Kenedy |  | South | Wind | Jul-06 | 200 |  |
| 06INR0016 | Dow 9 | Brazoria |  | South | NG | Oct-06 | 0 |  |
| 05INR0015 | Gulf Wind | Kenedy |  | South | Wind | Sep-07 | 1,200 | 4 phases of 300 MW each (07, 08, 09, 10) |
| 01INR0028 | Orion Delaware Mt. Wind Farm | Culberson |  | West | Wind | Dec-07 | 175 |  |
| 06INR0006 | Cobisa-Greenville | Hunt |  | North | Gas | May-08 | 1,750 |  |
| 09INR0002 | J K Spruce 2 | Bexar |  | South | Coal | Aug-09 | 750 |  |
| 10INR0002 | Hugo Plant | Choctaw, OK |  | North | Coal | Dec-10 | 500 |  |
|  |  |  |  |  | Totals |  | 4,795 |  |
| PROJECTS INTO OPERATION |  |  |  |  |  |  |  |  |
| INR # | SiteName | County |  | Region | Fuel | In Service Date | MW into Grid |  |
| N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  |
| ACTIVE GENERATION INTERCONNECTION REQUESTS BEING PROCESSED |  |  |  |  |  |  |  |  |
|  |  |  | North | South | West | Total |  |  |
| Security Screening Study |  |  | 0 | 0 | 2 | 2 |  |  |
| SSS Completed |  |  | 1 | 3 | 10 | 14 |  |  |
| Full Interconnect Study |  |  | 7 | 5 | 8 | 20 |  |  |
| FIS Completed |  |  | 1 | 0 | 3 | 4 |  |  |
| Interconnect Agreement Completed (Includes public letters) |  |  | 3 | 3 | 7 | 13 |  |  |
| Capacity for Grid, MW |  |  | 4,549 | 3,660 | 6,104 | 14,313 |  |  |
| Wind MW (under development) |  |  | 480 | 2,830 | 5,237 | 8,547 |  |  |

Generation Currently Under RMR Contract in ERCOT (as of 6/1/05)

| Unit | Capacity (Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date |
| --- | --- | --- | --- | --- |
| BM Davis 2 | 356 | Under Contract | 1/1/05-12/31/05 | Under Review |
| JL Bates 1 & 2 | 183 | Under Contract | 1/1/05-12/31/05 | 3Q 2006 |
| La Palma 4, 5, 6, &7 | 249 | Under Contract | 1/1/05-12/31/05 | 1Q 2006 |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/05-12/31/05 | 3Q 2010 |
| PH Robinson 2 | 461 | Under Contract | 5/17/05-5/16/06 | Under Development |
| Total MW Under RMR: | 1,421 |  |  |  |

Studies underway or planned to be started within Transmission Services

- 345/138 kV Autotransformer outage congestion analysis and possible planning criteria change

- BM Davis Unit 2 RMR exit strategy review

- Bryan/College Station study continues.  Voltage collapse study is being performed for the years 2005, 2006, and 2010 to benchmark how planned transmission improvements affect the area’s voltage stability Bryan and College Station security study will be sent to the North Regional Planning Group in July

- Continue to enhance dynamic data models

- Continue to enhance fidelity of contingency files and testing

- Continue to enhance fidelity of planning base cases to better match real-time operating environment

- CSC determination and CM Zone calculations for 2006 is underway along with Training Market Support group

- CSC/CM 2005 zonal transfers dynamic limit evaluation (reliability/security protected information)

- DFW/NE 2009 Congestion Relief Study Scope is being developed with stakeholders

- Enhance generation data gathering efforts and model improvements

- ERCOT Process Improvement, reanalysis and documentation of processes

- Hays SPS revised and all TXU ED SPS were submitted to ERCOT are currently being reviewed.  Modifications to these SPS may be needed before final approval is given

- Improve functionality of “Operations and System Planning” internet site

- Killeen and Temple area security study.  Similar to the Bryan/College Station area, Shane Wallin and Jeff Billo will be performing the voltage analysis for the Killeen area, with assistance from Jose Conto

- Load modeling improvements and improvements to base case modeling

- Load stability modeling project- Phase II (EPRI Solutions) is starting

- Lower Rio Grande Valley analysis

- Net Dependable Capability Testing Data ERCOT staff efforts are ongoing to determine the fidelity of and best practices in planning for the generator data that is sent to ERCOT compliance

- October 1 Report work is underway

- Outreach program to help stakeholders understand planning activites

- PH Robinson 2 RMR exit strategy review

- Steady State WG 2006 set A base cases ERCOT staff review, many items identified

- Steady State WG base case (planning) and network model branch data (operations) comparison will be conducted on July 1

- Steady State WG base case and network model transformer rating comparison was performed in June and a summary was sent to the TDSP’s on June 22.  A follow-up comparison will be conducted around August 15 in order to measure the progress of updates

- Transient Voltage Dip analysis of the Corpus Christi area, work performed by Siemens/PTI in cooperation with Flint Hills, AEP TCC and Ercot System Planning

- Transmission Project Information Tracking (TPIT) investigate moving to online database with on demand changes and reporting

- Utility Wind Interest Group (UWIG) wind farm stability modeling effort continuing support

- West Texas ERCOT/ SPP joint study is underway to determine possible mutual benefits

- West-North transfer limit study, later this year

Studies that have been completed by Transmission Services and posting location

- DFW/NE 2006 congestion relief study is complete. The report is being presented to TAC and the ERCOT Board in July

- RMR initial determination completed for Valero Refining – Texas, L.P. Channel Unit 1 and 2 with a not needed determination

- RMR initial determination completed for Wharton County Power Partners New Gulf Unit 2 with a not needed determination

- SPS Approval Process has been approved internally by ERCOT Transmission Services and ERCOT System Operations.

- SPWG 2005 Future Year short circuit base cases for the years 2006 to 2009 are currently being built.  The first Pass has already been compiled.  Pass 2 corrections and additions have been received by all TDSPs.  The cases will be compiled and sent back to them for review

- Survey of Critical Voltage Stability Events Annual (reliability/security protected information) completed.  Results will be provided to transmission owners and compliance in July

Upcoming Events

- Steady State WG 2006 Data Set A cases will be posted in July

- NERC OC Transmission Subcommittee is being reorganized

- South RPG/RMR Exit meeting July 15 at ACC, review BM Davis and PH Robinson  RMR Exit Strategies

- NERC PC Transmission Issues Subcommittee Meeting August 3 & 4 in Dallas

Other Issues

- Began discussion with ERCOT Compliance in an attempt to ensure that future compliance surveys (e.g. UFLS) obtain data in a format that is more readily incorporated into system modes.

- Responding to NERC recommendations ROS Dynamics WG will simulate an actual event to test dynamic models.  DWG is reviewing an event to assess its suitability to the NERC recommendation scope

- National Renewable Energy Laboratory (NREL) is willing to perform stability studies together with ERCOT System Planning to validate the dynamic models of wind farm, subject to the availability of disturbance data for a transient event in the West Texas network

Interesting observations

- The change to Net Dependable Capability (NDC) values as Pmax of generating units in the latest network base cases (being created in 2005 for the year 2006 and beyond) will require that the dynamic data be tuned such that the numerical relationship between Pmax and Pgen does not create errors during dynamic simulations.  DWG members and ERCOT System Planning are working together to develop a process to adopt these changes

- Mothball/decommission of generation is reducing voltage stability margins

Future issues

- Developing/applying accurate generator reactive capability curves

- Combined Cycle Stability Model development postponed to 2006 due to budget reduction, is included in 2006 budget submission