## Merged Market List
2006 Project Prioritization - PUCT, Market and ERCOT Projects
Orange highlights: description that will be rewritten to add clarity
Source | Committee | Src Doc | Project | Proj. No. | Impact Area | Add'l Info | Priority | Level 2 Sort | Rank | CBA Score | Net Benefit | 2006 Cost Range | Running Total Range | Summary Description | Benefit Summary
PUCT | SO |  | Enhancements to MOMS ISR | 50002 | Market Monitoring | 2005 Carryover | 1 | 1 | 1 | 23 | -363069 | $100k-$500k | <$2M | Potomac Economics developed ISR software (Indices, Screening and Reporting) to aid the PUCT in exercising its regulatory responsibilities to monitor the ERCOT market. | Help ensure ancillary services are available at reasonable prices; deter illegal contact and anticompetitive behavior; help identify market power abuses and prevent their reoccurence; promote fair and competitive market operations; help eliminate loopholes and flaws in market design
PUCT | SO |  | Enhancements to MOMS Study Market Clearing Engines | 50003 | Market Monitoring | 2005 Carryover | 1 | 1 | 2 | 23 | -277874 | $100k-$500k | <$2M | This Project would involve implementing some enhancements to which have been identified as being valuable for MOMS (Market Oversight and Monitoring System). Descriptions of many of these enhancements are captured as SPRs in the Areva issue tracking system. | Help ensure ancillary services are available at reasonable prices; deter illegal contact and anticompetitive behavior; help identify market power abuses and prevent their reoccurence; promote fair and competitive market operations; help eliminate loopholes and flaws in market design
Market | RMS | SCR738 | Enhancement to FasTrak Tools | 50007 | Market Impact | 2005 Carryover | 1 | 2 | 3 | 20 | 18301584 | $100-$500k | <$2M | FasTrak is the retail transaction issue resolution tool. The system currently in place does not include the capability to track issues by variables such as ESI ID or TDSP, and does not allow determination of issue aging. In addition, the tool cannot be queried and interfacing with the tool is somewhat cumbersome. The FasTrak tool needs to be made more user friendly and enhanced with features that will allow issues to be better tracked and manipulated by Market Participants for purposes of better managing the retail transaction issue resolution process. | Significant direct cost savings and time efficiencies for CRs and TDSPs. CBA estimates varying amounts of savings depending on size of market participant.
Market | RMS | SCR739 | Potential Load Loss | 50023 | Market Impact | 2005 Carryover | 1 | 2 | 4 | 11 | 895240 | $100k-$500k | <$2M | Provide CR’s with a daily extract of customer loss notifications based on ERCOTs receipt of a TDSPs accepted response to a transaction that would cause a CR to lose the customer (and their associated load). The extract would be available via the ERCOT Portal. | Estimated savings of $20,000 per year per CR due to improved accuracy in scheduling power.
Market | RMS | SCR740 | Enhancements to SCR727 | 50024 | Market Impact | 2005 Carryover | 1 | 2 | 5 | 15 | 3532131 | $500k-$1M | <$2M | Suggested modifications include, but are not limited to: • Providing usage to CRs for backdated LSE Relationship Changes • Including a file name or number in order to identify the order in which SCR727 files should be loaded by the MP • Auditing capabilities to allow MPs the function to confirm the accuracy of their extracts • Ability to link a dB change back to the source of the change (i.e. FasTrak issue, batch processing) | 8 hours savings per day per CR due to fewer D2D and DEV FasTrak issues.
Market | RMS | PRR312 | Enhance ESIID Lookup Function | 50025 | Market Impact | 2005 Carryover | 1 | 2 | 6 | 14 | 726865 | <$100k | <$2M | Provide additional information for an ESI ID to include Station ID, Power Region, Premise Type, status (active/de-energized/inactive) for an ESI ID. In addition, advise if there is a pending Move In/Move Out for the ESI ID. | 1 hour time savings per week per CR due to increased efficiencies
ERCOT | IO |  | 2005 Storage to Support Ongoing Operations | 50125 | Infrastructure | 2005 Carryover | 1 | 3 | 7 | 23 | 4630932 | <$100k | <$2M | Addition and optimization of data storage to meet ongoing demands | Establish Homogeneous storage infrastructure; Reduce storage management overhead; Improve continuity of storage related to business continuity (DR); Improve reporting accuracy and timeliness;Reduce the O&M overhhaed for storage reporting
ERCOT | RO |  | SOA consolidated Retail Transactions | 50121 | Market Impact | 2005 Carryover | 1 | 3 | 8 | 21 | 3244060 | $100k-$500k | $2M-$4M | The Service Oriented Architecture (SOA) project is comprised of a series of sub-projects designed to implement a service-oriented architecture – a collection of services on a network that communicate with one another, making it easier to integrate applications. The goals of SOA include the following: o Replace SeeBeyond EAI technology with TIBCO EAI technology; o Deploy Service Oriented Architecture (SOA) methodology/framework; o Deploy sufficient TIBCO licensing footprint to support ERCOT’s future integration needs through 2007. | Expected efficiency gain of 32% on current application interface development time. Reduced need for data center expansion due to consolidation of application interface activities in a common architecture.
ERCOT | RO |  | TX SET 2.1 | 40034 | Market Impact | 2005 Carryover | 1 | 3 | 9 | 15 | -4786014 | <$100k | $2M-$4M | To implement changes to retail transactions as identified by TX SET in support of the RMS directed Task Forces, DNP, TITF, and 810/867/824 Workgroup for the Texas Electric Retail Market… 1. Support the MOU/EC entrance, 2. Disconnect for Non-Pay process, 3. Communication of additional billing determinants to the ERCOT's Electric Retail Market | Enhancements to systems to accommodate MOU/EC participants into the Retail Electric Market; enhancements to billing determinants for better customer service by the CR
ERCOT | SO |  | Operator Training Simulator/Testing Simulation Environment | 40090 | Compliance | 2005 Carryover | 1 | 3 | 10 | 18 | 1426448 | >$3M | $6M-$8M | This project will deliver an Operator Training Simulator (OTS) for use in training System Operators to handle normal and emergency system conditions | Current cost of ancillary service (including congestion) is about 500M$/year - Improved operator training woud improve operation efficiency - Assuming saving of 0.5% of this cost per year, would give 2.5 M$/year
ERCOT | SO |  | CSC Thermal & Volt Limits Calculations/Posting | 30084 | ERCOT Operations | 2005 Carryover | 1 | 3 | 11 | 18 | 22486 | <$100k | $6M-$8M | The objective of this project is to eliminate the daily and time consuming manual work around for calculating and posting CSC Limits and move from a day-ahead calculation to a more near real-time calculation; hence, improving the accuracy and consistency of CSC Limits and potentially greatly decreasing congestion costs. | Internal savings of 6 hours per workday performing manual limit calculations
ERCOT | SO | PRR425 | Outage Scheduler Enhancements Phase II | 40084 | Market Impact | 2005 Carryover | 1 | 3 | 12 | 19 | 916617 | <$100k | $6M-$8M | These enhancements will provide the Outage Coordination team the capability to supply better information on outages to the Market and ERCOT, as well as comply with PRR 425 mandates | Reduce unnecessary congestion management costs due to incorrect outage approval - 2 incidents per year at a cost of $250,000 per incident
ERCOT | SO |  | Incident Report | 40086 | ERCOT Operations | 2005 Carryover | 1 | 3 | 13 | 17 | -95351 | <$100k | $6M-$8M | (1) Improve Protocol violation creation accuracy and efficiency. (2) Enable Routing, Approval, Trnasmittal of Notifications and Status tracking to Stakeholders. (3) Archive all Vilation Transmittals, Dates Sent, Dates Received, and Dates Resolved and provide reporting capability per Market Participant. (4) Provide a "tickler" function for alerting compliance and Operations shift supervisor of overdue responses. (5) Enable coordinated and responsive updates to the system regarding protocol references, violation per protocol reference, assigned client rep, and MP contact person. | Reduction in manual effort: 0.5 hours per workday
ERCOT | IO |  | Capacity True Up | 50013 | Infrastructure | 2005 Carryover | 1 | 3 | 14 | 18 | -172477 | 0 | $6M-$8M | Create a long term solution to the discrepancies found between Production and the lower environments. Evaluate present lower environment as compared to production. Create an architectural plan to address discrepancies. Relocate, upgrade or add hardware where necessary. | Significant intangible benefits: Addresses existing, high level issue related to reliability performance; Consistency - by making these hardware changes will eliminate at least some of the issues seen in major rollouts from test to production.
ERCOT | IO |  | EDW BI Reporting Tool | 50004 | Market Monitoring | 2005 Carryover | 1 | 3 | 15 | 24 | 15276127 | <$100k | $6M-$8M | Enable consistent and efficient reporting for the PUCT, ERCOT, and eventually, MPs. Implementation of the BI Tool will enable users to translate business questions into optimized queries. | Adding new services for the PUCT and the Market do not always create cost savings for ERCOT. This is a framework project and will have larger downstream impacts on cost savings, through additional secured access to information by the PUCT and the Market.
ERCOT | IO |  | Altiris DC Implementation | 50028 | Infrastructure | 2005 Carryover | 1 | 3 | 16 | 20 | 8321 | $100k-$500k | $6M-$8M | Implement Altiris monitoring software in the Data Center Environment. Be able to run reports on all systems against a known good configuration. Enable comparison of two systems to one another to analyze differences between the systems for troubleshooting purposes. | Upon review of audit results, issues were discovered and recommendations were made to improve security/safety issues that required response prior to the next audit.
ERCOT | IO |  | EDW EMMS Reports | 50005 | Market Impact | 2005 Carryover | 1 | 3 | 17 |  | 0 | 0 | $6M-$8M | Transition PUCT, ERCOT, and MP reporting to the EDW EMMS ODS | The legacy Data Archive has design limitations that do not enable ERCOT to capture all necessary business data. Maintenance of and development is significantly expensive. Objective: Transition PUCT, ERCOT, and MP reporting to the EDW EMMS ODS
ERCOT | IO |  | Lodestar Extracts | 40042_06 | Market Impact | 2005 Carryover | 1 | 3 | 18 | 25 | 1013815 | 0 | $6M-$8M | To migrate the Generation, Load, Settlements & Billing, and Shadow Pricing extracts from the Data Archive to the ODS (Operational Data Store). | Market benefit: 10 minutes of savings per day per Market Participant due to optimized data access.
ERCOT | CO |  | Intrusion Detection/Intrusion Protection | 50132 | Security / Audit | 2005 Carryover | 1 | 3 | 19 | 23 | -925451 | 0 | $6M-$8M | Implement Network Intrusion Detection and Intrusion Protection Systems into the ERCOT network at the perimeter and internal network layers. | Allows ERCOT to appropriately respond to E&Y audit findings; improves monitoring capability of data transported across the network, allowing for the identification of attack or malware activity
ERCOT | CO |  | Collateral Calculation | 50017 | Market Impact | 2005 Carryover | 1 | 3 | 20 | 17 | 26954 | 0 | $6M-$8M | Automate much of the "data gathering" piece of credit monitoring that is currently done manually using Excel spreadsheets. | Significant intangible benefits plus time savings in Credit group due to automation of collateral calculations
ERCOT | CO |  | Lawson SIR - Time Tracking | 50015_01 | ERCOT Operations | 2005 Carryover | 1 | 3 | 21 | 18 | 63910 | 0 | $6M-$8M | Replace manual Excel time tracking with online Lawson entry system for ERCOT employee time reporting | Internal ERCOT benefit: increased efficiencies in Finance department and improved ease of time entry for ERCOT employees
PUCT | IO |  | EDW BI Foundation P2 - Repl Reserves Market Ad-hoc Reporting | 50001_03 | Market Monitoring | EDW | 1.1 | 1 | 22 |  | 0 | 0 | $6M-$8M | Sub-project 50001_03 asks for the creation of an ad-hoc reporting piece for the new (not yet in place, to be created as part of EMMS Release 4) Replacement Reserves Market | The EDW will minimize the necessity for PUCT and ERCOT users to manually manipulate data for reporting, thereby improving the consistency and accuracy of ERCOT reports. It will serve as the logical foundation for all extracting and reporting.
PUCT | IO |  | EDW BI Foundation P2 - Ad-hoc Access to QSE Rpt Data | 50001_04 | Market Monitoring | EDW | 1.1 | 1 | 23 |  | 0 | 0 | $6M-$8M | Sub-project 50001_03 asks for the creation of an ad-hoc reporting piece for the new (not yet in place, to be created as part of EMMS Release 4) Replacement Reserves Market | The EDW will minimize the necessity for PUCT and ERCOT users to manually manipulate data for reporting, thereby improving the consistency and accuracy of ERCOT reports. It will serve as the logical foundation for all extracting and reporting.
PUCT | IO |  | EIS BI Foundations III | New | Market Monitoring | EDW | 1.1 | 1 | 24 | 25 | -195455 | $100k-$500k | $6M-$8M | Enable consistent and efficient reporting for the PUCT, ERCOT, and, eventually, MPs. This project will roll out a third set of Business Intelligence (BI) components per the PUCT's requests. | Improve ERCOT's reliability performance; cyber security; efficiency; and accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market.
PUCT | SO |  | Increase Number of Seats for Study Market Clearing Engines | New | Market Monitoring | PUCT | 1.1 | 1 | 25 | 23 | -224062 | $100k-$500k | $6M-$8M | This Project would involve increasing the number of seats for the Study Market Clearing Engines from two to unlimited. | Help ensure ancillary services are available at reasonable prices; deter illegal contact and anticompetitive behavior; help identify market power abuses and prevent their reoccurence; promote fair and competitive market operations; help eliminate loopholes and flaws in market design
PUCT | SO |  | Enhancements to MOMS Metrics and Reports | New | Market Monitoring | PUCT | 1.1 | 1 | 26 | 23 | -500000 | $100k-$500k | $6M-$8M | This Project would involve implementing enhancements to the Market Monitoring Reports and Metrics in the MOMS software. These enhancements will be in the areas of: User Interface Improvements, Additional Indices and Screens, and Additional Alerts and Automated Reporting. | Help ensure ancillary services are available at reasonable prices; deter illegal contact and anticompetitive behavior; help identify market power abuses and prevent their reoccurence; promote fair and competitive market operations; help eliminate loopholes and flaws in market design
PUCT | IO |  | EIS Conformed Data Warehouse Foundations | New | Market Monitoring | EDW | 1.1 | 1 | 27 | 29 | 48620154 | $1M-$3M | $8M-$10M | Roll out the architecture and framework for the next generation data warehouse environment. This project is in direct support of Section 17 of the Protocols and is a required element to directly support the PUCT and the Market. | Market cost savings equates to 2 hours of savings per day per participant, through optimized access to data, additional data access, and analytical processes to be rolled out at a later time through data marts
PUCT | IO |  | EIS CDW Data Marts | New | Market Monitoring | EDW | 1.1 | 1 | 28 | 25 | 24350470 | $500k-$1M | $8M-$10M | Roll out first wave of data marts in the next generation data warehouse environment. Understand the PUCTs initial need for mart build-out and project future needs This project is in direct support of Section 17 of the Protocols and is a required element to directly support the PUCT and the Market. | Market cost savings equates to 1 hour of savings per day per participant, through optimized access to data, additional data access, and analytical processes to be rolled out at a later time through data marts
Market | COPS |  | TML Phase 3 - Wholesale Enhancements | 40103 | Market Impact | Market | 1.1 | 2 | 29 | 18 | 11145103 | $500k-$1M | $8M-$10M | The scope of Phase 3 will focus on user experience enhancement of the new portal platform for ERCOT Wholesale Market Participants. The goal is to incorporate additional functionalities and enhanced usability to fill in gaps between the current portal and the needs of QSEs, Transmission Operators and Resources. | 50 impacted QSE's, 3 hours per calendar day savings in scheduling, 1 hour per workday in settlement mismatch analysis
Market | RMS | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--project to improve availability and reduce outages in key retail commercial applications. | New | Market Impact | Market | 1.1 | 2 | 30 | 24 | In Progress | $1M-$3M | $10M-$12M | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745 | Savings based on cost estimates of data cleanup due to outages: 4 large incidents per year at $25k each; 20 small incidents per year at $5k each.
Market | RMS |  | Performance Measures Reporting Requirements (changes to Project 24462) | New | Market Impact | Market | 1.1 | 2 | 31 | 18 | -1000000 | $1M | $12M-$14M | Expected project needed to enhance reporting systems as a result of T&Cs requirements effecting PUCT Performance Measures Project 24462 | TBD
Market | RMS |  | Terms and Conditions requirements, not limited to Texas SET changes | New | Market Impact | Market | 1.1 | 2 | 32 | 17 | -500000 | $500k | $12M-$14M | To implement Public Utility Regulations as they relate to the establishment of non-discriminatory terms and conditions of retail delivery service, including delivery service to a Retail Customers provided by a transmission and distribution utility (TDU). Certain transactions and system processes must be created and others modified to accomplish the regulatory requirements. | TBD
ERCOT | IO |  | 2006 Minor Capital | New | Infrastructure | Infrastructure | 1.1 | 3 | 33 |  | 0 | $1M-$3M | $14M-$16M | Capital purchases over the course of the year: new desktop and laptop systems, SAN switch upgrades, voice recording system for Outage Coordinators, add'l Mercury Interactive licenses, etc. | Continued maintenance activites in support of ERCOT's infrastructure
ERCOT | RO |  | SOA Extend Footprint | New | Market Impact | Enhance-ment | 1.1 | 3 | 34 | 21 | 1165368 | $1M-$3M | $16M-$18M | This project will continue the strategic implementation, approved by the BoD, of Service Oriented Architecture (SOA) using TIBCO technology. It includes: o Continued replacement of integration points within ERCOT with TIBCO technology. o Implementation of new business processes to address replacement of outdated automated and/or manual business processes. | Internal ERCOT savings due to manual process reduction and reduction in project manual processes; reduction of licensing in software products replaced by TIBCO
ERCOT | SO |  | DC Tie Automation & Scheduling | 40036 | Market Impact | Initiating in 2005 | 1.1 | 3 | 35 | 23 | 52677463 | $1M-$3M | $18M-$20M | To automate as much as possible the current manual processes that consume considerable ERCOT resources in managing and accounting for energy flow across the DC Ties. To provide the ERCOT System Operator with a tool to properly schedule transactions across the DC Ties with Mexico. | Reduced energy cost due to import from Mexico: 80 MW * $30 * 24 hours * 365 days
ERCOT | MO |  | Replace Maestro | New | Infrastructure | Initiating in 2005 | 1.1 | 3 | 36 | 22 | 380296 | 0 | $18M-$20M | This project will investigate the replacement of ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below: • Maestro is currently not supported – Major upgrade required • Maintenance cost expensive due to CPU Pricing Model • Security Risk – passwords not encrypted • Preventing upgrade of DBMS and Operating System • Uses a Proprietary Database | Increased efficiencies in script creation, testing and maintenance (6 hours per day); Change migration efficiency; Improved job scheduling capabilities
ERCOT | CO |  | Iron Mail Implementation | 50141 | Security / Audit | Initiating in 2005 | 1.1 | 3 | 37 | 17 | -107189 | 0 | $18M-$20M | Replace present Spam management system with IronMail - Update: merging with E-mail Security project and initiating in 2005 | Reduce support costs for spam filtering
ERCOT | RO |  | Enhance Digital Certificate Program | New | Market Impact | Process Improve. | 1.1 | 3 | 38 | 15 | 4074838 | $100k-$500k | $18M-$20M | ERCOT is implementing a 2005 project, VeriSign Upgrade Project (PR 40107), that is upgrading ERCOT’s digital certificate technology from the vendor’s Lite to the Enterprise version. This 2006 project is a follow-up that will take advantage of features/enhancements in the Enterprise version not included in the scope of the 2005 project. | Estimated savings: 6 hours of maintenance per digital certificate per year
ERCOT | SO |  | Network Model Management System (NMMS) | New | ERCOT Operations | Initiating in 2005 | 1.1 | 3 | 39 | 24 | 879954 | $1M-$3M | $20M-$22M | Business has the following objectives with the implementation of this project: (1) Provide improved reliability by mitigating risk associated with model delays or premature implementations. (2) Provide an improved timeline and data management flow for modeling transmission grid modifications. (3) Improves the Market by providing predictable, consistent, and efficient implementation of transmission grid modifications. (4) Timely accurate modeling provided would promote improved Ancillary Service management. (5) Improve the accuracy of the Operation model. | Reduction of manual modeling workarounds (4 hours per day); avoid FTE increase in this area (3 FTE's)
ERCOT | SO |  | Topology Estimation System | 40061 | ERCOT Operations | Initiating in 2005 | 1.1 | 3 | 40 | 16 | 1190876 | $500k-$1M | $22M-$24M | With this additional software application functionality added to the SE environment the accuracy and reliability of the SE solution will be improved leading to increased accuracy of all downstream real-time sequence processes. | Reduce congestion cost due to topology errors: 2 incidents per year at $250k each; also, faster identification of issues: 1 event per month identified 4 hours earlier (100 MW * $30 *4 * 12 months)
ERCOT | CO |  | Risk Management (incl Security Auditing and Monitoring SW) | New | Security / Audit | Security | 1.1 | 3 | 41 | 27 | -349170 | $100k-$500k | $22M-$24M | To acquire software for the purpose of identifying vulnerabilities within the network, operating systems and applications. Provide automated, real time capabiliteis to audit and monitor compliance with ERCOT's security infrastructure, policies, and procedures. | Improve ERCOT's ability to identify vulnerabilities associated with the network, internet-facing applications and other cyber-critical applications
ERCOT | SO | PRR525 | SCE Performance and Monitoring | 50130 | Market Impact | Compliance | 1.1 | 3 | 42 | 23 | 6382530 | $100k-$500k | $22M-$24M | Provide real-time SCE Performance Monitoring and reporting capability for PRR525 that was approved by the ERCOT BOD. | Savings estimate: 0.5% of ancillary service market (0.005 * $500,000,000)
ERCOT | MO |  | MV90 Upgrade Part 2 - Installation of Software | 50033_02 | Infrastructure | Initiating in 2005 | 1.1 | 3 | 43 | 14 | 46011 | 0 | $22M-$24M | This project will install and implement the MV-90 software upgrade that was purchased in 2005. Support of the current product version ends in 2007. | Automation of manual tasks (1 hour per workday); Allow TDSPs to select new meter types for deployment as EPS meters
ERCOT | CO |  | Vendor and Contract Management | 50111 | Security / Audit | Process Improve. | 1.1 | 3 | 44 | 21 | -254403 | $100k-$500k | $22M-$24M | Provide database which provides tracking and reporting regarding all vendors and vendor contracts,.to help enforce company policies, procedures, and financial reporting. Regulatory support to include: Sarbanes-Oxley, Corporate Contract Management Procedures. | Resolves an audit finding and increases internal controls; provides more efficient reporting capabilities; increases reliability of information about vendors and vendor contracts
ERCOT | RO |  | ESI ID Account Table Split | New | Infrastructure | Process Improve. | 1.1 | 3 | 45 | 18 | 835672 | $100k-$500k | $22M-$24M | Normalize type of data associated to business objects. Multiple business objects are using the same tables which are growing large causing performance and scalability issues. | Increased efficiences in development and integration time as well as end user interaction (approximately 12 hours per day)
ERCOT | MO |  | DC Tie Automation (Pk2 Only) | 50018 | Market Impact | Process Improve. | 1.1 | 3 | 46 | 19 | 25041 | $100k-$500k | $22M-$24M | This project will implement the EAA and CRC DC Tie accounting tasks that are currently being performed manually for settlement. It is recommended to work this project with the Package 1 component although some automation may be achieved without it. | Automation of various manual aspects of DC Tie accounting (approximately 750 hours per year [1/3 FTE])
ERCOT | CO |  | Host Intrusion Detection System | New | Security / Audit | Security | 1.1 | 3 | 47 | 26 | -298222 | $100k-$500k | $22M-$24M | The development of a system for reporting attacks against individual servers thereby increasing the granularity of incident monitoring and investigation. | Event correlation gives ERCOT the ability to identify incidents at a very early stage and mitigate damages; increased productivity of Security Operations group
ERCOT | RO |  | EDW Siebel Transition | 50059 | Infrastructure | EDW | 1.1 | 3 | 48 | 23 | 448938 | $500k-$1M | $24M-$26M | Transition of Siebel reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday)
ERCOT | RO |  | EDW TCH (Transaction Clearinghouse) Transition | 50060 | Infrastructure | EDW | 1.1 | 3 | 49 | 23 | 743338 | $100k-$500k | $24M-$26M | Transition of TCH reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday)
ERCOT | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061 | Infrastructure | EDW | 1.1 | 3 | 50 | 23 | 743338 | $100k-$500k | $24M-$26M | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday)
ERCOT | RO |  | ETS (ESIID Tracking System) Transition to EDW | 50088 | Infrastructure | EDW | 1.1 | 3 | 51 | 21 | 1185671 | $500k-$1M | $26M-$28M | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Improved reporting and analysis efficiency (7 hours per workday); Improved development efficiencies (16 hours per workday)
ERCOT | SO |  | Operations Support Study Environment/Disaster Recovery Test Environment | 50052 | Infrastructure | Enhance-ment | 1.1 | 3 | 52 | 18 | 329414 | $500k-$1M | $26M-$28M | Conflicts with Test environment scheduling indicate the need for Operations Support group to be able to study conditions independent of production and test environment. This project will provide the necessary environment. | Reduce unnecessary congestion management costs due to incorrect outage approval - 2 incidents per year at a cost of $250,000 per incident
ERCOT | MO |  | Lodestar 4.0 Upgrade | 40066_04 | Infrastructure | Software Upgrade | 1.1 | 3 | 53 | 19 | 26444 | $100k-$500k | $26M-$28M | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs | Nightly processing speed improvement; improved data editing capabilities (0.5 hours per workday); enhanced querying capability for users (0.5 hours per workday)
ERCOT | SO |  | Integrate Risk Based Transmission Reliability Analysis Tool into RT and Study Mode | New | ERCOT Operations | Enhance-ment | 1.1 | 3 | 54 | 16 | 3744643 | $100k-$500k | $26M-$28M | Provide Risk based security assessment results in terms of: (1) Identify which double circuit contingency/overloads exceed a risk threshold which justifies congestion management action; (2) Provide screening to identify “most risky” contingencies, including N-2 events; (3) Evaluate consequences of contingency events, including voltage instability risk, cascading risk, low voltage risk, etc. | Estimated reduction of double circuit base congestion (10% * $15,000,000)
ERCOT | CO |  | Forensics and Investigations | New | Security / Audit | Deferring to 2007 | 1.1 | 3 | 55 | 26 | -253828 | 0 | $26M-$28M | Software and hardware to support the detailed investigation of cyber security incidents. Update: this project will be revisited in 2007. | Augments the intrusion detection/protection system by allowing mapping of network-based threats
ERCOT | IO |  | Windows Domain Restructuring | New | Infrastructure | Infrastructure | 1.1 | 3 | 56 | 21 | 122841 | $100k-$500k | $26M-$28M | Restructure Windows forest under ercot.com domain as an implementation of best practices. This project should result in one Windows Domain with proper trusted relationships among the environments. | Improve ERCOT's reliability performance. Proper infrastucture design is necessary for all projects and effects implementation and management of all systems.
ERCOT | SO |  | Operator Interface Enhancements | New | ERCOT Operations | Enhance-ment | 1.1 | 3 | 57 | 18 | 713028 | $100k-$500k | $26M-$28M | This project consists of three distinct enhancements: 1) Offset Spreadsheet Replacement; 2) Constraint Entry Check/Validation; 3) Transmission Security Spreadsheet | Reduction in balancing energy cost due to improvement in offset value
ERCOT | SO |  | Breaker to Breaker One Lines/System Map | 50083 | ERCOT Operations | Enhance-ment | 1.1 | 3 | 58 | 18 | -732819 | $500k-$1M | $28M-$30M | Provide graphical representation of system-wide connectivity. Provide ability to view all or part of the ERCOT system including powerflow. This project should provide the operator the ability to navigate easily from one station or substation to another in a one-line diagram format.
ERCOT | CO |  | Log and Event Management | 50140 | Security / Audit | Initiating in 2005 | 1.1 | 3 | 59 | 27 | -655320 | 0 | $28M-$30M | Through the use of robust technology, identify, correlate and investigate possible incidents where systems were attacked directly (popularly know has hacking) or indirectly (worms, viruses and denial of service). Allow a single console system to permit the investigation of Intrusion Detection, Operating System, Application logs for event detection and analysis. | Manual monitoring of logs is impossible without either a software solution or a large number of analysts. A software solution is recommended.
ERCOT | CO |  | Email Security | 50141 | Security / Audit | Initiating in 2005 | 1.1 | 3 | 60 | 29 | -346746 | 0 | $28M-$30M | Provide the ability to encrypt email that may contain confidential or restricted information. | Response to an audit finding that sensitive data sent between ERCOT and Market Participants across the internet is encrypted.
ERCOT | IO |  | Firewall Modules Between Internal Subnets | New | Infrastructure | Infrastructure | 1.1 | 3 | 61 | 28 | -132651 | $100k-$500k | $28M-$30M | Separation of CORP Servers from Workstation Envrionment. This will provide for a more secure and segmented environment. | Improve ERCOT's reliability performance; security; accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market; and supports the baseline architecture that delivers current services.
ERCOT | SO |  | EMMS Production Support Process Automation | 50065 | ERCOT Operations | Process Improve. | 1.1 | 3 | 62 | 17 | 92451 | $100k-$500k | $28M-$30M | This project will provide the following capabilities: Increased Automation of the current EMMS database load procedures. Increased Automation of the current EMMS Site Failover procedures. Monitoring processes and alarming. | Increase automation of tasks in EMMS Production Support (0.5 FTE savings)
ERCOT | CO |  | Lawson 8.1 Upgrade | New | Infrastructure | Software Upgrade | 1.1 | 3 | 63 | 19 | 177090 | $100k-$500k | $28M-$30M | Upgrade Lawson Application Suite and Environment to version 8.1 | Internal ERCOT benefit: increased efficiencies in various areas and reduced cost and risk in maintaining unsupported software
ERCOT | SO |  | Replace DSM6 High-Speed Frequency Recorder | 30021 | Infrastructure | Initiating in 2005 | 1.1 | 3 | 64 | 24 | -92757 | 0 | $28M-$30M | Add redundant high speed frequency recorder to ensure reliable capture of frequesncy disturbances. | Intangible benefits: Supports NERC Standards and Reporting requirements; increases accuracy of reportable frequency disturbance events data; provides sub-second accuracy data for monitoring LAAR, under-frequency load shed, and system frequency response.
ERCOT | IO |  | User Provisioning | 50034 | Infrastructure | Infrastructure | 1.1 | 3 | 65 | 17 | 1539157 | $100k-$500k | $28M-$30M | To provide ERCOT with a user provisioning and password synchronization/management software solution. (Software provider is M-Tech Inc., and the software package is called ID-Synch and P-Synch.) | User Provisioning Software will automate much of EAC position. In addition, this project will provide intangible benefits related to productivity and NERC compliance.
ERCOT | CO |  | Document Management | 50123 | ERCOT Operations | Process Improve. | 1.1 | 3 | 66 | 24 | 8370569 | $100k-$500k | $28M-$30M | To implement a document management system and roll out to one or more ERCOT departments in addition to the current HR, Legal, and Finance implementation. | Improved efficiency in document handling within ERCOT
ERCOT | IO |  | EDW Lodestar Decommission | 50030 | Infrastructure | EDW | 1.1 | 3 | 67 | 29 | 67868 | $100k-$500k | $28M-$30M | Transition reporting to the EDW Lodestar ODS. | Reduction of support costs of over 50% (10 hours per day to 4 hours per day)
ERCOT | IO |  | EDW EMMS Decommission | 50031 | Infrastructure | EDW | 1.1 | 3 | 68 | 29 | 81234 | <$100k | $28M-$30M | Transition reporting to the EDW EMMS ODS | Reduction of support costs of over 50% (10 hours per day to 4 hours per day)
ERCOT | IO |  | EIS Reporting Tool II | New | Market Monitoring | EDW | 1.1 | 3 | 69 | 24 | 14054788 | $1M-$3M | $30M-$32M | Enable consistent and efficient reporting for the PUCT, ERCOT, and MPs. Implementation of the reporting tool will enable users translate business questions into optimized queries. This project rolls out reporting functionality and additional licensing from the framework project 50004. | Market benefit: Create efficiencies in information retrieval (1 hour per workday savings for all Market Participants)
ERCOT | CO |  | Lawson SIR - Process Flow | 50015_02 | Security / Audit | Process Improve. | 1.1 | 3 | 70 | 19 | 145389 | $100k-$500k | $30M-$32M | Implement Lawson Process Flow to enable workflow processing within Lawson. 1) Automation of requisition approval process; 2) Email notifications to approvers when a requisition is awaiting their approval; 3) Peform the financial control of allowing only certain users to approve GL entries over a specific amount | Reduction in manual effort tracking purchase orders
ERCOT | IO |  | IPC Line Networking | New | Infrastructure | Infrastructure | 1.1 | 3 | 71 | 19 | -137394 | $100k-$500k | $30M-$32M | Implementation of Line Networking to facilitate improved operation of the IPC Trader Phone. This will provide System Operations with additional site failover options. | Provides additional site failover capabilities. Telecommunications project.
ERCOT | SO |  | EMMS Software Upgrade - OSI PI, OAG | New | Infrastructure | Initiating in 2005 | 1.1 | 3 | 72 | 18 | -160250 | 0 | $30M-$32M | This project will address the upgrade of two important software applications to the business users: 1) Open Access Gateway applications upgrade; 2) 2. OSI-soft Historian upgrade | Intangible benefit: Upgrades to OSI PI and OAG will bring us back to versions supported by our vendors
ERCOT | CO |  | Computer Aided Facilities Mgmt | New | ERCOT Operations | Process Improve. | 1.1 | 3 | 73 | 22 | 24100 | <$100k | $30M-$32M | This project supports: • Long-range and annual facility planning • Facility financial forecasting • Real estate acquisition and/or disposal • Work specifications, installation and space management • Architectural and engineering planning and design • New construction management and build-out • Maintenance and operations management • Telecommunications integration, security and general administrative services • Floor plans • Building and property information • Space characteristics and usage • Employee and occupancy data • Workplace assets (furniture and equipment) • Business continuity and safety information • LAN and telecom information | Enhance asset management reporting; automate key business processes (6 hours per workday)
ERCOT | SO |  | Improvements to Voltage and Transient Stability Studies (VSA/TSA) Phase II | 50029 | ERCOT Operations | Process Improve. | 1.1 | 3 | 74 | 19 | -266337 | $100k-$500k | $30M-$32M | Requirements for DSA (aka TSAT) specified in Release 3/4 deferred to future release. | Intangible benefits: Improved CSC and TGR calculations; improved accuracy of overall system reliability by analyzing unmeasured risk; improved ability to monitor RMR unit commitment needs as related to transient stability
ERCOT | IO |  | Austin QA Buildout | 40070 | Infrastructure | Infrastructure | 1.1 | 3 | 75 |  | 0 | $500k-$1M | $32M-$34M | The ability to run concurrent application tests, using equipment that will match more closely the production environment. Create a production functional equivalent for integration, regression, and negative testing, and for User Acceptance testing, break-fix, and volume testing.
ERCOT | IO |  | Disk Based Backup | 50027 | Infrastructure | Infrastructure | 1.1 | 3 | 76 | 20 | -437582 | $100k-$500k | $32M-$34M | Remove the overhead and performance impact of backups on production systems to increase performance and meet the needs of current growth | Increased efficiency in performing data restores and refreshing test environments. Savings in tape cartridges ($120k per year). Eliminates risk of unrecoverable data due to tape error.
ERCOT | IO |  | TCC Data Center Virtualization | New | Infrastructure | Infrastructure | 1.1 | 3 | 77 | 25 | 0 | $3M-$5M | $36M-$38M | Analysis of this situation, using internal expertise, and outside consulting expertise, validates the need to expand the Taylor Data Center in order to maintain the necessary redundant capacities. | Addressing power and cooling limitations will allow ERCOT to continue to effectively support ongoing operations and additional capital projecte requirements
ERCOT | IO |  | Market Facing Redundancy | New | Market Impact | Duplicate Deletion | 1.1 | 3 | 78 | 21 | 2281129 | $500k-$1M | $36M-$38M | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745 | Internal ERCOT savings in server maintanence (15 hours per workday)
ERCOT | SO |  | EMS Archive Comparison Tool Phase II | 50039 | ERCOT Operations | Process Improve. | 1.1 | 3 | 79 | 16 | 1029079 | $100k-$500k | $36M-$38M | This project will add deferred requirements to the R4 delivered case comparision capability. Some of the deferred requirements are, The ability to compare fields on multi-dimensional tables, The ability to compare fields on records that have no key field, The ability to compare something other than all of the fields in a database is very useful. It would be ideal if a dedicated comparison attribute was added to the Habitat database schema. This field would exist for the exclusive use of the comparison tool and would allow developers to flag fields of interest from a comparison perspective and eliminate the overloading of the MODELING field. | Reduce unnecessary congestion management costs due to modeling error - 2 incidents per year at a cost of $250,000 per incident
Market | RMS |  | Mass Customer Transition | 40038 | Market Impact | Candidate to Reprioritize | 1.2 | 2 | 80 | 16 | 2642217 | $1M-$3M | $38M-$40M | Certain circumstances may arise during the course of business in the Texas retail electric market that may necessitate the transition of ESI IDs from one CR to another or one TDSP to another in quantities and on a time frame that is not completely supported by standard market transactions or business processes. For a detailed outline of the business process and responsibility of all Entities involved in the transition, refer to the approved RMS Retail Customer Transition procedures documented in the Retail Market Guide. | Estimated savings of $100k per year per TDSP and $100k per year per POLR CR.
Market | COPS | SCR743 | Settlement Disputes Extract (QSE Dispute Extract) | New | Market Impact | Candidate to Reprioritize | 1.2 | 2 | 81 | 19 | 662292 | <$100k | $38M-$40M | Provide QSEs detailed information regarding all submitted settlement disputes. The current method of looking up disputes via the ERCOT Texas Market Link Portal has several limitations, including manually reviewing Dispute ID’s one at a time. | Estimated savings of 8 hours per year for 50 QSEs due to improved dispute tracking
Market | COPS | PRR577 | TDSP Load Extract | New | Market Impact | Candidate to Reprioritize | 1.2 | 2 | 82 | 17 | 67205 | <$100k | $38M-$40M | To receive aggregated TDSP Load data from ERCOT for the purposes of accurately identifying TDSP system peaks required for FERC filings | Possible fines associated with non-compliance = $100k. This number is estimated, and based on the assumption FERC may fine the TDSP for non-compliance considering the TDSP can not produce the data accurately.
Market | WMS | PRR590 | Update Unit Telemetry Requirement | New | Market Impact | Market | 1.2 | 2 | 83 | In progress | In progress | <$100k | $40M-$42M | This revision proposes to add a requirement for QSEs to submit real-time AGC status and Ramp Rate for all online units in their portfolio. This addresses Potomac Economics Recommendation #14.
Market | COPS |  | Extract/Report Enhancements | New | Market Impact | Candidate to Reprioritize | 1.2 | 2 | 84 | 10 | 0 | $100k-$500k | $40M-$42M | To implement enhancements recognized as necessary with implementation of web services (SCR740). Estimate: 4 small changes at $50k each; 1 large change at $300k | Changes will only be considered if they have a positive net benefit
ERCOT | SO |  | SO-SIR Enhancements | New | ERCOT Operations | SIR | 1.2 | 3 | 85 | 14 | -140237 | $100k-$500k | $40M-$42M | To implement SO-SIR enhancements using internal ERCOT resources - inlcudes EMMS/EDW/Portal | Dependent on nature of SIR enhancements
ERCOT | MO |  | SIR Enhancement Projects - 3 Releases | New | ERCOT Operations | SIR | 1.2 | 3 | 86 | 15 | -210000 | $100k-$500k | $40M-$42M | To resolve System Investigation Requests to continue to improve system performance and remove manual workarounds that currently exist in the ERCOT Production environment. | Dependent on nature of SIR enhancements
ERCOT | RO |  | SIR enhancements | New | ERCOT Operations | SIR | 1.2 | 3 | 87 |  | 0 | $500k-$1M | $40M-$42M | To implement RO-SIR enhancements using internal ERCOT resources | Dependent on nature of SIR enhancements
ERCOT | CO |  | Continuous Monitoring Software | New | Security / Audit | Security | 1.2 | 3 | 88 | 15 | -194924 | $100k-$500k | $40M-$42M | Provide automated capabilities to review and interrogate data from ERCOT's key business systems to help ensure there are no fraudulent transactions being processed throughout the organization. | Intangible benefit: Provide improved assurance that fraud is not being perpetrated throughout the organization
ERCOT | SO |  | Automate AS Qualification Testing | 30073 | ERCOT Operations | Process Improve. | 1.2 | 3 | 89 | 16 | 128370 | $100k-$500k | $40M-$42M | Add automation to the existing process of providing Ancillary Service Qualification testing. | Internal ERCOT benefit: Savings of 5 hours per workday of manual Ancillary Services qualification testing
ERCOT | MO |  | REC Program Modifications | New | Infrastructure | Software Upgrade | 1.2 | 3 | 90 | 19 | -389860 | $100k-$500k | $42M-$44M | The REC program has been in operation for almost 4 years, and the technology roadmap has deviated from Microsoft tools. Currently, the REC program is written in ASP. In order to efficiently continue support of this application, it will need to be ported to Java in line with ERCOT's technology roadmap. | Enhance ability to make changes and enhancements to the REC program software; better align with long-term IT strategic direction.
ERCOT | RO |  | Web services that integrate L* and Siebel data for MPs | New | Market Impact | Process Improve. | 1.2 | 3 | 91 | 16 | 12039169 | $100k-$500k | $42M-$44M |  | Market benefit: fewer D2D and DEV FasTrak issues (8 hours per workday for 25 CRs)
ERCOT | CO |  | Enterprise Document Management | New | Security / Audit | Process Improve. | 1.2 | 3 | 92 | 15 | 5684673 | $100k-$500k | $42M-$44M | Provide a document management system to be used across the enterprise for policies, procedures, department documentation, etc. | Internal ERCOT benefit: 10 min. time savings per employee per workday
ERCOT | MO |  | Lodestar Web Services | New | Market Impact | EDW | 1.2 | 3 | 93 | 20 | 1604295 | $100k-$500k | $42M-$44M |  | Market benefit: Create efficiencies in information retrieval (0.5 hours per workday savings for QSEs, CRs and Resources)
ERCOT | RO |  | Enhancements to Retail Test Website | New | Market Impact | Process Improve. | 1.2 | 3 | 94 | 12 | 499742 | $100k-$500k | $42M-$44M | This project will provide increased efficiency and agility to the testing of Retail Market Participants. It also provides additional reporting and produces existing reporting in a more expeditious manner. | Market benefit: For each day that is reduced in the length of a market test flight, each MP could reduce their expenditure no the flight by 1/2 FTE for that day
ERCOT | CO |  | NERC Tracking Database | New | Compliance | Compliance | 1.2 | 3 | 95 | 21 | -44482 | <$100k | $42M-$44M | Track NERC recommendations, Compliance audit issues, mitigation plans, investigations and correspondence to market participants.
ERCOT | SO |  | Security Constrained Power Flow for Feasible Generation for Outage Evaluation | 50048 | ERCOT Operations | Process Improve. | 1.2 | 3 | 96 | 16 | 157285 | $100k-$500k | $42M-$44M | This project will provide the capability for the outage coordinator to simultaneously study multiple planned generation outages over a time range taking into account all defined contingencies and feasible generation patterns. The intent of this project is to automate the process of determining a feasible generation solution that would meet the system load demand and keep the flows on the transmission elements within their thermal limit, as part of the Outage Evaluation process. | Reduced manual effort in Outage Coordination (12.5 hours per workday)
ERCOT | RO |  | Commercial Apps - calendar consolidation | New | ERCOT Operations | Process Improve. | 1.2 | 3 | 97 | 23 | 32821 | $100k-$500k | $44M-$46M | Develop single business calendar for use by all retail applications | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs)
ERCOT | CO |  | Business Function Automation/MSPS Time Mgt Integration | New | Security / Audit | Process Improve. | 1.2 | 3 | 98 | 8 | 6648962 | $500k-$1M | $44M-$46M | Automate key business functions with a business process management tool. | ERCOT benefit: 10 minutes of time savings per ERCOT employee per day
ERCOT | IO |  | Tools and Strategy for Information Lifecycle Management | New | ERCOT Operations | Process Improve. | 1.2 | 3 | 99 | 19 | 2763458 | $1M-$3M | $46M-$48M | Develop strategy for Information lifecycle management to manage data in production databases.
ERCOT | SO | PRR428 | RMR Process Automation | 40087 | Market Impact | Process Improve. | 1.2 | 3 | 100 | 19 | 2699772 | $500k-$1M | $46M-$48M | The proposed functionality will automate the Availability/Delivery plan interaction between ERCOT and QSE and provide an interface to run the reliability study that uses the RPRS Market Clearing engine. The requriements were already gathered during Release 4 planning. External effort is for any AREVA work.
ERCOT | CO |  | Generator Database Automation | 50038 | ERCOT Operations | Compliance | 1.2 | 3 | 101 | 21 | -31568 | <$100k | $46M-$48M | ERCOT currently does not have an organization-wide generator database. By maintaining a single repository of generator information, there will be fewer errors due to out-of-date information.
ERCOT | IO |  | Network Analysis | New | Infrastructure | Infrastructure | 1.2 | 3 | 102 | 24 | -241464 | $100k-$500k | $46M-$48M | The Network Group requires the capability to analyze and troubleshoot problems in depth and in real-time. This tool will give the Network Group the facility by which to accomplish this.
ERCOT | SO |  | Voltage Scheduler | 40091 | ERCOT Operations | Candidate to Reprioritize | 1.2 | 3 | 103 | 11 | -313377 | $100k-$500k | $46M-$48M | It is expected some of the framework developed for Security Constrained Power flow tool will be used in this project. A tool is required to compute the set point voltages for all generators in the ERCOT grid such that the post contingency voltages at the transmission buses are greater than 0.95 per unit. Calculating the generator voltage points would vastly help guard the transmission grid against voltage problems and improve the system efficiency for transferring power from one region to another region.
ERCOT | IO |  | Exchange 2003 Implementation | New | Infrastructure | Software Upgrade | 1.2 | 3 | 104 | 22 | 29345 | $100k-$500k | $46M-$48M | Upgrade Email system to latest version and avoid sunsetting and need for emergency migration later. Exchange 2003 is also necessary for upgrading new software products with a dependancy on Exchange.
ERCOT | SO |  | SPS Modeling Enhancements | 50035 | ERCOT Operations | Process Improve. | 1.2 | 3 | 105 | 11 | -124791 | $100k-$500k | $48M-$50M | The objective for this project is to implement the deferred requirements from Release 4
ERCOT | IO |  | System Dev Lifecycle | 50075 | ERCOT Operations | Process Improve. | 1.2 | 3 | 106 |  | 0 |  | $48M-$50M
ERCOT | SO |  | Performance Monitoring for ERCOT, TDSP, & QSE | 40085 | Compliance | Compliance | 1.2 | 3 | 107 | 20 | -593125 | $500k-$1M | $48M-$50M | Merge eight performance reports into one project • (ER-50067) Load Forecast Performance Report • (ER-30104) STLF and BES Offset Reports • (ER-30025) Monitor A/S Performance & Frequency Control Algorithms • (ER-30111) Balancing Energy AS Provider Performance Report • (ER-30086) Frequency Performance Metric Report • (ER-40077) Graphs for Monitoring Frequency Performance • (ER-50072) Near Miss Indicator for Capacity & Energy Emergency • (ER-50073) OOME & VDI Performance Reports
ERCOT | IO |  | IT Systems Map | New | Infrastructure | Process Improve. | 1.2 | 3 | 108 | 19 | 1269302 | <$100k | $48M-$50M | Create a map of the ERCOT DC environment including all servers in all environments, node to node, applications, Ips, System Model, RAM, Processor, HBA, FA Path and all other important information. Some of this effort may be completed in the Austin iTest project.
ERCOT | SO |  | Governor Analysis Enhancements | 50071 | Compliance | Process Improve. | 1.2 | 3 | 109 | 21 | -77675 | <$100k | $48M-$50M
ERCOT | IO |  | Network Response | New | Infrastructure | Process Improve. | 1.2 | 3 | 110 | 27 | -120323 | $100k-$500k | $48M-$50M | Reduce the amount of time required to disable infected hosts on the ERCOT Corporate network.
Market | RMS | SCR737 | Estimated Meter Read Data | 50091 | Market Impact | Market | 1.3 | 2 | 111 | 7 | 450952 | $100-$500k | $48M-$50M | Create a calendar month, summary report to be presented at RMS that will provide Market Participants with estimated meter reading information broken-down by TDSP territory and indicating customer class. This report will also indicate the degree to which meter reads occur consecutively across two or more months and the degree to which estimates may straddle Move-Ins and Move-In/Forced Outs.
ERCOT | CO |  | TCC Physical Security Enhancements | 50107 | Security / Audit | Infrastructure | 1.3 | 3 | 112 | 24 | -162355 | $100k-$500k | $48M-$50M | To enhance the physical security of the TCC and the blue building.
ERCOT | IO |  | Nortel PBX Upgrade | New | Infrastructure | Infrastructure | 1.3 | 3 | 113 | 19 | -227002 | $100k-$500k | $48M-$50M | Position ERCOT's PBX systems to be in compliance with current software and firmware requirements. This will also allow future performance enhancements to be implemented when necessary as well as enabling ERCOT to test and implement VOIP.
ERCOT | RO |  | 867 inbound map rewrite | New | Market Impact | Process Improve. | 1.3 | 3 | 114 | 11 | 215743 | $100k-$500k | $48M-$50M | Re-Write of Inbound 867 maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing
ERCOT | SO |  | Outage Sensitive Factor Screening Technique | 30056 | ERCOT Operations | Process Improve. | 1.3 | 3 | 115 | 14 | 93757 | $100k-$500k | $48M-$50M | To reduce the computational time in the calculation of the OSF tool to less than 5 minutes; thereby increasing efficiency and productivity within Outage Coordination.
ERCOT | CO |  | Budgeting Tool | 40029 | ERCOT Operations | Process Improve. | 1.3 | 3 | 116 | 16 | 162056 | <$100k | $48M-$50M | Evaluate, select, and implement an automated budgeting tool that offers interconnectivity to the Lawson Accounting system.
ERCOT | RO |  | 814 inbound XML rewrite | New | Market Impact | Process Improve. | 1.3 | 3 | 117 | 17 | 314843 | $100k-$500k | $50M-$52M | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing.
ERCOT | SO |  | Entity Name Change in ERCOT Applications | 50056 | ERCOT Operations | Process Improve. | 1.3 | 3 | 118 | 11 | -836494 | $500k-$1M | $50M-$52M | This project will identify the applications in ERCOT that use the entity’s name and modify those applications to allow for the future name changes without system or data impact.
ERCOT | IO |  | WAN Equipment Upgrade | New | Infrastructure | Infrastructure | 1.3 | 3 | 119 | 9 | -495666 | $100k-$500k | $50M-$52M | Upgrade WAN equipment to improve ERCOT's analysis of the WAN connectivity. This will also enhance tracking and reporting of ERCOT's WAN and the utilization of various IP protocols.
ERCOT | CO |  | Benefits Data Transmission | New | ERCOT Operations | Process Improve. | 1.3 | 3 | 120 | 12 | -62055 | <$100k | $50M-$52M | ERCOT currently submits data to our benefits provider manually by extracting the data from Lawson to an Excel spreadsheet and emailing the data. Lawson support edi transmission of data. This would completely automate the process eliminating any potential human error or intentional data manipulation.
ERCOT | RO |  | Enhancements to ERCOT.com (enhancements not included in PR-40106) | New | Market Impact | Enhance-ment | 1.3 | 3 | 121 | 18 | 950476 | $100k-$500k | $50M-$52M
ERCOT | SO |  | Automatic Generation of One-line Diagrams | 30171 | ERCOT Operations | Process Improve. | 1.3 | 3 | 122 | 10 | -239382 | $500k-$1M | $52M-$54M | Automate the generation and verification of one-line diagrams to eliminate human error during one-line display building activities.
ERCOT | IO |  | Switch Consolidation | New | Infrastructure | Infrastructure | 1.3 | 3 | 123 | 24 | -347514 | $100k-$500k | $52M-$54M | The Network Group currently maintains several hubs and switches that can be consolidated in to a single chassis switch. Provisioning will call for two in Austin and two in Taylor. Most of these devices are obsolete and end-of-life.
ERCOT | SO |  | Line Naming Convention | 40080 | ERCOT Operations | Process Improve. | 1.3 | 3 | 124 | 11 | -80682 | $100k-$500k | $52M-$54M | Establish standard naming convention for naming transmission lines throughout ERCOT (ERCOT and TDSP).
ERCOT | CO |  | Security Camera Enhancements | 50106 | Security / Audit | Security | 1.3 | 3 | 125 | 26 | -234135 | $100k-$500k | $52M-$54M | To enhance visibility of the Austin/Taylor data centers, the EMMS test lab, and the Blue building.
ERCOT | SO |  | Satellite Communications for Black Start suppliers | 50050 | Market Impact | Initiating in 2005 | 1.3 | 3 | 126 | 19 | -85403 | 0 | $52M-$54M | Provide backup communications via Satellite Phone between ERCOT Operations and TSPs for the purpose of coordinating Black Start procedures. Protocols require backup communications for the purpose of Black Start coordination. | Operational readiness for potential black start event
ERCOT | IO |  | Alcatel MDR8000 SNMP Upgrade | New | Infrastructure | Infrastructure | 1.3 | 3 | 127 | 16 | -55022 | <$100k | $52M-$54M | This will enable Network access to the 8000 rather than modem dial-up and also enable SNMP alarm reporting of the 8000 radio to the HP OV system.
ERCOT | SO |  | Remodel Control Room Console Configuration | 50051 | ERCOT Operations | Facilities | 1.3 | 3 | 128 | 12 | -764944 | $500k-$1M | $52M-$54M | The objectives of this project are to improve operator efficiency and eliminate ergonomic concerns by redesigning the console footprint. The improved design should minimize side-to-side movement currently required to view all of the computer monitors an operator must use to perform his/her duty. This project would provide for 8 operator positions in each control room.
ERCOT | IO |  | VM Development Implementation | New | Infrastructure | Infrastructure | 1.3 | 3 | 129 | 9 | 104708 | $100k-$500k | $52M-$54M | Move as many Development systems to VMs as possible - Elimination of hardware, licensing, heat, power and etc.
ERCOT | SO |  | ICCP Security Enhancements | New | ERCOT Operations | Security | 1.3 | 3 | 130 | 16 | -146594 | $100k-$500k | $52M-$54M | Provide the Market Participants with capability to encrypt and authenticate data transfer using Inter Control Center Protocol (ICCP)
Market | RMS |  | Texas Set 2.2 | New | Market Impact | Market | 2.1 | 2 | 131 | 15 | 3862239 | $500k-$1M | $54M-$56M | This is a place holder for new TxSet version 2.2 for 2006
Market | WMS | PRR409 | Voltage Support Service | 30032 | Market Impact | Market | 2.1 | 2 | 132 | 14 | -1099000 | $1M-$3M | $54M-$56M | The current Protocols allow for excessive reactive dispatching on the part of TSPs without compensation to generation owners. This PRR changes the power factor envelope from +-.95 to +-.98, and allows for payment to generators.
ERCOT | RO |  | Web based ERCOT 101 training | New | Market Impact | Process Improve. | 2.1 | 3 | 133 |  | 0 | $500k-$1M | $56M-$58M
ERCOT | MO |  | Uninstructed Deviation Calc for Uncontrollable Renewable Resource | 50015 | Market Impact | Process Improve. | 2.1 | 3 | 134 | 15 | 38178 | <$100k | $56M-$58M | The Settlement system shall automate receiving and calculating URC charges based on imported RPP data cuts. Also, OOME down shall be calculated using RPP data in lieu of Resource Plan data for units opt for RPP. This project will automate the manual processes currently performed by ERCOT Settlements team (Option A on the Impact Analysis)
ERCOT | SO |  | Outage Coordination Statistical Reports | 50093 | Compliance | Compliance | 2.1 | 3 | 135 | 20 | -98719 | $100k-$500k | $56M-$58M | Develop reports indicating outage statistics focused on Compliance monitoring needs.
ERCOT | CO |  | Integrated MW Telemetry Validation Against EPS Meter Readings | 50098 | Compliance | Compliance | 2.1 | 3 | 136 | 20 | -75332 | <$100k | $56M-$58M | Improve the validity and accuracy of real-time data used for state estimation, studies and other operational and market needs.
ERCOT | IO |  | System Engineering Metrics | 50077 | Infrastructure | Infrastructure | 2.1 | 3 | 137 | 14 | -131183 | $500k-$1M | $56M-$58M | Ensure delivery of key service metrics, ensure growth and capital efforts are adequately forecasted, and stimulate continuous improvement for data center capacity management.
ERCOT | RO |  | L* Retail POC (Proof of Concept) | New | ERCOT Operations | Process Improve. | 2.1 | 3 | 138 | 15 | -602009 | $500k-$1M | $56M-$58M
ERCOT | CO |  | Voltage/Reactive Compliance Management Database | 50055 | Compliance | Compliance | 2.1 | 3 | 139 | 21 | -112639 | $100k-$500k | $56M-$58M | Collect information necessary to enforce Protocol 6.10.9 Reactive Power Supply from Generation Resources Required to Provide VSS Performance Criteria.
ERCOT | RO |  | MP Automation of Manual Cancels | New | Market Impact | Process Improve. | 2.1 | 3 | 140 |  | 0 | <$100k | $56M-$58M
ERCOT | IO |  | TCC Modular Storage/Additional Office Space | New | Infrastructure | Facilities | 2.1 | 3 | 141 | 22 | -708911 | $500k-$1M | $58M-$60M | When TCC2 is completed, ERCOT will not have any storage space available on-site for critical computer equipment. A modular storage/office building will give ERCOT additional office space if needed and an on-site, secure environmentally controlled storage area for equipment.
ERCOT | CO |  | SIR Tool Replacement | New | ERCOT Operations | SIR | 2.1 | 3 | 142 | 12 | 26303 | <$100k | $58M-$60M | Consolidate the SIR tool with the Service Desk tool that is used for helpdesk and OCC processing.
ERCOT | RO |  | Siebel GUI-Based Data Validation Improvements | New | ERCOT Operations | Process Improve. | 2.1 | 3 | 143 |  | 0 | <$100k | $58M-$60M
ERCOT | IO |  | Console Operations Area | New | Infrastructure | Facilities | 2.1 | 3 | 144 | 25 | -443271 | $1M-$3M | $60M-$62M | Provide a permanent and suitable location for Console Operations. The build-out will provide a 1500 sq.ft. location in the hardened area of TCC adjoining the Data Center. The objective is to design and construct a work area with the proper communcation infrastructure and audio visual capabilities needed for this environment.
ERCOT | CO |  | Project Portfolio Management System | New | ERCOT Operations | Process Improve. | 2.1 | 3 | 145 | 13 | -644026 | $500k-$1M | $60M-$62M | Provide additional portfolio analysis features to existing project scheduling tool that allows for tracking and reporting on project portfolio health, performance, budgets, costs and issues.
ERCOT | RO |  | Name to DUNS conversion | New | ERCOT Operations | Process Improve. | 2.1 | 3 | 146 | 14 | -25320 | $100k-$500k | $60M-$62M | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names.
ERCOT | CO |  | Unit Testing - Electronic Submittal via Web | 50070 | Compliance | Compliance | 2.1 | 3 | 147 | 21 | -369884 | $100k-$500k | $60M-$62M | By automating the test submittal process, human error is minimized while the speed of which the ERCOT EMMS is updated is greatly improved. QSEs can be held more accountable for their data submittal. An organization-wide database will also improve Planning modeling accuracy by providing the ability to use actual data rather than the current process of using nameplate data.
ERCOT | RO |  | MP configuration Table | New | ERCOT Operations | Process Improve. | 2.1 | 3 | 148 | 18 | -3351 | $100k-$500k | $60M-$62M | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information.
ERCOT | RO |  | Publish / subscribe self services / communications | New | Market Impact | Process Improve. | 2.1 | 3 | 149 |  | 0 | $500k-$1M | $62M-$64M
Market | WMS | SCR720 | Zone Forecast and Actual Generation | 20126 | Market Impact | Market | 2.2 | 2 | 150 | 17 | -80000 | <$100k | $62M-$64M | ERCOT will provide real-time posting of Forecasted Net Zonal Energy and Actual Zonal Generation as an interim means of making a portion of the QSE data requirements available between now and the time that real-time XML
Market | WMS | SCR728 | Display ERCOT Deployments | 20126 | Market Impact | Market | 2.2 | 2 | 151 | 17 | -80000 | <$100k | $62M-$64M | Display ERCOT total aggregated balancing energy deployment, total aggregated responsive deployment, total aggregated non-spin deployment, ERCOT SCE and ERCOT responsive reserve on the ERCOT public website
Market | RMS |  | Retail Enhancements to TML - Phase 4 | 50058 | Market Impact | Market | 2.2 | 2 | 152 | 16 | -960000 | $500k-$1M | $62M-$64M
ERCOT | SO |  | Enhancement to Market Analyst Interface for Ancillary Service Schedule Monitoring | 40082 | ERCOT Operations | Process Improve. | 2.2 | 3 | 153 | 11 | 16493 | <$100k | $62M-$64M | Create and install a display in the Operations Market Analyst Interface to display all QSE ancillary services resources and obligations based on A/S requirements, A/S schedules entered and A/S awards. This functionality is needed to allow Operations to ascertain which QSEs have changed or are deficient in their A/S schedules.
ERCOT | RO |  | EDI Transaction logging | New | ERCOT Operations | Process Improve. | 2.2 | 3 | 154 | 14 | -99482 | $100k-$500k | $62M-$64M | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs.
ERCOT | CO |  | Compliance Web Page Enhancements | New | ERCOT Operations | Enhance-ment | 2.2 | 3 | 155 | 17 | -55243 | <$100k | $62M-$64M | To be deleted
ERCOT | SO |  | Web Posting for Market Transparency-Rollover | 20126 | Market Impact | Process Improve. | 2.2 | 3 | 156 | 17 | 0 |  | $62M-$64M | To be deleted
ERCOT | CO |  | Metal/Explosives Detectors | 50105 | Security / Audit | Security | 2.2 | 3 | 157 | 18 | -118792 | $100k-$500k | $64M-$66M | To enhance physical security capabilities during times of heightened security alerts/threat levels.
Market | RMS | SCR742 | Automated Retail Transaction Verification | New | Market Impact | Market | 2.3 | 2 | 158 | 13 | 3436738 | $500k-$1M | $64M-$66M | Build interface to existing Market Certification environment This option involves building automation and an integrated user interface to the existing market certification environment.
Market | RMS | SCR734 | CSA Report for CRs | 50057 | Market Impact | Market | 2.3 | 2 | 159 | 8 | 150206 | $100k-$500k | $64M-$66M | Provide CR’s with an on-demand extract capability to retrieve CSA (Continuous Service Agreement) data for their DUNS via the ERCOT Portal
ERCOT | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | New | Market Impact | Enhance-ment | 2.3 | 3 | 160 |  | 0 | $100k-$500k | $64M-$66M
ERCOT | CO |  | Lawson Expense Management | New | ERCOT Operations | Process Improve. | 2.3 | 3 | 161 | 14 | -55641 | <$100k | $64M-$66M | Implement Lawson Expense mangement in order to track expenses online.
ERCOT | RO |  | Unified Member Account Management View | New | ERCOT Operations | Enhance-ment | 2.3 | 3 | 162 |  | 0 | $100k-$500k | $64M-$66M
ERCOT | CO |  | Electronic Turnstyle | 50103 | Security / Audit | Security | 2.3 | 3 | 163 | 15 | -311784 | $100k-$500k | $64M-$66M | To enhance the overall effectiveness of the exisitng security/access control system(s).
Market | WMS | PRR454 | OOME Off-line | 30193 | Market Impact | Market | 3.1 | 2 | 164 | n/a | n/a (3.x priority) | $100k-$500k | $64M-$66M | When a generation unit receives an OOME instruction that would force it off-line, ERCOT must provide OOME instructions until the unit was scheduled to come off-line, or an OOMC instruction when the unit is requested to return.
ERCOT | SO |  | Resource Plan Improvement Phase II (EMMS Release 5) | 50074 | ERCOT Operations | Process Improve. | 3.1 | 3 | 165 | n/a | n/a (3.x priority) | $100k-$500k | >$66M
ERCOT | RO |  | Automate Internal Surveys | New | ERCOT Operations | Process Improve. | 3.1 | 3 | 166 | n/a | n/a (3.x priority) |  | >$66M
ERCOT | CO |  | Resource Plan Metric Automation | 50095 | ERCOT Operations | Compliance | 3.1 | 3 | 167 | 21 | -53360 | <$100k | >$66M | Automate Resource Plan Performance Metrics (scores) generated on a daily, month-to-date, and monthly basis.
ERCOT | IO |  | PowderHorn Tape Library Redundancy | New | Infrastructure | Infrastructure | 3.1 | 3 | 168 | 14 | -191098 | $100k-$500k | >$66M | Provide redundant power for the Tape backup library. | The existing tape library is not power redundant and losses of power to the unit will halt functionality of backup and restore operations.
ERCOT | IO |  | TML Port to Solaris | 50062 | Infrastructure | Infrastructure | 3.1 | 3 | 169 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | Windows and Jrun environment has proven problematic. Jrun will end of life next year (complete product), and Windows for DMZ applications is being decommissioned.
ERCOT | RO |  | Outage notification system & storage facility (centralized) | New | Market Impact | Process Improve. | 3.1 | 3 | 170 | n/a | n/a (3.x priority) |  | >$66M
ERCOT | IO |  | MET Center Remediation | 50082 | Infrastructure | Facilities | 3.1 | 3 | 171 | n/a | n/a (3.x priority) | <$100k | >$66M | To remediate potential drainage problems and reduce/eliminate water migration underneath the foundation of the MET Center facility.
Market | RMS | PRR241 | UFE Analysis | 30022 | Market Impact | Market | 3.2 | 2 | 172 | n/a | n/a (3.x priority) | $1M-$3M | >$66M | 1) Revises the beginning date for UFE analysis in Section 11.5.1 to January 2002. 2) Modifies the language in 11.5.2.1 to accommodate a December 1, 2001 implementation timeline. 3) Adds language in 11.5.2.1 to require TDSPs to leave "old control area" boundary meters in place until UFE analysis zones are defined. Definition of zones to take place after June 1, 2001 but supporting December 1, 2001 deadline.
Market | RMS | SCR736 | TML ESIID TXN Portal Flag | 50100 | Market Impact | Market | 3.2 | 2 | 173 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | Append a data Flag of “P” to the Transaction Type number to indicate when a displayed transaction was generated and transmitted through the Texas Market Link portal by Market Participants, rather than being generated by Market Participant’s system and transmitted in the Market via GISB.
Market | COPS |  | TCR Synchronization of Credit Payment with Settlement Invoices | 30103 | Market Impact | Market | 3.3 | 2 | 174 | n/a | n/a (3.x priority) | $100k-$500k | >$66M
Market | RMS | PRR385 | DLC Implementation |  | Market Impact | Market | 3.3 | 2 | 175 | n/a | n/a (3.x priority) |  | >$66M | This PRR will allow the DLC programs to be appropriately profiled and ERCOT systems to properly process DLC programs.
Market | RMS | PRR478 | Use of Lagged Dynamic Samples for New Load Profiles | 40056 | Market Impact | Market | 3.3 | 2 | 176 | n/a | n/a (3.x priority) | $500k-$1M | >$66M | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open.
Market | WMS | PIP112 | DLC for BULs | 50108 | Market Impact | Market | 3.3 | 2 | 177 | n/a | n/a (3.x priority) | $1M-$3M | >$66M
Market | WMS | PRR311 | DLC to BUL Transition | 50108 | Market Impact | Market | 3.3 | 2 | 178 | n/a | n/a (3.x priority) | Included with PR50108 | >$66M | Permits load control or load management programs involving small energy consumers (under 1 MW) to provide a balancing-up load (BUL) without the requirement that interval data recorders (IDRs) be installed on all of the participating
Market | WMS | PRR484 | Changes for Implementation of Direct Load Control (DLC) | 50108 | Market Impact | Market | 3.3 | 2 | 179 | n/a | n/a (3.x priority) | Included with PR50108 | >$66M | The requested changes will facilitate and specify how DLC programs participate in the BUL market.
Market | WMS | PIP128 | Synchronous Condenser Compensation | 30034 | Market Impact | Market | 3.3 | 2 | 180 | n/a | n/a (3.x priority) | $100k-$500k | >$66M
Market | WMS | PIP210 | Block Bidding for Reserve Services - Related to PRR496 | 50046 | Market Impact | Market | 3.3 | 2 | 181 | n/a | n/a (3.x priority) | <$100k | >$66M
Market | WMS | PRR307 | Controllable Resources | 30039 | Market Impact | Market | 3.3 | 2 | 182 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | This revision defines Load which can provide Regulation Service.
Market | WMS | PRR426 | URC for Uncontrollable Resources | 40057 | Market Impact | Market | 3.3 | 2 | 183 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | Defines an Uncontrollable Renewable Resource and allows wind resource to elect to use their Renewable Production Potential in lieu of their schedule as the basis for URC charges and OOME Down payments.
Market | WMS | PRR355 | BLT OOME | 30132 | Market Impact | Market | 3.3 | 2 | 184 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | Allows availability of Block Load Transfers for OOME deployment
Market | WMS | SCR729 | Unit Status Information | 20126 | Market Impact | Market | 3.3 | 2 | 185 | n/a | n/a (3.x priority) | <$100k | >$66M | Modify the ERCOT market clearing engine to allocate RRS to hydro units operating in synchronous condenser mode
Market | WMS |  | TGR (Trading piece) | 50110 | Market Impact | Market | 3.3 | 2 | 186 | n/a | n/a (3.x priority) | $100k-$500k | >$66M
Market | WMS | SCR735 | Include Hydro Units in Synchronous Condenser Mode in SPD RRS Allocation | 50120 | Market Impact | Market | 3.3 | 2 | 187 | n/a | n/a (3.x priority) | <$100k | >$66M
Market | WMS | PRR496 | Block Bidding and Deployment of LaaRs providing Responsive Reserve Service and Non-Spinning Reserve Service | 50046 | Market Impact | Market | 3.3 | 2 | 188 | n/a | n/a (3.x priority) | <$100k | >$66M | Include provisions for LaaRs to have the option to bid Responsive Reserve Service and Non-Spinning Reserve Service as a block.
Market | WMS | PRR436 | Enhance LaaR/BUL Ability to Participate in Balancing Energy Up Service, Non-Spinning Reserve Service, and Responsive Reserve Service Markets | 30191 | Market Impact | Market | 3.3 | 2 | 189 | n/a | n/a (3.x priority) | <$100k | >$66M | This PRR would include the changes proposed by the Demand Side Working Group to clarify the role of Loads in the Ancillary Service and BUL markets.
ERCOT | SO |  | Include Hydro Units in Synchronous Condenser Mode in SPD RRS Allocation | 50120 | Market Impact | Market | 3.3 | 3 | 190 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | The ERCOT market clearing engine, which performs Resource Plan Validation and the Hour-Ahead Study, and clears the Real Time Balancing Energy Market, should be modified to allocate Responsive Reserve Service according to the ERCOT Operating Guides to hydro units operating in synchronous condenser mode.
ERCOT | RO |  | Market Meeting Electronic Voting | New | Market Impact | Process Improve. | 3.3 | 3 | 191 | n/a | n/a (3.x priority) |  | >$66M
ERCOT | CO |  | Lawson eRecruiting | New | ERCOT Operations | Process Improve. | 3.3 | 3 | 192 |  | -115862 | $100k-$500k | >$66M | Implement Lawson eRecruiting module. ERCOT owns the license to support this functionality.
ERCOT | SO |  | For Responsive Reserve & Non-Spinning Reserve Services; Block Deployment (for Responsive & Non-Spin) | 50046 | Market Impact | Market | 3.3 | 3 | 193 | n/a | n/a (3.x priority) | $100k-$500k | >$66M | Market change proposed in PRR496 to allow Block-bidding of Loads Acting as Resource for Responsive and Non-Spin services. This will require an Areva project to change the logic of the Ancillary Service procurement process to select (or skip) a block of offered services for LaaRs (up to 150MW blocks). The effort included is for adding block procurement for LAAR in AS market clearing engine - changing the problem formulation and using mixed integer programming (MIP) for solving. Per AREVA, the AIMMS licensing already includes the MIP solver.
ERCOT | RO |  | Administration of Enrollment notifications | New | Market Impact | Process Improve. | 3.3 | 3 | 194 | n/a | n/a (3.x priority) |  | >$66M
Market | WMS | PRR598 | Charge Against OOM Start Up (FKA Extension of Credit Against OOM Start Up) | New | Market Impact | Market | 1.1 | 2 | 32.3 |  |  | <$100k
Market | WMS | PRR599 | Notification for Mismatched Inter-QSE Energy Schedules | New | Market Impact | Market | 1.2 | 2 | 34.4 |  |  | <$100k
Market | WMS | PRR601 | 15 Minute Ramping for BES and Base Power Schedule | New | Market Impact | Market | 1.2 | 2 | 79.5 |  |  | $100k-$500k
Market | WMS | PRR614 | Balancing Bids for Replacement Capacity | New | Market Impact | Market | 1.1 | 2 | 32.6 |  |  | <$100k
Market | ROS | SCR744 | Outage Scheduler View Only Access | New | Market Impact | Market | 1.1 | 2 | 38 |  |  | $100k-$500k
Market | RMS | PRR565 | Calculation of Losses for Settlement | New | Market Impact | Market | 3.1 | 2 |  |  |  | <$100k

## Summaries
Project Count by Priority and Source |  |  |  |  | Total Project Cost by Priority and Impact Area
Count of Project | Source |  |  |  | Sum of 2006 Cost | Impact Area
Priority | ERCOT | Market | PUCT | Grand Total | Priority | Compliance | ERCOT Operations | Infrastructure | Market Impact | Market Monitoring | Security / Audit | Grand Total
1.0 | 15 | 4 | 2 | 21 | 1.0 | 4007677 | 95985 | 251591.4 | 1849696 | 337228 | 0 | 6542177.4
1.1 | 47 | 4 | 7 | 58 | 1.1 |  | 4960241.25 | 10753004.5 | 10324775.5 | 3742439.25 | 1089464.65 | 30869925.15
1.2 | 26 | 5 |  | 31 | 1.2 | 764478 | 3866469.75 | 1227411 | 4784665.75 |  | 1020024.9 | 11663049.4
1.3 | 19 | 1 |  | 20 | 1.3 |  | 2809901.6 | 1037745 | 659535 |  | 371223 | 4878404.6
2.1 | 17 | 2 |  | 19 | 2.1 | 602444.25 | 1997950.5 | 2843640 | 3203725 |  |  | 8647759.75
2.2 | 5 | 3 |  | 8 | 2.2 |  | 283227.75 |  | 1040000 |  | 104139 | 1427366.75
2.3 | 4 | 2 |  | 6 | 2.3 |  | 209583.9 |  | 1302700 |  | 301806 | 1814089.9
3.1 | 7 | 1 |  | 8 | 3.1 |  | 434214 | 382772.25 | 0 |  |  | 816986.25
3.2 |  | 2 |  | 2 | 3.2 |  |  |  | 0 |  |  | 0
3.3 | 5 | 16 |  | 21 | 3.3 |  | 107751.6 |  | 505359 |  |  | 613110.6
Unranked |  | 1 |  | 1 |  |  |  |  | 0 |  |  | 0
Grand Total | 145 | 41 | 9 | 195 | Grand Total | 5374599.25 | 14765325.35 | 16496164.15 | 23670456.25 | 4079667.25 | 2886657.55 | 67272869.8
Project Cost by Priority and Source
Sum of 2006 Cost | Source
Priority | ERCOT | Market | PUCT | Grand Total
1.0 | 4860236.4 | 1425713 | 256228 | 6542177.4
1.1 | 23980919.9 | 4297225 | 2591780.25 | 30869925.15
1.2 | 8533049.4 | 3130000 |  | 11663049.4
1.3 | 4728404.6 | 150000 |  | 4878404.6
2.1 | 6897759.75 | 1750000 |  | 8647759.75
2.2 | 387366.75 | 1040000 |  | 1427366.75
2.3 | 964089.9 | 850000 |  | 1814089.9
3.1 | 816986.25 | 0 |  | 816986.25
3.2 |  | 0 |  | 0
3.3 | 613110.6 | 0 |  | 613110.6
Unranked |  | 0 |  | 0
Grand Total | 51781923.55 | 12642938 | 2848008.25 | 67272869.8