## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of July 8, 2005
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb 2005
Planning – March 14, 2005
Execution – August 2005
Implementation – January/February ‘06
Closing – February ‘06
Recent:
Facilitated Webex demonstrations from three vendors from June 13th - 22nd
Narrowed the list to two vendors: Siebel and Serena Software
Presented project update to TTPT
Facilitated proof of concept July 5th – 8th and July 12th – 15th
Next steps:
Finalize product selection (July 19th)
Finalize conceptual design
Finalize detailed design
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of July 8, 2005
Page 2

## Slide 3
Product selection taking longer than originally planned
  After product selection is complete, the project schedule will be re-evaluated. The revised schedule will be published at the next RMS meeting.
Project Issues/Risks
PR-50007 Enhancements to FasTrak
As of July 8, 2005
Page 3

## Slide 4
** All target dates will become firm after design is complete and project plan finalized
Requirements – June ’05
Design (published document) – August ’05
Internal Testing – December ’05 – January ’06
External Testing – December ’05 – January ‘06
Internal Training – January ‘06
External Training – January ‘06
Production (Go live) – January/February ‘06
High level timeline
PR-50007 Enhancements to FasTrak
As of July 8, 2005
Page 4

## Slide 5
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of July 8, 2005
Page 5