## Slide 1
Objectives:
Define and implement a website layout that enables users to find key information efficiently
Develop a process to ensure the sustainability of the investment in the enhancements
Scope/Why is this important?:
Search engine functionality (including metadata strategy)
Improve navigation - create a new information architecture for the site (task driven focus)
Content owners can post updates easily – content manager
Process for maximizing the use of key real estate for critical and timely information
All information and processes are maintained after the redesign
Dependencies:
None at this time
Project Objectives / Scope / Dependencies
PR-40106 ERCOT.com
As of July 8, 2005
Page 1

## Slide 2
Phase:
Initiation – completed in Sept ‘04
Planning – completed in June ‘05
Execution – Started on June 13, 2005
Closing – goal December ‘05
Recent:
Purchased and implemented Serena’s CMS product
Received training on Serena’s CMS product
Began work on re-designing ERCOT’s public website and migrating documents using the CMS tool
Next steps:
Purchase and install Google Search Appliance
Continue work on re-designing ERCOT’s public website
Continue work on migrating documents to ERCOT’s re-designed site by using Serena’s CMS product.
Schedule meeting with MPs to illustrate project progress
Summary of Project Status
PR-40106 ERCOT.com
As of July 8, 2005
Page 2

## Slide 3
** All target dates – will have firm dates after project plan is completed
Requirements (pens down) – June ‘05
Design (published document) – June/July ’05
ERCOT Testing – October ’05
Market Testing – October ‘05
Training – October/November ’05
Production (Go live) – November ‘05
High level timeline
PR-40106 ERCOT.com
As of July 8, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 24 Program Area: RO
What prompted the project:
  Market Survey
  TML Phase II Mid-Term Requirements
  Strategic Fit
Supporting business drivers:
  Data from the Market Survey strongly encouraged the implementation of a search engine
  Peer website comparisons between the other ISOs
  Practical usage feedback
Additional Information
PR-40106 ERCOT.com
As of July 8, 2005
Page 4