## Slide 1: Project Updates to DEWG
Jackie Ashbaugh
ERCOT
July 14, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Project Updates
PR 50007 - FasTrak
PR 40106 - ERCOT.com (given by S. Egger)
PR 50024 - Enhancements to SCR 727 (SCR 740 Web Service for ESIID data)
PR 40007 - SCR727 move from Data Archive to ODS
PR 30026 - EPS Meter Data Extract/Resource ID Extract
PR 40042_06 - Lodestar Batch Extracts
2005 Upcoming Projects
TBD
Necessary Project Updates?
TBD
Projects
ERCOT Project Updates
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
PR-50007 Enhancements to FasTrak
  Planning Phase
  Implementation scheduled for 1st Qtr. 2006 – Market Decision for delivery
  Facilitated Webex demonstrations from three vendors from June 13th - 22nd
  Narrowed the list to two vendors: Siebel and Serena Software
  Presented project update to TTPT
  Facilitated proof of concept July 5th – 8th and July 12th – 15th
  Product selection taking longer than originally planned
    After product selection is complete, the project schedule will be re-evaluated. The revised schedule will be published at the next RMS meeting.
  Next Steps:
    Finalize product selection (July 19th)
    Finalize conceptual design
    Finalize detailed design
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
PR-50024 Enhancements to SCR 727
  Execution phase
  Building design for phase 1 (Business Intelligence)
  Drafting analytical design for phase 2 (Services – architecture)
  Implementation date: 02/2006
  Next Steps:
    Build for phase 1 & 2
    Begin developing test scenarios
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
Internal ERCOT Projects to move Lodestar Extracts to ODS
  Extracts included:
    SCR 727 ESIID Extract
    EPS Meter Data Extract aka Resource ID Extract
    Load Extract
    Generation Extract
    Settlements & Billing Extract
    Settlement Input Data Extract
    Public Reference Data Extract
    Shadow Pricing Extract
  Goal is to implement all Lodestar Extracts out of the ODS environment by the end of 2005
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Updated Lodestar Extracts Timeline
  Same impact to dispute timeline as the current extract timeline
  Improved impact to dispute timeline for trade dates with backouts/reruns
  Repeatable process
  Daily extracts posted everyday
  Compliant with existing protocols
  Extracts include complete, approved trade date data that correspond to Settlement Statements
  Synchronized postings for SCR 727 and RID extracts to Load, Generation, and Settlements & Billing extracts
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
PR-40007 SCR 727 Phase 2
  SCR 727 ESIID Extract, Public Reference Data Extract
  Execution phase
  Develop a market level data extract called Public Reference Data Extract to include all non-interval market data provided in RID, SCR 727, Load, Generation, and Settlements & Billing Extracts
  Developers are unit testing their design
  Completing development the timing logic for when to run and what timestamp data range to include in each extract – to be implemented to production by 09/01/2005
  Currently, market participants that are MREs, but not the TDSPs of an ESIID receive a separate MRE extract. With the move to the ODS, the MRE and TDSP extracts be merged to provide one extract file per DUNs number. ERCOT received 6 responses from TDSP/MREs in agreement with the proposed change sent to DEWG on 06/29/2005.
  Next Steps:
    Begin PTEST and UAT on SCR 727 logic
    Test timing logic triggers
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
PR-30026 EPS Meter Data Extract/Resource ID Extract
  RID Extract
  Execution phase
  Completing development the timing logic for when to run and what timestamp data range to include in each extract – to be implemented to production by 09/01/2005
  Next Steps:
    Test timing logic triggers
    Prepare code for ITEST
    Complete development of ITEST test plan for technical integration testing and UAT
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
PR-40042_06 Lodestar Batch Extracts
  Load, Generation, Settlements & Billing, Settlement Input Data and Shadow Pricing
  Execution phase
  Business Requirements changes completed 06/2005
    Redefining business requirements to meet the needs of providing complete, approved batch of trade dates on a daily basis
    Incorporate extract timelines into design
  Completed resource management changes
  Development of Initial and daily extracts logic process
  Develop Settlement Input Data Extract
  Completing development the timing logic for when to run and what timestamp data range to include in each extract – to be implemented to production by 09/01/2005
  Next Steps:
    Test timing logic triggers
Notes: <number>
<footer>
<header>
<date/time>