## Slide 1: Residential Survey

## Slide 2: Survey Objectives
Develop a more accurate algorithm to predict the presence and use of electric heat for residential customers.
  Algorithm inputs are premise level historical usage and weather zone
  Algorithm output is probability of having electric heat
Collect data to support analysis to potentially develop new profile types

## Slide 3: Two-Phased Survey Approach
Phase 1: Pilot mail survey to 1,000 customers, equally distributed across all weather zones
  Estimate response rate for phase 2
  Assess response accuracy
Phase 2: Full mail survey
  Go/No-Go decision based on pilot responses
    Evaluate accuracy based on usage history
    Analyze response rate to determine sample size required to achieve statistically significant results
    Ensure the budget supports the required sample size
  Draw sample based on pilot response rate results

## Slide 4: Survey Administration
Reducing Customer Confusion
  Bilingual (English/Spanish) versions
  ERCOT supported 24-hour, bilingual, toll-free telephone number
  ERCOT supported web page containing ERCOT background, survey question details, toll-free telephone number, and “Frequently Asked Questions” (FAQs)
Minimizing Call Center Impacts
  Cover letter will refer customer questions/concerns to toll-free number
  FAQs will be provided to REPs to be used as training materials for the call centers
Improving Response Rate
  Postage-paid return envelope
  ERCOT purchased customer name associated with address information
Correlating ESI-ID to Response
  Bar-coded survey form linking ESI-ID to response

## Slide 5: Survey Update
Completed:
  Approval of Survey at May TAC meeting.
  Bilingual versions of the cover letter and survey.
  ERCOT website posted.
  Procurement activities with the firm to provide names for sampled addresses.
  Procurement activities with selected Market Research firm.
  Survey population (stratified by profile type and weather zone) has been identified and addresses are being validated against databases.
  Code development to validate responses regarding heating type.
  Survey mailed out on June 9, with responses by July 7.

## Slide 6: Survey Response Review

## Slide 7: Survey Response Review
Responses to question #2 (primary heating system)
  85% accurate response to electric vs. gas heat based on multi-year consumption analysis
  Response breakdown:
    57 Electricity
    51 Natural or bottle gas
    1 Invalid
    1 Other or not sure
Zero (0) phone inquiries to contact number provided.
  9.4% overall valid response rate

## Slide 8: Go/No-Go Evaluation Criteria
Evaluate accuracy based on usage history
  85% accurate response to electric vs. gas heat based on multi-year consumption analysis
Analyze response rate to determine sample size required to achieve statistically significant results
  9.4% overall valid response rate
  40,000 surveys to be mailed, equally stratified by profile type and weather zone
  ± 7% accuracy at 95% confidence
Ensure the budget supports the required sample size
  Remaining budget supports additional 40,000 surveys

## Slide 9: Projected Residential Survey Timeline
Conduct Pilot Survey
RSTF/RMS Review
TAC Review
Conduct Full Survey
Responses provided to ERCOT
ERCOT analysis of survey responses
PWG review of analysis
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC

## Slide 10: RMS Recommendation
RMS recommends approval of the full mail residential survey