## Slide 1
TAC Presentation
Nodal Mobilization Issues
Ray Giuliani
August 4, 2005

## Slide 2
The Nodal Timeline Challenge
Project Mobilization 2
Requirements/SOW/Procurement 7
Market Trials 7
Development 15
Transition to Go-Live 1.5
Test 3
Install 2
Integration 5
Critical Path: duration (mos.)
Total 42.5

## Slide 3
The Nodal Timeline Challenge
Project Mobilization 2
Requirements/SOW/Procurement 7
Market Trials 7
Development 15
Transition to Go-Live 1.5
Test 3
Install 2
Integration 5
Critical Path: duration (mos.)
All application work starts at the same time
Total 42.5

## Slide 4
The Nodal Timeline Challenge
Project Mobilization 2
Requirements/SOW/Procurement 7
Market Trials 7
Development 15
Transition to Go-Live 1.5
Test 3
Install 2
Integration 5
Critical Path: duration (mos.)
Aug 1, 2005
Feb 15, 2009
All application work starts at the same time
Total 42.5

## Slide 5
1
5
5
6.5
Lodestar
0.5
3
11
6
CRRs
1
3
15
7
MOS (RT) – LMP
work in progress
MOS (DA) – LMP
1
3
15
7
MOS – SCUC
1
3
12
7
State Estimator
1
3
12
7
Power Flow
1
3
12
7
LGC (AGC)
1
3
12
7
TSAT
1
3
12
7
VSAT
0.5
0.5
11
5.5
Outage Evaluation
Install
Test
Design/ Development
Requirements/ SOW/Procurement
Application
TBD
Credit Monitor
Market Monitor
1
3
12
7
Real Time Contingency Analysis
TBD
The Nodal Timeline Challenge

## Slide 6
The ERCOT Management Challenge
Day Ahead &
CRRs
Outage Evaluation
Real Time &
CRRs
Real Time Contingency Analysis
MOS – SCUC
MOS(RT) - LMP
Lodestar
Lodestar
Credit Monitor
Credit Monitor
Servers
Networks
Tools
Applications
System Operations
Commercial Operations
Finance
Market Monitor
Market Monitor
PUCT Staff
IT Operations
MOS(DA) - LMP
State Estimator
VSAT
TSAT
LGC(AGC)
CRRs
CRRs
Baseline
LGC(AGC)

## Slide 7: ERCOT Management Challenge
  ERCOT needs:
  TAC decision-making body that will provide service level requirements and timely guidance
  Director level implementation leader
  What does TAC need?