July 2005 Report

To

Technical Advisory Committee

Reliability and Operations Subcommittee

Prepared by ERCOT Transmission Services

Transmission Project Summaries (updates coming next month)

Major transmission projects completed (updates coming next month)

| Project Title | Project Description | Transmission Owner | Actual In-Service Date | Service Level kV |
| --- | --- | --- | --- | --- |
| Eagle Mountain 345 kV breakers | Install two 345 kV breakers | TXU Electric Delivery | Apr-05 | 345 |
| Roanoke Switch 345/138 kV autotransformer | Install (2nd) 345/138 kV autotransformer (600 MVA) at Roanoke Switch | TXU Electric Delivery | Mar-05 | 345 |
| Watermill - Tricorner 345 kV line | Upgrade Watermill - Tricorner 345 kV line | TXU Electric Delivery | Feb-05 | 345 |
| Obrien 345/138 kV autotransformer | Added third 345/138 kV, 400MVA autotransformer (A3) @Obrien | CNP | Jan-05 | 345 |

Status of major transmission projects (updates coming next month)

| Project Title | Project Description | Transmission Owner | Projected In-Service Date | Service Level kV | Location County |
| --- | --- | --- | --- | --- | --- |
| Anna 345/138 kV autotransformer | Install a (2nd) 345/138 kV autotransformer (600 MVA) at Anna | TXU Electric Delivery | May-05 | 345 | COLLIN |
| Lake Creek second 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer | TXU Electric Delivery | May-05 | 345 | MCLENNAN |
| Martin Lake 345 kV breakers | Install two 345 kV bus tie breakers | TXU Electric Delivery | May-05 | 345 | RUSK |
| Monticello 345 kV breaker | Install one 345 kV bus tie breaker | TXU Electric Delivery | May-05 | 345 | TITUS |
| Watermill - Cedar Hill (2nd) 345 kV circuit | Install Watermill - Cedar Hill (2nd) 345 kV circuit | TXU Electric Delivery | May-05 | 345 | DALLAS |
| Cedar Bayou 345/138 kV autotransformer | Add fourth 345/138 kV, 800MVA autotransformer (A4) @Cedar Bayou and reconnect third auto (A3) to the west bus, parallel to A1 & A2 | CNP | Jun-05 | 345 | HARRIS |
| Salem 345/138 kV autotransformer upgrade | Upgrade Salem 345/138 kV autotransformer capacity to 672 MVA | LCRA | Jun-05 | 345 | WASHINGTON |
| Kendall 345/138 kV autotransformer # 2 | Install a second 345/138 kV autotransformer at the Kendall substation | LCRA | Jun-05 | 345 | KENDALL |
| Watermill - W. Levee (2nd) 345 kV circuit | Install Watermill - W. Levee (2nd) 345 kV circuit | TXU Electric Delivery | Oct-05 | 345 | DALLAS |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A1) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A4) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| Rio Hondo, add 345/138 kV auto | Rebuild La Palma to Rio Hondo 138 kV with 2-795 ACSS, double circuit capable and add 345/138 kV autotransformer at Rio Hondo | AEP/TCC | Apr-06 | 345 | CAMERON |
| Pecan Creek 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at Pecan Creek | TXU Electric Delivery | May-06 | 345 | BELL |
| Venus - Sherry 345 kV line | Construct Venus - Sherry 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| W. Levee - Norwood 345 kV line | Construct W. Levee - Norwood 345 kV line | TXU Electric Delivery | May-06 | 345 | DALLAS |
| Venus - Liggett 345 kV line | Construct Venus - Liggett 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| Venus - Johnson Switch 345 kV line | Upgrade existing 345 kV line | TXU Electric Delivery | May-06 | 345 | ELLIS |
| Valley 345/138 kV autotransformer | Replace existing 450 MVA 345/138 kV autotransformer with a 600 MVA autotransformer | TXU Electric Delivery | May-06 | 345 | FANNIN |
| Jewett - TH Wharton 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU Electric Delivery | May-06 | 345 | LEON |
| Jewett - Tomball 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU Electric Delivery | May-06 | 345 | LEON |
| T.H.Wharton - Jewett ckt.1 | Upgrade tie lines from TH Wharton to TXU tie point to increase thermal ratings to 1450 MVA by raising conductors and upgrading limiting equipment at TH Wharton | CNP | May-06 | 345 | HARRIS |
| Nelson Sharpe, add 345/138 kV autotransformer | Construct Nelson Sharpe 345/138 kV substation in the Lon Hill to Rio Hondo 345 kV line and add a phase-shifting transformer at Nelson Sharpe in Davis 138 kV line | AEP/TCC | May-06 | 345 | KLEBERG |
| Zorn Auto | Replace the 600MVA Zorn Auto 2 with a 478MVA auto (7045-7180) | LCRA | Jun-06 | 345 | GUADALUPE |
| Clear Springs | Add a new 345/138 kV 478 MVA auto-transformer at the Clear Springs substation(7050). The existing 345 kV bus at the Clear Springs will be converted from a ring bus configuration to a double-bus double-breaker configuration. Upgrade the 7.2-mile Clear Springs(7680)-Geronimo(7604)-Seguin(7228) 138 kV transmission line (T-264) from 336 ACSR to Bundled 795 ACSR double circuit capable. Upgrade the 7.2-mile Clear Springs(7680)-Freiheit(7462)-Hortontown(7175)-Comal(7176) 138 kV transmission line (T-264, T-394, and T-119) from 336 ACSR to Bundled 795 ACSR double circuit capable. | LCRA | Jun-06 | 345 | GUADALUPE |
| Kendall-CPS Cagnon 345-kV line | Construct a 345 kV bundled 1590 ACSR line (approximately 45 miles) between Kendall (7046) and Cagnon (5056) | LCRA / CPS | Jun-06 | 345 | BEXAR |
| Skyline - Replace 345kV Autotransformer #2 & #4 | Replace the two 480 MVA autotransformers(#2 & #4) with one 600 MVA autotransformer. | CPS | Jul-06 | 345 | BEXAR |
| Elm Creek Substation | Install new 345 kV switching station at the intersection of the existing 345kV lines from STP-Skyline, STP-Hill Country, and both lines from Marion to San Miguel. | CPS | Oct-06 | 345 | GUADALUPE |
| Jacksboro Switch - W. Denton 345 kV line | Construct Jacksboro Switch - W. Denton 345 kV line | TXU Electric Delivery | Dec-06 | 345 | JACK |
| Sandow 345/138 kV autotransformer | Install second 345/138 kV autotransformer | TXU Electric Delivery | Dec-06 | 345 | MILAM |
| Odessa EHV 345/138 kV 300 MVA autotransformer replacement | Replace existing 300 MVA 345/138 kV autotransformer with a 450 MVA autotransformer | TXU Electric Delivery | Dec-06 | 345 | ECTOR |
| Sandow 345/138 kV autotransformer | Install second 345/138 kV autotransformer | TXU Electric Delivery | Dec-06 | 345 | MILAM |
| Paris Switch - Anna 345 kV line | Construct Paris Switch - Anna 345 kV line | TXU Electric Delivery | Dec-06 | 345 | LAMAR |
| WAP 345 kV sub. | Upgrade fault duty rating of WAP 345 kV to at least 56 kA | CNP | Dec-06 | 345 | FORT BEND |
| Smithers 345 kV sub. | Upgrade fault duty rating of Smithers 345 kV to at least 52 kA | CNP | Dec-06 | 345 | FORT BEND |
| STP - Dow ckt.18 and ckt.27 | Replace 2000 Amp equipment on both circuits from STP to DOW. | CNP | Dec-06 | 345 | MATAGORDA |
| DeCordova - Benbrook 345 kV line upgrade | Upgrade capacity of line | TXU Electric Delivery | May-07 | 345 | HOOD |
| DeSoto 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at DeSoto | TXU Electric Delivery | May-07 | 345 | DALLAS |
| Plano Tennyson 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at Plano Tennyson | TXU Electric Delivery | May-07 | 345 | COLLIN |
| Trinidad - Richland 345 kV line | Upgrade Trinidad - Richland 345 kV line | TXU Electric Delivery | May-07 | 345 | HENDERSON |
| Venus - Cedar Hill 345 kV line | Upgrade existing 345 kV line | TXU Electric Delivery | May-07 | 345 | ELLIS |
| Spruce to Skyline 345kV 2nd Circuit | Build 2nd 345 kV line from Spruce to Skyline substation | CPS | Jun-07 | 345 | BEXAR |
| Second Whitney 345/138 Autoitransformer | Install second 450MVA 345/138KV auto at Whitney | Brazos | Jun-08 | 345 | BOSQUE |
| Hillje Switching Station | Build a new 345 kV Hillje substation. Loop ckt.1 STP-Holman into the new substation. | CNP | Dec-08 | 345 | WHARTON |
| STP - Hillje ckt. | Build new 345 kV line from STP to Hillje. | CNP | Dec-08 | 345 | MATAGORDA |
| WAP - Hillje ckt. | Build new 345 kV double circuit line from WA Parish to Hillje. | CNP | Dec-08 | 345 | FORT BEND |
| Increase CNP 345/138 kV autotransformer capacity | Add several 800 MVA autotransformers in the CNP transmission system | CNP | Dec-08 | 345 | HARRIS/CHAMBERS/FORT BEND/GALVESTON/BRAZORIA |
| WA Parish - Bellaire ckt 50 | Raise conductors to increase thermal ratings | CNP | Dec-08 | 345 | FORT BEND |
| Smithers - Bellaire ckt.98 | Raise conductors to increase thermal ratings | CNP | Dec-08 | 345 | FORT BEND |
| West Denton - NW Carrollton 345 kV circuit | Add second Circuit from West Denton to NW Carrollton | TXU Electric Delivery/TMPA | May-09 | 345 | DENTON |
| Skyline - Install a third 345kV Autotransformer | Install one 600 MVA autotransformer. | CPS | May-09 | 345 | BEXAR |
| Second Concord 345/138 Autotransformer | Install second 300MVA 345/138KV auto at Concord | Brazos | Jun-09 | 345 | JOHNSON |
| Cagnon to Hillcountry 345kV 2nd Circuit | Build 2nd 345 kV line from Cagnon to Hill Country substation | CPS | Jun-09 | 345 | BEXAR |
| Hill Country to Skyline 345 kV 2nd Circuit | Build 2nd 345 kV line from Hillcountry to Skyline substation | CPS | Jun-09 | 345 | BEXAR |
| Dansby to Twin Oak 345 kV | Design and build a double circuit 345 that will tie into the existing TMPA Gibbons to Twin Oaks line | BTU | Jul-09 | 345 | BRAZOS |
| 2nd Lewisville Auto | Install (2nd) 345/138 kV autotransformer at Lewisville station | Brazos | Dec-09 | 345 | DENTON |
| Laredo Lobo, build 345 kV for 675MVA autotransformer | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/TCC | Mar-10 | 345 | WEBB |
| Laredo Lobo to San Miguel, build 345 kV line | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/STEC | May-10 | 345 | WEBB |
| Liggett - Trinity Switch 345 kV line | Construct Liggett - Trinity 345 kV line | TXU Electric Delivery | May-10 | 345 | DALLAS |
| Trinity Switch 345/138 kV autotransformer | Create Trinity Switch and install a 600 MVA 345/138 kV autotransformer | TXU Electric Delivery | May-10 | 345 | TARRANT |
| Hutto Switch - Salado Switch 345 kV line | Construct Hutto Switch - Salado Switch 345 kV line | TXU Electric Delivery | May-10 | 345 | WILLIAMSON |
| Hutto Switch 345/138 kV autotransformer | Create 345 kV switching station and install a 345/138 kV autotransformer | TXU Electric Delivery | May-10 | 345 | WILLIAMSON |
| Zorn/Clear Springs-Harris Branch-Hutto Switch 345-kV line | Construct a 345 kV DC 2x1590 ACSR line between Zorn/Clearsprings and Hutto Switch and other ONCOR and AE projects | LCRA | Jun-10 | 345 | WILLIAMSON |
| Harris Branch 345/138kV autotransformer | Install a 345/138kV autotransformer at Harris Branch substation | Austin Energy | Dec-10 | 345 | TRAVIS |
| Harris Branch 345/138kV autotransformer & Harris Branch 138kV circuit to East and Techridge Substation. | Install a 345/138kV autotransformer at Harris Branch substation. Cut-in the existing East to Techridge 138kV circuit to establish the 138kV East to Harris and 138kV Harris to Techridge circuits | Austin Energy | Dec-10 | 345 | TRAVIS |
| Frontera, add SS with 345/138 kV autotransformer | Addition North Edinburg to Frontera to South McAllen 345 kV line with bundled 1590 ACSR conductor and double circuit capable structures and 345/138 kV substation at Frontera | AEP/TCC | May-11 | 345 | HIDALGO |
| Laredo Lobo to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Frontera to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Rio Bravo, 138 kV SS with 345/138 kV autotransformer | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| North McCamey to Twin Buttes 345 kV Line | 12/02 plan recommends the construction of a 345kV 2x1590 ACSR line between North McCamey and Twin Buttes | LCRA/AEP | Jan-12 | 345 | UPTON |
| North McCamey - Odessa 345 kV Line | 12/02 plan recommends the construction of a 345 kV 2x1590 ACSR line between North McCamey and Odessa and 2x600 MVA autotransformers at North McCamey | LCRA/AEP | Jan-12 | 345 | UPTON |
| North McCamey 345/138 kV autotransformer | Recommends the addition of a 345/138kV autotransformer North McCamey | LCRA/AEP | Jan-12 | 345 | UPTON |
| Frontera to South McAllen 345 kV line | Construct a 345 kV transmission line from Frontera to South McAllen. | LCRA/AEP | May-15 | 345 | HIDALGO |
| Rio Hondo to Ranchito, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345 kV line | AEP/TCC |  | 345 | CAMERON |
| Ranchito, new SS with 345/138 kV autotransformer | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| Ranchito to South McAllen, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| South McAllen, new SS with 345/138 kV autotransformer | Construct a 345 kV substation south of South McAllen cut into the South McAllen to Hidalgo 138 kV line and install a 345/138 kV autotransformer | AEP/TCC |  | 345 | HIDALGO |
| Loma Alta - Ranchito or la Palma 345-kV line | Install 345-kV line from Loma Alta to La Palma or Ranchito | BPUB |  | 345 | CAMERON |
| Loma Alta - Rio Hondo 345-kV line | Install 345-kV line from Loma Alta to Rio Hondo | BPUB |  | 345 | CAMERON |
| Loma Alta 345kV station and autotransformer | Construct a 345 substation and connect to the existing Loma Alta 138 substation. | BPUB |  | 345 | CAMERON |
| Sandow - Temple Switch 345 kV line | Upgrade Sandow - Temple Switch 345 kV line | TXU Electric Delivery |  | 345 | MILAM |

Status of active generation interconnection requests

| PUBLIC PROJECTS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR # | SiteName | County | Region | Fuel | In Service Date | MW into Grid | Notes |
| 04INR0015 | Buffalo Gap 1 and 2 | Taylor | West | Wind | Sep-05 | 240 | 120 MW in 2005, 120 MW in 2006 |
| 04INR0020 | WKN Wind 1 Snyder | Scurry | West | Wind | Dec-05 | 61 |  |
| 05INR0010 | Jack County Generation Facility | Jack | North | Gas | Dec-05 | 700 | testing 6/1/05, commercial 12/1/05 |
| 06INR0008 | Big Spring Carbon Plant | Howard | West | Waste heat | Apr-06 | 12 |  |
| 03INR0034 | Silver Star Project | Erath | West | Wind | Jun-06 | 60 |  |
| 05INR0018 | Horse Hollow 2 | Taylor | West | Wind | Jun-06 | 127 | Second of two phases |
| 05INR0015 | Gulf Wind | Kenedy | South | Wind | Jul-06 | 200 |  |
| 06INR0016 | Dow 9 | Brazoria | South | NG | Oct-06 | 0 |  |
| 01INR0028 | Orion Delaware Mountain Wind Farm | Culberson | West | Wind | Dec-07 | 175 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | North | Gas | May-08 | 1,750 |  |
| 09INR0002 | J K Spruce 2 | Bexar | South | Coal | Aug-09 | 750 |  |
| 10INR0002 | Hugo Plant | Choctaw, OK | North | Coal | Dec-10 | 500 |  |
|  |  |  |  | Totals |  | 5,740 |  |
| PROJECTS INTO OPERATION |  |  |  |  |  |  |
| INR # | SiteName | County | Region | Fuel | In Service Date | MW into Grid |  |
| 05INR0014 | Sun Substation | Scurry | West | Gas | May-05 | 0 |  |
| 05INR0018 | Horse Hollow 1 | Taylor | West | Wind | Jun-05 | 220.5 | First of two phases |
| ACTIVE GENERATION INTERCONNECTION REQUESTS BEING PROCESSED |
|  |  | North | South | West | Total |  |  |
| Security Screening Study | 2 | 1 | 2 | 5 |  |  |
| SSS Completed | 0 | 3 | 11 | 14 |  |  |
| Full Interconnect Study | 7 | 5 | 8 | 20 |  |  |
| FIS Completed | 1 | 0 | 3 | 4 |  |  |
| Interconnect Agreement Completed (Includes public letters) | 3 | 3 | 6 | 12 |  |  |
| Capacity for Grid, MW | 5,804 | 3,940 | 6,033 | 15,777 |  |  |
| Wind MW (under development) | 480 | 2,830 | 5,366 | 8,676 |  |  |

Generation Currently Under RMR Contract in ERCOT (as of 8/1/05)

| Unit | Capacity (Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date |
| --- | --- | --- | --- | --- |
| BM Davis 2 | 356 | Under Contract | 1/1/05-12/31/05 | 3Q 2006 |
| JL Bates 1 & 2 | 183 | Under Contract | 1/1/05-12/31/05 | 3Q 2006 |
| La Palma 4, 5, 6, &7 | 249 | Under Contract | 1/1/05-12/31/05 | 1Q 2006 |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/05-12/31/05 | 3Q 2010 |
| PH Robinson 2 | 461 | Under Contract- 90 Day Termination Notice Sent | 5/17/05-5/16/06 | 10/29/05 |
| Total MW Under RMR: | 1,421 |  |  |  |

Studies underway or planned to be started within Transmission Services

- 345/138 kV autotransformer outage congestion analysis

- BM Davis Unit 2 RMR exit strategy review

  - Remain in RMR status until transmission additions are completed

- Bryan/College Station study

- Continue efforts to maintain reliable service to the lower Rio Grande Valley

- DFW/NE 2009 congestion study

- Dynamic and voltage stability limit evaluation of 2005 CSC/CM zonal transfers

- Enhance dynamic data models

- Enhance fidelity of contingency files and testing

- Enhance fidelity of planning base cases to better match real-time operating environment

- Enhance generation data gathering efforts and model improvements

- Evaluation of Laredo MRA proposals

- Examine limitations involving the Menard 138/69 kV autotransformer southeast of San Angelo

- Killeen and Temple area security study performing the voltage analysis for the Killeen area

- Load modeling improvements and improvements to base case modeling

- Load stability modeling project - Phase II (EPRI Solutions) is starting

  - ROS and TAC endorsed/supports this effort

  - ROS encouraged transmission owners to get involved in the project to improve stability modeling and support reliability studies

- Net Dependable Capability Testing Data ERCOT staff efforts are ongoing to determine the fidelity of and best practices in planning for the generator data that is sent to ERCOT compliance

- October 1 report work is underway and includes the following

  - Desktop software installed and training completed

  - Develop graphics

  - Develop outline elements

  - Develop summary of congestion costs

  - Develop documentation of ERCOT operational improvements

  - Projection of marginally congested elements

- Outreach program to help stakeholders understand planning activities

  - TPPA presentation

- PH Robinson 2 RMR exit strategy review

- Steady State WG base case (planning) and network model branch data (operations) comparison was conducted in July

  - Differences were identified and forwarded to NDSWG and SSWG for resolution

  - Updates to the planning and operations (service requests) data are due by Aug 1

  - Another comparison will be conducted the second week in August

- Transient Voltage Dip analysis of the Corpus Christi area, work performed by Siemens/PTI in cooperation with Flint Hills, AEP TCC and ERCOT System Planning, public report being prepared

- Transmission Loss Factors 2006 calculations

- Transmission Project Information Tracking (TPIT) investigate moving to online database with on demand changes and reporting

- Transmission Services will be looking at how to incorporate biennial unit reactive test data into the Steady State WG base cases for more accurate modeling

- Utility Wind Interest Group (UWIG) wind farm stability modeling effort

- West Texas ERCOT/SPP joint study is underway to determine possible mutual benefits

- West-North transfer limit study

Studies that have been completed by Transmission Services

- BM Davis MRA evaluation of two proposals

- Conducted survey of normally open lines that are closed automatically through system protection

- Critical Transient Stability Events Annual (2005) Survey (reliability/security protected information) completed

  - Results will be provided to transmission owners and compliance in August

- Critical Voltage Stability Events Annual (2005) Survey (reliability/security protected information) completed

  - Results will be provided to transmission owners and compliance in August

- CSC determination and CM Zone calculations for 2006 has been completed, current proposal is to keep the current zones for 2006

- ERCOT Process Work Improvement Project Phase 1, development of internal process documentation is underway

- ERCOT Wholesale Market Basic Training by client reps was very informative and recommended

- Hackberry SPS, Commerce SPS and several modifications to existing TXU ED SPSes has been approved.

- Hays SPS revisions have been approved and an approval letter is being sent to LCRA

  - Changes were necessary to accommodate the recent addition of a second 345/138 kV autotransformer at Kendall

- LAAR increase study impact by major industrial customer

- PH Robinson 2 RMR exit strategy review completed

  - Exit notice to be provided in August

- PUCT workshop on Proj. 28,500 prepared projection of relative marginal costs for

- Sierra Vista (AEP) project study completed

  - Very simple project, radial substation to serve load

- South RPG/RMR Exit Strategy meeting held on July 15th to discuss B.M. Davis unit 2, P.H. Robinson unit 2 and Laredo RMR exit strategies

  - Technical characteristics of Laredo tie to CFE/Mexico were presented

- SPS approval procedure has been approved and posted on the ERCOT Operations and Planning secure website in the “Special Protection System (SPS) Information” folder

- System Protection WG 2005 Future Year short circuit base cases for the years 2006 to 2009 are currently being built

  - Third pass has been completed and the TDSP’s are reviewing the cases

  - Corrections and additions for pass 4 are due on August 9th, 2005

- Steady State WG 2006 Data Set A base cases have been completed and posted

Upcoming Events

- NERC PC TIS Meeting, August 3 & 4, Irving

- NERC PC TIS Meeting, August 29 & 30, location not determined yet

- NERC PC Meeting, September, 14 & 15, Dallas

- NERC OC TS Meeting, September 20 & 21, Washington DC

Other Issues

- Continuing to work with ERCOT Compliance in an attempt to ensure that future compliance surveys (e.g. UFLS) obtain data in a format that is more readily incorporated into system modes

- National Renewable Energy Laboratory (NREL) is willing to perform stability studies together with ERCOT System Planning to validate the dynamic models of wind farm, subject to the availability of disturbance data for a transient event in the West Texas network

- Responding to NERC recommendations ROS Dynamics WG will simulate an actual event to test dynamic models.  DWG is reviewing an event to assess its suitability to the NERC recommendation scope.  System planning staff will provide support to the study

- Senate Bill 20 (renewable) has been signed by Governor Perry

  - RPS cumulative installed renewable capacity

    - 2,280 megawatts by January 1, 2007

    - 3,272 megawatts by January 1, 2009

    - 4,264 megawatts by January 1, 2011

    - 5,256 megawatts by January 1, 2013

    - 5,880 megawatts by January 1, 2015

    - 10,000 megawatts by January 1, 2025

    - 500 megawatts of capacity from a renewable energy technology other than a source using wind energy

  - Requires transmission planning and construction to support these goals

Things Transmission Services feels TDSP/TO’s should be paying attention to

- Continue to support the model and contingency file validation efforts between Planning and Operations models

- Differences in generation Mvar capability between planning and operations models

- Ensure transmission additions are completed in a timely manner and accurate system operations model updates are submitted when projects are completed

- Terminal equipment upgrades to increase utilization of existing conductors

Interesting observations

- Several interconnection security screening studies simulating transfers west to north indicate an increase total transfer capability if the following possible improvements are made in the DFW area.  These items may also show up in the DFW/NE 2009 congestion study for transfers from the west.

  - Reconfigure Benbrook Station to ensure the loss of any 345 kV circuit does not also cause the loss of an autotransformer

  - Add second 345 kV circuit connecting Jacksboro to Willow Creek and on to Parker

  - Upgrade Everman to Decordova 345 kV line

  - Upgrade several 138 kV lines in Kimball area

  - Install a third Benbrook 345/138 kV autotransformer

  - Upgrade Oklaunion to Fisher Road 345 kV line

  - Install a second 345/138 kV autotransformer at Eagle Mountain

  - Numerous terminal equipment upgrades

- ERCOT Operations is concerned with a possible first contingency voltage collapse beginning at Presidio 69 kV in far, far West Texas.  The loss of Barrilla Junction to Alamito 138 kV or the loss of the 138/69 kV Alamito transformer can both cause problems.  AEP has projects in TPIT with Summer 2005 completion dates to address the situation and the SSWG Summer 2006 Peak case shows no problem given the additional construction in the area over the course of the upcoming summer to summer calendar year

- Falcon Seaboard Co-Gen surrounding 138 kV circuits were modeled incorrectly in planning model; planning model will be corrected via IDEV

- System Planning analysis shows the flow across individual CSC interfaces does not appear to be reliable indicators for voltage stability issues – System Planning is working with System Operations to develop more effective measures for establishing voltage stability based system operating limits

Future issues

- Generation deficiency for SSWG 2006 Data Set B planning bases

- Generator reactive capability data, planning and operations differences

- Reactive load (power factor) modeling in planning and operations

Internet Links

- Operations and System Planning Data area

  - http://www.ercot.com/tmaps/Login.cfm

  - Major data folders of interest in this area

    - Power System Planning Charter & Processes

    - October 1 Report to PUCT Annual

    - CSC CM Zone 2005 Data Files

    - Capacity, Demand, and Reserve Reports

      - Report on generation capacity, projected demand and reserves

    - Contingency Information – planning

    - Demand and Energy Reports (D&E) Monthly Actuals

      - Monthly actual demand and energy report

    - EIA-411 DOE Regional Electricity Supply and Demand Projections

    - Generation Project Interconnection Information

      - Public new and existing generation projects in ERCOT since 1996

    - Maps of ERCOT Transmission System

    - Operations Engineering Procedures

    - Operations Model Data

      - System Operations Base Case updated often

    - Regional Planning Group NORTH

    - Regional Planning Group SOUTH

    - Regional Planning Group WEST

    - Reliability Must-Run (RMR) Studies

    - Special Protection Schemes (SPS) Information

    - Steady State Base Case Info & Old Data

    - Steady State Power Flow Base Cases 2005 Data Set A (2005 eight seasonal cases)

    - Steady State Power Flow Base Cases 2005 Data Set B (2006-2010 cases)

    - System Protection Short Circuit Data

    - TNT Cost Benefit Study Data

    - Transmission Project & Information Tracking (TPIT)

    - Voltage Security Study of ERCOT System

    - Wind Stability Modeling ERCOT Project