## Slide 1
EXECUTION
Site Acceptance Testing continues.
INITIATION TO PLANNING WITH NO CAPITAL BUDGET YET APPROVED
Project Scope/Deliverables
Timeline
Issues / Actions
Financial Milestones as of 6/30/05
Executive Summary of Status
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Activity | Frcstd. Completion Date | % Complete | Status
Scope Lock | 5/28/04 | 100% | Complete
Detail Design | 10/29/04 | 100% | Complete
Build and Unit Test | 12/3/04 | 100% | Complete
Pre-FAT | 1/24/05 | 100% | Complete
Factory Acceptance Test | 3/11/05 | 100% | Complete
Production Migration – EMS | 6/15/05 | 100% | Complete
Site Acceptance Test / Regression Test | 4/4/05 thru 9/9/05 | 65% | In progress
User Acceptance Test | 9/6/05 thru 9/9/05 | 0% | Not Started
Market Participant Test | 9/12/05 thru 9/23/05 | 0% | Not Started
Production Migration - MMS | 9/28/05 | 0% | Not started
Sponsor: Saathoff
Bus Lead: Patterson
Last Update
This Update
Bus Align/ Scope Risk
Technical Risk
Schedule Risk
Staffing Risk
Financial Risk
Overall
G
Y
G
G
G
R
G
G
G
G
 | Approved Budget |  |  | Current Forecast / Actual |  | 
 | Capital | Expense | Total | Total Forecast | Committed to Date | Actual to Date
Labor |  |  |  |  |  | 
AREVA Labor |  |  |  |  |  | 
HW |  |  |  |  |  | 
SW |  |  |  |  |  | 
Other |  |  |  |  |  | 
Total |  |  |  |  |  | 
X
Updated
G
G
G
10 major deliverables from AREVA (MOS–5, POS-4, PUCT-1) + 7 internal sub projects (4 Billing & Settlements, 3 DA/DW)
Billing & Settlements development underway. OOM Tool Enhancements planning near completion.
DA/EDW planning completed.
Contingent upon final patch delivery from AREVA on August 4, 2005, the market migration is targeted for September 28, 2005
Market Participant Test
Client Services will re-establish timeline.
G
Y

## Slide 2: Deliverables
Associated PRR # | Project Title
PRR211 | Association of BE Bids with RPRS
PRR413 | Optimization for the Whole Operating Day in RPRS Procurement Process
PRR359 | Resource Plan Improvement (Phase II)
PRR485 | Unit Specific Bid Limits based on Generic Costs
PRR342 PRR414 | AS Simultaneous Selection
PRR423 | Dispatch of Generation Resources Below Minimum Operating Level
PRR422 | OOM Zonal Dispatch Instructions
 | Enhancement to OOM tools for congestion management
 | Improve Data Elements for Local Constraints & OOMs
 | EMMS Parameters Capture for MMS Reclear Fidelity
 | OOM Participation in Providing Ancillary Services
Complete | Special Protection Schemes [6/15/2005]
Complete | Improve Power System Model Maintenance via Database Archive Comparison [6/15/2005]
Complete | Improvements to VSAT/TSAT [6/15/2005]

## Slide 3: Contributing Factors for Delaying Migration
Quality of AREVA Patches (10 weeks)
  Ongoing issues with OOM related patches from AREVA
    Three patches received - April 29th, May 24th and July 7th
    Final patch delivery expected on August 4th
ERCOT (June) Changes to Scope (2 weeks)
  OOM (1 week)
  RPRS (1 week)
  MOMS (none)
Resource Conflicts (4 weeks)
  Unexpected level of production support activities
    Null notification
    Adjustment period A/S Market Issues
    Problems with Non-Spin recall
    RPRS issues due to addition of new QSEs
  Schedule slippage resulted in conflicts with planned training and vacation schedules

## Slide 5
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
SEPT 5 – 9: UPDATE Test Contacts and Test URL/IP addresses
SEPT 7 – 9: Confirm Test URL/IP addresses
  MP “Test” Listener Connectivity
SEPT 12 – SEPT 23: Release 4 XML Testing
  Structured Notification Tests
  Unstructured Testing on MOTE
Tentative Market Participant Test Plan

## Slide 6
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
Distribute Example XML – AUG 25th
MP Test Plan
Contingent on Rel4 Migration into iTest by Aug 15th.
Sample OOM Deployments
Sample RPRS Bid and Award.

## Slide 7
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Sponsor: Saathoff
Bus Lead: Patterson
MP Test Lead: Coon
MP Test Plan