## Slide 1
Objectives:
Improve site structure and navigation
Identify & implement an ownership structure
Implement a web content management system (Serena Software’s Collage)
Implement a search engine (Google Search Appliance)
Develop a process to ensure the sustainability of the investment in the enhancements
Scope/Why is this important?:
Search engine functionality (including metadata strategy)
Improve navigation - create a new information architecture for the site (task driven focus)
Content owners can post updates easily – content manager
Process for maximizing the use of key real estate for critical and timely information
All information and processes are maintained after the redesign
Public areas of the site
Dependencies:
None at this time
Project Objectives / Scope / Dependencies
PR-40106 ERCOT.com
As of August 16, 2005
Page 1

## Slide 2
Phase:
Initiation – completed in Sept ‘04
Planning – completed in June ‘05
Execution – Started on June 13, 2005
Closing – goal December ‘05
Recent:
Received training on Serena’s CMS product
Began work on re-designing ERCOT’s public website and migrating documents using the CMS tool
Conducted information meetings for ERCOT employees
Conducted information meetings for MPs
Next steps:
Purchase and install Google Search Appliance
Continue work on re-designing ERCOT’s public website
Continue work on migrating documents to ERCOT’s re-designed site using Serena’s CMS product.
Summary of Project Status
PR-40106 ERCOT.com
As of August 16, 2005
Page 2

## Slide 3
** All target dates – will have firm dates after project plan is completed
Requirements (pens down) – June ‘05
Design (published document) – June/July ’05
ERCOT Testing – October ’05
Training – October/November ’05
Production (Go live) – November ‘05
High level timeline
PR-40106 ERCOT.com
As of August 16, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 24 Program Area: RO
What prompted the project:
  Market Survey
  TML Phase II Mid-Term Requirements
  Strategic Fit
Supporting business drivers:
  Data from the Market Survey strongly encouraged the implementation of a search engine
  Peer website comparisons between the other ISOs
  Practical usage feedback
Additional Information
PR-40106 ERCOT.com
As of August 16, 2005
Page 4