## Slide 1: Project Updates to DEWG
Jackie Ashbaugh
ERCOT
August 11, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Project Updates
PR 40106 - ERCOT.com
PR 50007 - FasTrak
PR 50024 - Enhancements to SCR 727 (SCR 740 Web Service for ESIID data)
PR 40007 - SCR727 move from Data Archive to ODS
PR 40042_06 – Lodestar Batch Extracts
PR 30026 - EPS Meter Data Extract/Resource ID Extract
2005 Upcoming Projects
PR 50023 Potential Load Loss
Necessary Project Updates?
TBD
Projects
ERCOT Project Updates
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
PR-40106 ERCOT.com
  Execution Phase
  Received training on Serena’s CMS product
  Began work on redesigning ERCOT’s public website and migrating documents using the CMS tool
  Conducted information meetings for ERCOT employees
  Next Steps:
    Purchase and install the Google Search Appliance
    Continue work on redesigning ERCOT’s public website
    Continue work on migrating documents to ERCOT’s re-designed site using the Serena’s CMS product
    August 12th meeting with MPs to illustrate project progress
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
PR-50007 Enhancements to FasTrak
  Execution Phase
  Finalized product selection – selected Serena Software’s Team Track product
  Finalizing contract negotiations with Serena Software
  Starting conceptual design phase of the project
  Implementation slated for Q1 2006.
  Next Steps:
    Finalize conceptual design
    Schedule training for ERCOT employees on Serena’s Team Track product
    Set up Team Track development environment
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
PR-50024 Enhancements to SCR 727
  Execution phase
  Building design for phase 1 (Business Intelligence) – developer resourcing issue resolved
  Building design for phase 2 (Services – architecture)
  Implementation date: 1st Quarter 2006
  Next Steps:
    Finalize XML format
    Continue design on queuing theory
    Begin developing test scenarios for Product Test
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
PR-40007 SCR 727 Phase 2
  SCR 727 ESIID Extract, Public Reference Data Extract
  Execution phase
  Development of testing scenarios close to completion
  Developers are completing unit testing their design
  Completing development the timing logic for when to run and what timestamp data range to include in each extract – to be implemented to production by 09/01/2005
  Next Steps:
    Begin PTEST and UAT on SCR 727 logic late 08/2005
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
PR-30026 EPS Meter Data Extract/Resource ID Extract
  RID Extract
  Execution phase
  Completing development the timing logic for when to run and what timestamp data range to include in each extract – to be implemented to production by 09/01/2005
  Next Steps:
    Prepare code for ITEST
    Complete development of ITEST test plan for technical integration testing and UAT
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
PR-50023 Potential Load Loss
Bus Lead: Denise E. Taylor
phone number: 512-248-3932
e-mail: dtaylor@ercot.com
PPL: Source: Market Priority: 1.2 Rank: 32 Program Area: RO
What prompted the project: SCR 739 Pending Load Loss Reports for CRs
Phase:
Initiation – completed August 1, 2005
Planning – tentatively August 22, 2005
Supporting business drivers:
  Allow for more accurate and timely visibility into retail customer load changes
  Decrease time and cost incurred by CRs to adjust their power purchase forecasts and power schedules
Upcoming projects
Notes: <number>
<footer>
<header>
<date/time>