## Slide 1: TX SET V2.1 Market Coordination Team

## Slide 2
Business lead: Suzette Wilburn
Phone number: (512) 248-3991
Email address: swilburn@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 6 Program Area: RO
What prompted the project:
  MOU/EC Entrance to Texas Deregulated Market
  Market Efficiency
  Identified Transactional Gaps
Supporting business drivers:
  More efficient transaction processing
  Business process solidification
PR-40034/TX SET V2.1

## Slide 3
Objectives:
To implement all approved Change Controls as identified by the TX SET Working Group for market-wide use
Provide coordination, clarification of issues, and documentation for v2.1 Change Controls through the Market Coordination Team (MCT) efforts
Scope:
Support the MOU/EC entrance into the Texas deregulated market
Address Disconnect for Non-Pay processes
Communicate additional billing determinants to the Market
Dependencies:
Completion of Market Requirements from TX SET Working Group
PR-40034/TX SET V2.1

## Slide 4
Phase:
Initiation – Completed March 28 ‘05
Planning – Completed May 27th, 2005
Execution – Goal to complete early December ’05
Closing – Goal to complete late December ‘05
Recent:
Completed Internal Testing
Edited Protocols, Sections 15 and 24
Edited Retail Market Guide
Next steps:
Finalize edits to Protocols and Retail Market Guide
Submit for review
PR-40034/TX SET V2.1

## Slide 5
Requirements (pens down) – Completed April 7th, 2005
Design (internal document) – Completed May 27th, 2005
Build – Completed July 22nd, 2005
Internal Testing – Completed August 22nd, 2005
Internal Training – Completion goal of November 17th, 2005
Market Testing – Completion goal of November 23th, 2005
Production (Go live) – December 4th, 2005
PR-40034/TX SET V2.1

## Slide 6
Market Participant Progress Report
All Market Participants were requested to provide their progress on Design/Code/Test of TX SET V2.1 and identify any risks that would delay Flight 1005 or Implementation
No issues or risks have been identified by any Market Participant or Service Provider that would prevent them from testing in the 1005 Flight Test or implementing on December 4th, 2005
Deadline to sign up for Flight 1005 is September 21st, 2005
Connectivity for Flight 1005 begins September 27th, 2005
V2.1 MCT Updates

## Slide 7
September Progress - REPs

## Slide 8
September Progress - REPs

## Slide 9
September Progress - REPs

## Slide 10
September Progress – TDSPs/ERCOT

## Slide 11
Progress Update
Delayed Annual Validation Cross Impact
  Proposal by PWG to suspend sending 814_20s for annual validation until at least November 3rd
  TX SET Version 2.1 Requirement 33 (CC2003-576) adds new validation to the 814_20 transaction that requires the Meter Type and Meter Multiplier when sending a change in Load Profile for metered services
  814_20 transactions generated prior to the TX SET Version 2.1 implementation date of December 4rd must be received by ERCOT prior to December 2nd
  All 814_20s sent after the December 4th implementation date must be in 2.1 code to pass validation at ERCOT
V2.1 MCT Updates

## Slide 12
Next Steps
Next meeting on September 22nd in Austin
Finalize Protocol revisions
Finalize Retail Market Guide revisions
Submit Protocol and Retail Market Guide revisions
MCT Materials can be found on the ERCOT website
  www.ercot.com
  Select Market Participants & Stakeholders
  Select Texas Set
  Select Key Documents
  Select Related Working Groups
  Select Version 2.1 Market Coordination Team Documentation
V2.1 MCT Updates