August 2005 Report

To

Technical Advisory Committee

Reliability and Operations Subcommittee

Prepared by ERCOT Transmission Services

Transmission Project Summaries

Additional detailed project information is contained in the August 1 Transmission Project Information Tracking workbook posted in the “Operations and System Planning” data area on the internet.  See links at end of this document for address.

Completed Projects

Future Projects

Major transmission projects recently completed

Additional detailed project information is contained in the August 1 Transmission Project Information Tracking workbook posted in the “Operations and System Planning” data area on the internet.  See links at end of this document for address.

| Project Title | Project Description | Transmission Owner | In-Service Date | kV | Location County |
| --- | --- | --- | --- | --- | --- |
| Kendall 345/138 kV autotransformer # 2 | Install a second 345/138 kV autotransformer at the Kendall substation | LCRA | Aug-05 | 345 | KENDALL |
| EXXON - Bertron, S R Plant ckt.03 | Raised conductors to increase thermal ratings. | CNP | Jul-05 | 138 | HARRIS |
| Parkway Tap - Glenwood ckt.95 | Raised conductors to increase thermal ratings | CNP | Jul-05 | 138 | HARRIS |
| Greens Bayou - Parkway Tap ckt.95 | Raised conductors to increase thermal ratings | CNP | Jul-05 | 138 | HARRIS |
| Killeen Switch 138 kV capacitors | Install 138 kV capacitors | TXU ED | Jul-05 | 138 | BELL |
| Sun 138 kV capacitors | Install 138 kV capacitors | TXU ED | Jul-05 | 138 | SCURRY |
| Waco E system reactive capacitors | Install 138 kV capacitors | TXU ED | Jul-05 | 138 | MCLENNAN |
| Westfield | Installed new 138kV 80 MVAR capacitor bank on 138kV ckt.66 to Treaschwig. | CNP | Jul-05 | 138 | HARRIS |
| Central Austin : Build 69 kV Substation | Establish a new substation with (2) 30MVA transformers between Fiesta and Koenig Lane substations. New 69-kV transmission lines will be established. | Austin Energy | Jul-05 | 69 | TRAVIS |
| Alamito Creek, add 7.2 MVAR capacitor | Add 259 MVAR of static and 75 MVAR of dynamic reactive support throughout the McCamey area | AEP/TNC | Jul-05 | 69 | PRESIDIO |
| White Oak North | Increased reactive capability to 120MVAR | CNP | Jul-05 | 138 | HARRIS |
| Construct Booster 138KV Substation | Serve substation by looping into ckt.02 Velasco - Seaway | CNP | Jul-05 | 138 | BRAZORIA |
| Burleson Auto Relocation and Circuit 831 conversion | Relocate the existing 220MVA Burleson autotransformer to replace the failed Seaholm autotransformer and convert the 69kV Circuit 831 back to 138kV Circuit 1015. | Austin Energy | Jul-05 | 138 | TRAVIS |
| Jack County Plant to Cottondale Sw | Construct 3 138kv circuits from Jack County plant to vicinity of Cottondale Sw. | Brazos | Jul-05 | 138 | JACK |
| Reno to Cottondale Switch | Rebuild existing Reno to Cottondale Sw. 69kv line with 138kv const. | Brazos | Jul-05 | 138 | WISE |
| Southwest Research (SWRI) loop 138 kV line | Build new 138 kV line to SWRI substation | CPS | Jul-05 | 138 | BEXAR |
| Northwest Reliability Project, Phase 1 | Converted Kluge to a breaker substation. Looped Kluge into ckt.81 Klein - Pinehurst and ckt.21 Cameron - Addicks. Upgraded limiting equipment at Cameron and Kluge. Installed new 80 MVAR capacitor bank @ Kluge and 14.4 MVAR capacitor banks @Gertie and Cyfair. | CNP | Jun-05 | 138 | HARRIS |
| Allen Switch system reactive capacitors | Install 138 kV capacitors | TXU ED | Jun-05 | 138 | COLLIN |
| Crosby | Installed new 138kV 100 MVAR capacitor bank on 138kV ckt.66 to Atascocita. | CNP | Jun-05 | 138 | HARRIS |
| Cedar Bayou 345/138 kV autotransformer | Added fourth 345/138 kV, 800MVA autotransformer (A1) @Cedar Bayou and reconnected third auto (A3) to the west bus, parallel to 2A & 2B | CNP | Jun-05 | 345 | HARRIS |
| Flewellen - Obrien ckt.73 | Bundled 138kV Flewellen - Obrien ckt.73 and upgraded limiting equipment @Obrien and Flewellen substations to increase thermal ratings. | CNP | Jun-05 | 138 | FORT BEND |
| Liggett - Euless 138 kV line | Upgrade underground sections of 138 kV line | TXU ED | Jun-05 | 138 | DALLAS |
| Construct Goodyear 138KV Substation | Looped into Deepwater - Magnolia Park ckt.70 | CNP | Jun-05 | 138 | HARRIS |
| Plano Tennyson system reactive capacitors | Install 138 kV capacitors | TXU ED | Jun-05 | 138 | COLLIN |
| Carrollton East system reactive capacitors | Install 138 kV capacitors | TXU ED | Jun-05 | 138 | DALLAS |
| Iron Bridge 138/69 kV autotransformer | Install 138/69 kV autotransformer | TXU ED | Jun-05 | 138 | HUNT |
| Greens Bayou | Installed new 138kV 120 MVAR capacitor bank on 138kV ckt.70 to Lydell. | CNP | Jun-05 | 138 | HARRIS |
| Price Rd 138-kV Substation | Convert Price Rd Substation from 69-kV to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Lake Creek second 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer | TXU ED | Jun-05 | 345 | MCLENNAN |
| Deepwater - South Houston ckt.13 | Upgrade limiting equipment at South Houston to increase thermal ratings. | CNP | Jun-05 | 69 | HARRIS |
| Deepwater - South Houston ckt.13 | Upgraded limiting equipment at South Houston to increase thermal ratings. | CNP | Jun-05 | 69 | HARRIS |
| Ft. Lancaster to Friend Ranch, build 138 kV line | Addition of a Fort Lancaster to Friend Ranch 2x795 ACSR 138 kV line and double circuit capable structures | LCRA/AEP | Jun-05 | 138 |  |
| Fair Oaks Ranch 138 kV Substation loop | Install new 138kV substation loop into existing Boerne (LCRA) to Fair Oaks (LCRA) line. | CPS | Jun-05 | 138 | KENDALL |
| Cedar Bayou - Baytown ckt.88 | Raised conductors and partially reconductored ckt.88 Cedar Bayou - Baytown, and upgraded limiting equipment @Cedar Bayou to increase thermal ratings. | CNP | Jun-05 | 138 | HARRIS |
| Kendall-Miller Creek | Increase the line-to-ground clearance on the 40.4-mile Kendall(7152)-Miller Creek(7479) 138-kV transmission line as necessary to upgrade the circuit from its existing design rating of 82-MVA to its full conductor rating of 128-MVA. | LCRA | Jun-05 | 138 | KENDALL |
| Price Rd - Filter Plant 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Filter Plant - Airport 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Price Rd - FM 802 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| FM 802 - Midtown 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Midtown - Military Hwy 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Loma Alta - Price Rd 138-kV Circuit | Upgrade existing 69-kV circuit to 138-kV | BPUB | Jun-05 | 138 | CAMERON |
| Fair Oaks Ranch 138 kV Substation | Install new 138kV substation, loop into existing Boerne (LCRA) to Fair Oaks (LCRA) line. | CPS | Jun-05 | 138 | KENDALL |
| Braunig to Kennedy 138 kV Reconductor (Braunig - Elmendorf Section) | Rebuild 138 kV line from Braunig to Elmendorf to Eagle Creek to Floresville to Stockdale to Kennedy. | CPS | Jun-05 | 138 | BEXAR |
| Frontera to N McAllen, tap Palmhurst sub at 138 kV | Convert Moore Field and Palmhurst substations from 69 kV to 138 kV and connect to North Edinburg to Bates 138 kV line | AEP/TCC | Jun-05 | 138 | HIDALGO |
| Benbrook - Mistletoe 138 kV line | Upgrade 138 kV line | TXU ED | May-05 | 138 | TARRANT |
| Santa Anna to Bangs, rebuild 69 kV circuit | Convert Santa Anna to Brownwood 69 kV line to 138 kV with 795 MCM ACSR conductor | AEP/TNC | May-05 | 69 | COLEMAN |
| Santa Anna, add 138 kV SS | Convert Santa Anna to Brownwood 69 kV line to 138 kV with 795 MCM ACSR conductor | AEP/TNC | May-05 | 138 | COLEMAN |
| Brittmoore | Increased reactive capability to 127.2MVAR | CNP | May-05 | 138 | HARRIS |
| Fondren - H.O. Clarke ckt.25 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | HARRIS |
| Bayou - Orion ckt.79 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | HARRIS |
| Enprod - Mont Belvieu ckt.86 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | CHAMBERS |
| Hacher - Enprod ckt.86 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | CHAMBERS |
| Barhill - Hacher ckt.86 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | CHAMBERS |
| Crosby - Barhill ckt.86 | Verified conductors clearance to increase thermal ratings | CNP | May-05 | 138 | HARRIS |
| Humble | Increased reactive capability to 14.4MVAR | CNP | May-05 | 138 | HARRIS |
| Jeanetta | Increased reactive capability to 127.2MVAR | CNP | May-05 | 138 | HARRIS |
| North Belt | Increased reactive capability to 120MVAR | CNP | May-05 | 138 | HARRIS |
| T.H.Wharton West | Increased reactive capability to 120MVAR | CNP | May-05 | 138 | HARRIS |
| T.H.Wharton East | Increased reactive capability to 120MVAR | CNP | May-05 | 138 | HARRIS |
| Obrien | Increased reactive capability to 120MVAR | CNP | May-05 | 138 | FORT BEND |
| Watermill - Cedar Hill (2nd) 345 kV circuit | Install Watermill - Cedar Hill (2nd) 345 kV circuit | TXU ED | May-05 | 345 | DALLAS |
| Deepwater - Simson ckt.23 | Raised conductors to increase thermal ratings. | CNP | May-05 | 69 | HARRIS |
| Deepwater - South Channel ckt.16 | Raised conductors and upgraded limiting equipment at Deepwater to increase thermal ratings. | CNP | May-05 | 69 | HARRIS |
| Liggett system reactive capacitors | Install 138 kV capacitors | TXU ED | May-05 | 138 | DALLAS |
| South Mission, upgrade two 68 kV distributioin banks | Convert Bates to South Mission to South McAllen 69 kV line to 138 kV with 1590 ACSS reconnected to Frontera, and convert South McAllen and South Mission to 138 kV | AEP/TCC | May-05 | 138 | HIDALGO |
| Handley 138/69 kV autotransformer | Install a 150 MVA 138/69 kV autotransformer | TXU ED | May-05 | 138 | TARRANT |
| Airport 138-kV Substation | Relocate one 138/69-kV 60 MVA autotransformer from Loma Alta | BPUB | May-05 | 138 | CAMERON |
| Filter Plant 138-kV Substation | Convert Filter Plant Substation from 69-kV to 138-kV | BPUB | May-05 | 138 | CAMERON |
| Military Hwy 138-kV Substation | Facilitate the substation for a new 138-kV Circuit | BPUB | May-05 | 138 | CAMERON |
| Midtown 138-kV Substation | Convert Substation from 69-kV to 138-kV | BPUB | May-05 | 138 | CAMERON |
| FM 802 138-kV Substation | Convert Substation from 69-kV to 138-kV | BPUB | May-05 | 138 | CAMERON |
| Rockwall - E Richardson 138 kV line | Rebuild Rockwall - E Richardson 138 kV line | TXU ED | May-05 | 138 | ROCKWALL |
| White Point, add 2 series 10 Ohm reactors on Nueces Bay 138 kV lines | Install series reactors on both Nueces Bay to Whitepoint 138 kV circuits | AEP/TCC | May-05 | 138 | NUECES |
| Loma Alta 138-kV Substation | Facilitate the substation for a new 138-kV Circuit | BPUB | May-05 | 138 | CAMERON |
| Tomball | Increased reactive capability to 93.3MVAR | CNP | May-05 | 138 | HARRIS |
| Collin - Renner 138 kV line | Rebuild Collin - Renner 138 kV line for DCKT operation | TXU ED | May-05 | 138 | COLLIN |
| Morrison 138 kV breakers | Install two 138 kV bus tie breakers | TXU ED | May-05 | 138 | DALLAS |
| P.H. Robinson - Heights ckt.1 | Verified tie line from P.H. Robinson to TNMP tie point conductors clearance and upgraded limiting equipment at P.H. Robinson to increase thermal ratings. | CNP, TNMP | May-05 | 138 | GALVESTON |
| P.H. Robinson - ISP ckt.1 | Reconductored tie line from P.H. Robinson to TNMP tie point and upgraded limiting equipment at P.H. Robinson to increase thermal ratings. | CNP, TNMP | May-05 | 138 | GALVESTON |
| Cedar Hill Switch system reactive capacitors | Install 138 kV capacitors | TXU ED | May-05 | 138 | DALLAS |
| Rockport to Fulton #2, rebuild 69 kV Line | Rebuild Rockport to Fulton #2 69 kV line from 4/0 to 795 ACSR | LCRA/AEP | May-05 | 69 | ARANSAS |
| Texas City, PH Robinson-ISP-Greenbelt 138kV Line Reconductor | Reconductor 2-636 ACSR line running from PH Robinson to ISP to Greenbelt to 2-636 ACSS conductor | TNMP | May-05 | 138 | GALVESTON |
| Bates to Frontera, reconductor 138 kV line | Reconductor Bates to Frontera 138 kV line from 1272 ACSR to 1272 ACSS | AEP/TCC | May-05 | 138 | HIDALGO |
| P.H. Robinson - ISP -Greensbelt ckt.1 | Reconductored 2-636 ACSR tie line running from CNP tie point to ISP to Greenbelt to 2-636 ACSS conductor | CNP, TNMP | May-05 | 138 | GALVESTON |
| Martin Lake 345 kV breakers | Install two 345 kV bus tie breakers | TXU ED | May-05 | 345 | RUSK |
| Anna 345/138 kV autotransformer | Install a (2nd) 345/138 kV autotransformer (600 MVA) at Anna | TXU ED | May-05 | 345 | COLLIN |
| South Cross, add 3.6 MVAR cap | Add 259 MVAR of static and 75 MVAR of dynamic reactive support throughout the McCamey area | AEP/TNC | May-05 | 69 | CROCKET |
| Disconnected Choate 138KV Substation from CenterPoint Energy's system. | Disconnected customer owned Choate substation from CNP's ckt.79 Bayou - Orion and reconnected it to Bayou. | CNP | May-05 | 138 | HARRIS |
| North McCamey, add 2x28.8 MVAR caps | Add 259 MVAR of static and 75 MVAR of dynamic reactive support throughout the McCamey area | AEP/TNC | May-05 | 138 | UPTON |
| South Abilene, add 2-28.8 MVAR cap | Add 6-28.8 MVAR 138 kV capacitor banks in Abilene area | AEP/TNC | May-05 | 138 | TAYLOR |
| LCP - Pleasanton 138kV Reroute | Reroute part of the existing LCP-Pleasanton 138kV line | CPS | May-05 | 138 | BEXAR |
| East Munday, add 28.8 MVAR cap | Add 6-28.8 MVAR 138 kV capacitor banks in Abilene area | AEP/TNC | May-05 | 138 | CALLAHAN |
| Toyota 138 kV Substation | Install new 138 kV substation, loop into existing Braunig to Howard line. | CPS | May-05 | 138 | BEXAR |
| Santa Anna to Bangs, build 138 kV line | Convert Santa Anna to Brownwood 69 kV line to 138 kV with 795 MCM ACSR conductor | ? | May-05 | 138 | COLEMAN |
| Paris Switch - Brookston 138 kV line | Upgrade 138 kV line | TXU ED | Apr-05 | 138 | LAMAR |
| Copperas Cove and Clear Creek 138 kV capacitors | Install two 138 kV capacitor banks | TXU ED | Apr-05 | 138 | CORYELL |
| Monticello 345 kV breaker | Install one 345 kV bus tie breaker | TXU ED | Apr-05 | 345 | TITUS |
| T.H. Wharton - Gears ckt.95 | Verified conductors clearance to increase thermal ratings and upgrade in-series equipment at T.H. Wharton. | CNP | Apr-05 | 138 | HARRIS |
| MVEC Pharr to North Pharr, reconductor 138 kV line | Reconductor 138 kV MVEC Pharr to Hall Acres line from 336 to 795 ACSS conductor | AEP/TCC | Apr-05 | 138 | HIDALGO |
| McColl Road to North McAllen, reconductor/upgrade double circuit 138 kV Line | Reconductor North Edinburg to North McAllen 138/69 kV double circuit line with 795 ACSS conductor | AEP/TCC | Apr-05 | 138 | HIDALGO |
| Bentsen to South McAllen | Convert Bates to South Mission to South McAllen 69 kV line to 138 kV with 1590 ACSS conductor reconnected to Frontera, and conversion South McAllen and South Mission to 138 kV. Upgrade 69 kV line to 138 kV | SU | Apr-05 | 138 | HIDALGO |
| South Mission to Bentsen | Convert Bates to South Mission to South McAllen 69 kV line to 138 kV with 1590 ACSS conductor reconnected to Frontera, and conversion South McAllen and South Mission to 138 kV. Upgrade 69 kV line to 138 kV | SU | Apr-05 | 138 | HIDALGO |
| Baytown - EXXON ckt.66 | Raised conductors to increase thermal ratings | CNP | Apr-05 | 138 | HARRIS |
| Disconnect Cooper 69kV Substation from the system | Disconnected substation and deenergized ckt.19 H.O. Clarke - Cooper | CNP | Apr-05 | 69 | HARRIS |
| Comfort-Cico | Upgrade all terminal equipment on the Comfort(7155)-Cico(7151) 138kV transmission line to upgrade rating of line to 220MVA. | LCRA | Apr-05 | 138 | KENDALL |
| Eagle Mountain 345 kV breakers | Install two 345 kV breakers | TXU ED | Apr-05 | 345 | TARRANT |
| North Pharr, add 138 kV SS with temporary 138/69 kV auto | Convert Pharr to Weslaco SS to Harlingen SS 69 kV line to 138 kV from 4/0 to 795 ACSS and convert North Pharr to switching station | AEP/TCC | Apr-05 | 138 | HIDALGO |
| Toyota 138 kV Substation loop | Install new 138 kV substation loop into existing Braunig to Howard line. | CPS | Apr-05 | 138 | BEXAR |
| Relocate Tidal Generating Unit #2 | Relocated Gas Turbine Generating Unit #2 from Tidal to DIABOX. | CNP | Apr-05 | 138 | HARRIS |
| Construct Trinity Bay 138KV Substation | Looped substation into ckt.03 Cedar - Baytown | CNP | Apr-05 | 138 | CHAMBERS |
| Greens Bayou 138/69 kV autotransformer | Upgraded Autotransformer (A5) position to increase thermal ratings | CNP | Apr-05 | 138 | HARRIS |
| Santa Rosa Distribution, upgrade 2 transformers & distribution equipment | Convert Pharr to Weslaco SS to Harlingen SS 69 kV line to 138 kV from 4/0 to 795 ACSS and convert North Pharr to switching station | AEP/TCC | Apr-05 | 138 | HIDALGO |
| Veterans - Gears ckt.67 | Verified conductors clearance to increase thermal ratings. | CNP | Apr-05 | 138 | HARRIS |

Status of future major transmission projects (345 kV)

Additional detailed project information is contained in the August 1 Transmission Project Information Tracking workbook posted in the “Operations and System Planning” data area on the internet.  See links at end of this document for address.

| Project Title | Project Description | Transmission Owner | Projected In-Service Date | kV | Location County |
| --- | --- | --- | --- | --- | --- |
| Watermill - W. Levee (2nd) 345 kV circuit | Install Watermill - W. Levee (2nd) 345 kV circuit | TXU ED | Oct-05 | 345 | DALLAS |
| Zorn Auto | Replace the 600MVA Zorn Auto 2 with a 478MVA auto (7045-7180) | LCRA | Oct-05 | 345 | GUADALUPE |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A1) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| Bellaire 345/138kV autotransformer | Upgrade Autotransformer (A4) position to increase thermal ratings | CNP | Nov-05 | 345 | HARRIS |
| T.H.Wharton - Jewett ckt.1 | Upgrade tie lines from TH Wharton to TXU tie point to increase thermal ratings to 1450 MVA by raising conductors and upgrading limiting equipment at TH Wharton | CNP | Dec-05 | 345 | HARRIS |
| Laredo BTB Station, Rebuild and convert line to CFE to 230 kV. | Construct 150 MW CFE asynchronous interconnection and 138 kV switching station. | AEP/TCC | Mar-06 | 230 | WEBB |
| Rio Hondo, add 345/138 kV auto | Rebuild La Palma to Rio Hondo 138 kV with 2-795 ACSS, double circuit capable and add 345/138 kV autotransformer at Rio Hondo | AEP/TCC | Apr-06 | 345 | CAMERON |
| Rio Hondo, add 345/138 kV auto | Rebuild La Palma to Rio Hondo 138 kV with 2-795 ACSS, double circuit capable and add 345/138 kV autotransformer at Rio Hondo | AEP/TCC | Apr-06 | 345 | CAMERON |
| Temple Pecan Creek Switching Station | Establish Temple Pecan Creek Switching station and install a 600 MVA 345/138 kV autotransformer. | TXU ED | May-06 | 345 | BELL |
| Venus - Sherry 345 kV line | Construct Venus - Sherry 345 kV line | TXU ED | May-06 | 345 | ELLIS |
| W. Levee - Norwood 345 kV line | Construct W. Levee - Norwood 345 kV line | TXU ED | May-06 | 345 | DALLAS |
| Venus - Liggett 345 kV line | Construct Venus - Liggett 345 kV line | TXU ED | May-06 | 345 | ELLIS |
| Venus - Johnson Switch 345 kV line | Upgrade existing 345 kV line | TXU ED | May-06 | 345 | ELLIS |
| Valley 345/138 kV autotransformer | Replace existing 450 MVA 345/138 kV autotransformer with a 600 MVA autotransformer | TXU ED | May-06 | 345 | FANNIN |
| Jewett - TH Wharton 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU ED | May-06 | 345 | LEON |
| Jewett - Tomball 345 kV line upgrade | Upgrade tie lines from Jewett to TXU Electric Delivery tie point to increase thermal ratings to 1450 MVA or above. | TXU ED | May-06 | 345 | LEON |
| Ben Davis Sub: Add 345 terminal and install a 2nd 345-138 autotransformer | Expand 345 ring bus and add a 2nd 345-138 kV autotransformer | TMPA | May-06 | 345 | DALLAS |
| Nelson Sharpe, add 345/138 kV autotransformer | Construct Nelson Sharpe 345/138 kV substation in the Lon Hill to Rio Hondo 345 kV line and add a phase-shifting transformer at Nelson Sharpe in Davis 138 kV line | AEP/TCC | May-06 | 345 | KLEBERG |
| Greens Bayou 345/138 kV autotransformer. | Replace 400MVA Autotransformer (A1) at Greens Bayou with 800MVA and swap autotransformer (A1) and (A2) 138kV leads. | CNP | Jun-06 | 345 | HARRIS |
| Addicks 345/138 kV autotransformer. | Add second 600MVA Autotransformer (A2) at Addicks. | CNP | Jun-06 | 345 | HARRIS |
| Kendall-CPS Cagnon 345-kV line | Construct a 345 kV bundled 1590 ACSR line (approximately 45 miles) between Kendall (7046) and Cagnon (5056) | LCRA / CPS | Jun-06 | 345 | BEXAR |
| Clear Springs | Add a new 345/138 kV 478 MVA auto-transformer at the Clear Springs substation(7050). The existing 345 kV bus at the Clear Springs will be converted from a ring bus configuration to a double-bus double-breaker configuration. Upgrade the 7.2-mile Clear Springs(7680)-Geronimo(7604)-Seguin(7228) 138 kV transmission line (T-264) from 336 ACSR to Bundled 795 ACSR double circuit capable. Upgrade the 7.2-mile Clear Springs(7680)-Freiheit(7462)-Hortontown(7175)-Comal(7176) 138 kV transmission line (T-264, T-394, and T-119) from 336 ACSR to Bundled 795 ACSR double circuit capable. | LCRA | Jun-06 | 345 | GUADALUPE |
| Bellaire 345/138 kV autotransformer. | Add 800MVA autotransformer (A2) at Bellaire, swap ckt.05 to Jeanetta and ckt.09 to Brays at Bellaire and upgrade fault duty rating of Bellaire North 138kV bus to at least 63kA. | CNP | Jun-06 | 345 | HARRIS |
| Tomball two 345/138 kV autotransformers. | Replace two 600MVA Autotransformers (A1) and (A2) at Tomball with two 800MVA autos. | CNP | Jun-06 | 345 | HARRIS |
| Skyline - Replace 345kV Autotransformer #2 & #4 | Replace the two 480 MVA autotransformers(#2 & #4) with one 600 MVA autotransformer. | CPS | Jul-06 | 345 | BEXAR |
| Elm Creek Substation | Install new 345 kV switching station at the intersection of the existing 345kV lines from STP-Skyline, STP-Hill Country, and both lines from Marion to San Miguel. | CPS | Oct-06 | 345 | GUADALUPE |
| Elm Creek Reroute | Reroute 345kV lines (STP- Skyline, STP- Hill Country, Marion, San Miguel) to connect with future Elm Creek Switchyard | CPS | Oct-06 | 345 | GUADALUPE |
| Jacksboro Switch - W. Denton 345 kV line | Construct Jacksboro Switch - W. Denton 345 kV line | TXU ED | Dec-06 | 345 | JACK |
| Sandow 345/138 kV autotransformer | Install second 345/138 kV autotransformer | TXU ED | Dec-06 | 345 | MILAM |
| Odessa EHV 345/138 kV 300 MVA autotransformer replacement | Replace existing 300 MVA 345/138 kV autotransformer with a 450 MVA autotransformer | TXU ED | Dec-06 | 345 | ECTOR |
| Paris Switch - Anna 345 kV line | Construct Paris Switch - Anna 345 kV line | TXU ED | Dec-06 | 345 | LAMAR |
| P.H. Robinson 345/138 kV autotransformer. | Replace 500MVA Autotransformer (A3) at P.H. Robinson with 600MVA. | CNP | Dec-06 | 345 | GALVESTON |
| West Denton Sub: Construct 345 bus, add 2 line terminals and add a 2nd 345 auto | Expand 345 kV breaker and a half substation with line terminals for the Jacksboro line and N.W. Carrollton line. Add a 2nd 345-138 kV autotransformer | TMPA | Dec-06 | 345 | DENTON |
| DeCordova - Benbrook 345 kV line upgrade | Upgrade capacity of line | TXU ED | May-07 | 345 | HOOD |
| DeSoto 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at DeSoto | TXU ED | May-07 | 345 | DALLAS |
| Plano Tennyson 345/138 kV autotransformer | Install a 600 MVA 345/138 kV autotransformer at Plano Tennyson | TXU ED | May-07 | 345 | COLLIN |
| Trinidad - Richland 345 kV line | Upgrade Trinidad - Richland 345 kV line | TXU ED | May-07 | 345 | HENDERSON |
| Venus - Cedar Hill 345 kV line | Upgrade existing 345 kV line | TXU ED | May-07 | 345 | ELLIS |
| Ben Davis - Royse 345 line: Reconductor | Reconductor 17 miles of line to increase capacity | TMPA | May-07 | 345 | Dallas |
| WAP 345 kV sub. | Upgrade fault duty rating of WAP 345 kV to at least 63kA | CNP | Jun-07 | 345 | FORT BEND |
| Smithers 345 kV sub. | Upgrade fault duty rating of Smithers 345 kV to at least 63kA | CNP | Jun-07 | 345 | FORT BEND |
| STP - Dow ckt.18 and ckt.27 | Replace 2000 Amp equipment on both circuits from STP to DOW. | CNP | Jun-07 | 345 | MATAGORDA |
| Spruce to Skyline 345kV 2nd Circuit | Build 2nd 345 kV line from Spruce to Skyline substation | CPS | Jun-07 | 345 | BEXAR |
| Hillje Switching Station | Build a new 345 kV Hillje substation. Loop ckt.1 STP-Holman into the new substation. | CNP | Jun-07 | 345 | WHARTON |
| STP - Hillje ckt. | Build new 345 kV line from STP to Hillje. | CNP | Jun-07 | 345 | MATAGORDA |
| WAP - Hillje ckt. | Build new 345 kV double circuit line from WA Parish to Hillje. | CNP | Jun-07 | 345 | FORT BEND |
| Second Whitney 345/138 Autoitransformer | Install second 450MVA 345/138KV auto at Whitney | Brazos | Jun-08 | 345 | BOSQUE |
| Spruce 2 Power Plant loop | Install new 345kV connection between Spruce 2 and CPS Energy grid. | CPS | Jun-08 | 345 | BEXAR |
| Increase CNP 345/138 kV autotransformer capacity | Add several 800 MVA autotransformers in the CNP transmission system | CNP | Dec-08 | 345 | HARRIS/CHAMBERS/FORT BEND/GALVESTON/BRAZORIA |
| West Denton - NW Carrollton 345 kV circuit | Add second Circuit from West Denton to NW Carrollton | TXU ED/TMPA | May-09 | 345 | DENTON |
| Skyline - Install a third 345kV Autotransformer | Install one 600 MVA autotransformer. | CPS | May-09 | 345 | BEXAR |
| Second Concord 345/138 Autotransformer | Install second 300MVA 345/138KV auto at Concord | Brazos | Jun-09 | 345 | JOHNSON |
| Cagnon to Hillcountry 345kV 2nd Circuit | Build 2nd 345 kV line from Cagnon to Hill Country substation | CPS | Jun-09 | 345 | BEXAR |
| Hill Country to Skyline 345 kV 2nd Circuit | Build 2nd 345 kV line from Hillcountry to Skyline substation | CPS | Jun-09 | 345 | BEXAR |
| Dansby to Twin Oak 345 kV | Design and build a double circuit 345 that will tie into the existing TMPA Gibbons to Twin Oaks line | BTU | Jul-09 | 345 | BRAZOS |
| 2nd Lewisville Auto | Install (2nd) 345/138 kV autotransformer at Lewisville station | Brazos | Dec-09 | 345 | DENTON |
| Laredo Lobo, build 345 kV for 675MVA autotransformer | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/TCC | Mar-10 | 345 | WEBB |
| Liggett - Trinity Switch 345 kV line | Construct Liggett - Trinity 345 kV line | TXU ED | May-10 | 345 | DALLAS |
| Trinity Switch 345/138 kV autotransformer | Create Trinity Switch and install a 600 MVA 345/138 kV autotransformer | TXU ED | May-10 | 345 | TARRANT |
| Hutto Switch - Salado Switch 345 kV line | Construct Hutto Switch - Salado Switch 345 kV line | TXU ED | May-10 | 345 | WILLIAMSON |
| Laredo Lobo to San Miguel, build 345 kV line | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and conver | AEP/STEC | May-10 | 345 | WEBB |
| Hutto Switch 345/138 kV autotransformer | Create 345 kV switching station and install a 345/138 kV autotransformer | TXU ED | May-10 | 345 | WILLIAMSON |
| Zorn/Clear Springs-Harris Branch-Hutto Switch 345-kV line | Construct a 345 kV DC 2x1590 ACSR line between Zorn/Clearsprings and Hutto Switch and other ONCOR and AE projects | LCRA | Jun-10 | 345 | WILLIAMSON |
| Harris Branch 345/138kV autotransformer | Install a 345/138kV autotransformer at Harris Branch substation | Austin Energy | Dec-10 | 345 | TRAVIS |
| Northeast Metro 345/138kV autotransformer & Northeast Metro 138kV circuit to East and Techridge Subs. | Install a 345/138kV autotransformer at Northeast Metro substation. Cut-in the existing East to Techridge 138kV circuit to establish the 138kV East to Northeast Metro and 138kV Northeast Metro to Techridge circuits | Austin Energy | Dec-10 | 345 | TRAVIS |
| Frontera, add SS with 345/138 kV autotransformer | Addition North Edinburg to Frontera to South McAllen 345 kV line with bundled 1590 ACSR conductor and double circuit capable structures and 345/138 kV substation at Frontera | AEP/TCC | May-11 | 345 | HIDALGO |
| N Edinburg to Frontera, build 345 kV dbl crct Line | Addition North Edinburg to Frontera 345 kV line with bundled 1590 ACSR and double circuit capable structures and 345/138 kV substation at Frontera | LCRA/AEP | May-11 | 345 | HIDALGO |
| Laredo Lobo to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Frontera to Rio Bravo, new 345 kV line | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Rio Bravo, 138 kV SS with 345/138 kV autotransformer | Construct 345 kV line from Highway 59 to Rio Bravo to Frontera and add 345/138 kV substation at Rio Bravo with 345/138 kV autotransformer | AEP/TCC | May-11 | 345 | WEBB |
| Loma Alta - Ranchito or la Palma 345-kV line | Install 345-kV line from Loma Alta to La Palma or Ranchito | BPUB | Jun-15 | 345 | CAMERON |
| Loma Alta - Rio Hondo 345-kV line | Install 345-kV line from Loma Alta to Rio Hondo | BPUB | Jun-15 | 345 | CAMERON |
| Loma Alta 345kV station and autotransformer | Construct a 345 substation and connect to the existing Loma Alta 138 substation. | BPUB | Jun-15 | 345 | CAMERON |
| Rio Hondo to Ranchito, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345 kV line | AEP/TCC |  | 345 | CAMERON |
| Ranchito, new SS with 345/138 kV autotransformer | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| Ranchito to South McAllen, new 345 kV line | Construct 345 kV line from Rio Hondo to Ranchito and add 345/138/69 kV substation adjacent to existing Cavazos 69 kV substation with 600 MVA 345/138 kV autotransformer. Build 345/138/69 kV station and autotransformer | AEP/TCC |  | 345 | CAMERON |
| North McCamey to Twin Buttes 345 kV Line | 12/02 plan recommends the construction of a 345kV 2x1590 ACSR line between North McCamey and Twin Buttes | LCRA/AEP |  | 345 | UPTON |
| North McCamey - Odessa 345 kV Line | 12/02 plan recommends the construction of a 345 kV 2x1590 ACSR line between North McCamey and Odessa and 2x600 MVA autotransformers at North McCamey | LCRA/AEP |  | 345 | UPTON |
| North McCamey Three 345/138 kV autotransformers | 12/02 plan recommends the addition of Three 345/138kV autotransformers North McCamey | LCRA/AEP |  | 345 | UPTON |
| Frontera to South McAllen 345 kV line | Construct a 345 kV transmission line from Frontera to South McAllen. | LCRA/AEP |  | 345 | HIDALGO |
| South McAllen, new SS with 345/138 kV autotransformer | Construct a 345 kV substation south of South McAllen cut into the South McAllen to Hidalgo 138 kV line and install a 345/138 kV autotransformer | AEP/TCC |  | 345 | HIDALGO |

Status of active generation interconnection requests

Additional detailed generation interconnection information and impact is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the internet.  See links at end of this document for address.

| PUBLIC PROJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | SiteName |  | Status |  | County |  | Region |  | Fuel |  | In Service Date |  | MW into Grid |  | Notes |  |
| 04INR0015 | Buffalo Gap 1 and 2 |  | Interconnect Agreement |  | Taylor |  | West |  | Wind |  | Oct-05 |  | 240 |  | 120 MW in 2005, 120 MW in 2006 |  |
| 04INR0020 | WKN Wind 1 Snyder |  | Interconnect Agreement |  | Scurry |  | West |  | Wind |  | Dec-05 |  | 60 |  |  |  |
| 05INR0010 | Jack County Generation Facility |  | Interconnect Agreement |  | Jack |  | North |  | Gas |  | Dec-05 |  | 700 |  | testing 6/1/05, commercial 12/1/05 |  |
| 06INR0008 | Big Spring Carbon Plant |  | Interconnect Agreement |  | Howard |  | West |  | Waste heat |  | Apr-06 |  | 12 |  |  |  |
| 03INR0034 | Silver Star Project |  | Interconnect Agreement |  | Erath |  | West |  | Wind |  | Jun-06 |  | 225 |  | In two phases |  |
| 05INR0018 | Horse Hollow 2 |  | Interconnect Agreement |  | Taylor |  | West |  | Wind |  | Jun-06 |  | 127 |  | Second of two phases |  |
| 04INR0011 | Mesquite Wind Farm 1 |  | Interconnect Agreement |  | Shackelford |  | West |  | Wind |  | Nov-06 |  | 200 |  |  |  |
| 05INR0015 | Gulf Wind |  | Public Letter |  | Kenedy |  | South |  | Wind |  | Sep-07 |  | 1,200 |  | In four phases |  |
| 06INR0016 | Dow 9 |  | Interconnect Agreement |  | Brazoria |  | South |  | NG |  | Oct-06 |  | 0 |  |  |  |
| 01INR0028 | Orion Delaware Mountain Wind Farm |  | Interconnect Agreement |  | Culberson |  | West |  | Wind |  | Dec-07 |  | 175 |  |  |  |
| 06INR0006 | Cobisa-Greenville |  | Public Letter |  | Hunt |  | North |  | Gas |  | May-08 |  | 1,750 |  |  |  |
| 09INR0002 | J K Spruce 2 |  | Interconnect Agreement |  | Bexar |  | South |  | Coal |  | Aug-09 |  | 750 |  |  |  |
| 10INR0002 | Hugo Plant |  | Public Letter |  | Choctaw, OK |  | North |  | Coal |  | Dec-10 |  | 500 |  |  |  |
|  |  |  |  |  |  |  |  |  | Totals |  |  |  | 5,940 |  |  |  |
| PROJECTS INTO OPERATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INR # |  | SiteName |  |  | County |  | Region |  | Fuel |  | In Service Date |  | MW into Grid |  |  |  |
| ACTIVE GENERATION INTERCONNECTION REQUESTS BEING PROCESSED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | North |  | South |  | West |  | Total |  |  |  |  |
| Security Screening Study |  |  |  |  |  | 0 |  | 1 |  | 1 |  | 2 |  |  |  |  |
| SSS Completed |  |  |  |  |  | 1 |  | 2 |  | 7 |  | 10 |  |  |  |  |
| Full Interconnect Study |  |  |  |  |  | 8 |  | 6 |  | 10 |  | 24 |  |  |  |  |
| FIS Completed |  |  |  |  |  | 1 |  | 0 |  | 1 |  | 2 |  |  |  |  |
| Interconnect Agreement Completed (Includes public letters) |  |  |  |  |  | 3 |  | 3 |  | 7 |  | 13 |  |  |  |  |
| Capacity for Grid, MW |  |  |  |  |  | 5,804 |  | 3,940 |  | 5,641 |  | 15,385 |  |  |  |  |
| Wind MW (under development) |  |  |  |  |  | 240 |  | 2,360 |  | 4,454 |  | 7,054 |  |  |  |  |

Generation Currently Under RMR Contract in ERCOT (as of 9/1/05)

| Unit | Capacity (Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date |
| --- | --- | --- | --- | --- |
| BM Davis 2 | 356 | Under Contract | 1/1/05-12/31/05 | Under Review |
| JL Bates 1 & 2 | 183 | Under Contract | 1/1/05-12/31/05 | 3Q 2006 |
| La Palma 4, 5, 6, &7 | 249 | Under Contract | 1/1/05-12/31/05 | 1Q 2006 |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/05-12/31/05 | 3Q 2010 |
| PH Robinson 2 | 461 | Under Contract- 90 Day Termination Notice Sent | 5/17/05-5/16/06 | 10/29/05 |
| Total MW Under RMR: | 1,421 |  |  |  |

Studies underway or planned to be started within Transmission Services

- 345/138 kV autotransformer outage congestion

  - Study is 90% complete, final data analysis and report preparation remaining

- BM Davis Unit 2 RMR exit strategy review

  - Verify the planning model against the operational model that was used by Siemens PTI for the study ‘Transient Voltage Stability Analysis of the Corpus Christi Region’

  - The two models were compared and all discrepancies were resolved

    - Higher demand was observed in the operations cases than modeled in the planning cases

  - At ERCOT's request, AEP is preparing the transmission construction and outage plan for the completion of the Nelson Sharpe switching station.  This information will be used to determine the timeline for the exit of the B.M. Davis RMR agreement.

- Bryan/College Station study

  - Draft report prepared and will be released soon

- DFW/NE 2009 congestion study has been rolled into (replaced by) the Pre-Nodal Transmission Improvement Study

- DFW voltage stability study impact of “selected contingencies” for evaluation – quick examination of multiple circuit contingency outages and relative impact on voltage stability

- Dynamic (transient and voltage stability) limit evaluation of 2005 CSC/CM zonal transfers

- ERCOT/SPP joint study of interconnection feasibility

  - Thermal steady-state analysis of four potential DC-tie locations is complete

  - Highest transfer capability location will be used for economic analysis

- JL Bates Units 1 and 2, and La Palma Units 4, 5, 6, and 7 RMR Exit Strategy - review for possible exit in 2006

- Killeen and Temple area study has been rolled into (replaced by) the Pre-Nodal Transmission Improvement Study

- Load stability modeling project - Phase II (EPRI Solutions) is starting

  - ROS and TAC endorsed/supports this effort

  - ROS encouraged transmission owners to get involved in the project to improve stability modeling and support reliability studies

- LOLP/Reserve Margin Study - RFP for study to update 2002 study will be issued

- Lower Rio Grande Valley continue efforts to maintain reliable service

  - Lower Rio Grande Valley 2010 voltage stability study

  - Lower Rio Grande Valley 2010 transient event study

- Net Dependable Capability Testing Data - ERCOT staff efforts are ongoing to determine the fidelity of and best practices in planning for the generator data that is sent to ERCOT compliance

- NOIE load zones in nodal environment study- determination of impacts for PUCT

- October 1 report work is underway and includes the following

  - Graphics being developed

  - Outline elements completed

  - Summary of congestion costs being developed

  - Documentation of ERCOT operational improvements being developed

  - Projection of marginally congested elements completed

- Pre-Nodal Transmission Improvement Study initiated at request of PUCT

  - Identify and quantify long lead time transmission projects across the entire ERCOT system that will reduce congestion for the implementation of a nodal market in 2009

  - Process and scope for this project has been sent to the all the TDSP’s and Regional Planning Groups

  - Hosted conference calls to address questions about the process and scope of the project

  - TDSP support major is a element in completing this effort

- Rim Rock to Goat Creek 138 kV Switching Station and transmission line project was submitted by the Lower Colorado River Authority for South Regional Planning Group review on August 10th

- SPS approval procedure revisions

  - Streamline the process so that minor SPS additions and modifications can be reviewed in expedited manner

  - OGRR 172 recommendations being incorporated

- Steady State WG base case (planning) and network model branch data (operations) follow up comparison was conducted in August. Another follow up comparison will be conducted around September 15

- System Protection WG 2005 future year short circuit base cases for the years 2006 to 2009 are currently being built

- Transient Voltage Dip analysis of the Corpus Christi area, work performed by Siemens/PTI in cooperation with Flint Hills, AEP TCC and ERCOT System Planning - public report completed and posted

- Transmission Loss Factor 2006 calculations - underway

- Transmission Project Information Tracking (TPIT) - investigate moving to online database with on demand changes and reporting

- Transmission Services will be looking at how to incorporate biennial unit reactive test data into the Steady State WG base cases for more accurate modeling

- Utility Wind Interest Group (UWIG) wind farm stability modeling effort – underway supporting use group efforts

- West-North transfer limit study has been rolled into (replaced by) the Pre-Nodal Transmission Improvement Study and a larger wind impact/integration study

  - RFP under development and will be released in September

- Other ongoing work

  - Black start testing - staff support and witness of tests

  - Enhance dynamic data models

  - Enhance fidelity of contingency files and testing

  - Enhance fidelity of planning base cases to better match real-time operating environment

  - Enhance generation data gathering efforts and model improvements

  - Load modeling improvements and improvements to base case modeling

Studies that have been completed by Transmission Services and posting location

- Assisted operations in developing a procedure to electronically send the Generation Reactive Capability testing data to the TDSP to improve the reactive modeling in the planning cases

- Sierra Vista (AEP) project, submitted by American Electric Power, was accepted by the South Regional Planning Group on August 8th

- Steady State WG base cases have been revised with latest August TPIT updates and posted

- Valley and North Lake TXU generation possible return to market in 2006 - provided support to operations review

Upcoming Events

- Dynamics WG meeting scheduled for September 8-9, 2005

- NERC PC Meeting, September, 14 & 15, Dallas

- NERC OC TS Meeting, September 20 & 21, Washington DC

- NERC MMWG meeting in October 25 & 26, San Antonio

  - ERCOT Steady State WG Procedural Manual needs work to bring it into NERC compliance

- Pre-Nodal Transmission Improvement Study

  - Conference calls and/or meetings will be held at appropriate points in the study

- Steady State WG 2006 Data Set B will begin in September and be completed in November

Other Issues

- Continuing to work with ERCOT Compliance in an attempt to ensure that future compliance surveys (e.g. UFLS) obtain data in a format that is more readily incorporated into system modes

- National Renewable Energy Laboratory (NREL) is willing to perform stability studies together with ERCOT System Planning to validate the dynamic models of wind farm, subject to the availability of disturbance data for a transient event in the West Texas network

- Responding to NERC recommendations - ROS Dynamics WG will simulate an actual event to test dynamic models.  DWG is reviewing an event to assess its suitability to the NERC recommendation scope.  System planning staff will provide support to the study

Things Transmission Services feels TDSP/TO planning personnel should be paying attention to

- Continue to support the model and contingency file validation efforts between Planning and Operations

- Differences in generation Mvar capability between planning and operations models

- Ensure transmission additions are completed in a timely manner and accurate system operations model updates are submitted when projects are completed

- Terminal equipment upgrades to increase utilization of existing conductors

- Transition to the nodal market and the demands that is poses on planning and operation modeling

Interesting observations

•	Total installed and new generation with interconnection agreements for wind power projects in the greater Abilene/Sweetwater area is now greater than 1,300 MW, almost double the installed capacity in the McCamey area.  ERCOT operations and planning staff will be monitoring the area as new wind farms come online to determine possible impacts.

Future issues

- Generation deficiency for SSWG 2006 Data Set B planning bases

- Generator reactive capability data, planning and operations differences

- Reactive load (power factor) modeling in planning and operations

- Supporting and participating in ERCOT Network Model Management System project that integrates the planning and operations models into one database

Internet Links

- Operations and System Planning Data area

  - http://www.ercot.com/tmaps/Login.cfm

  - Major data folders of interest in this area

    - Power System Planning Charter & Processes

    - October 1 Report to PUCT Annual

    - CSC CM Zone 2005 Data Files

    - Capacity, Demand, and Reserve Reports

      - Report on generation capacity, projected demand and reserves

    - Contingency Information – planning

    - Demand and Energy Reports (D&E) Monthly Actuals

      - Monthly actual demand and energy report

    - EIA-411 DOE Regional Electricity Supply and Demand Projections

    - Generation Project Interconnection Information

      - Public new and existing generation projects in ERCOT since 1996

    - Maps of ERCOT Transmission System

    - Operations Engineering Procedures

    - Operations Model Data

      - System Operations Base Case updated often

    - Regional Planning Group NORTH

    - Regional Planning Group SOUTH

    - Regional Planning Group WEST

    - Reliability Must-Run (RMR) Studies

    - Special Protection Schemes (SPS) Information

    - Steady State Base Case Info & Old Data

    - Steady State Power Flow Base Cases 2005 Data Set A (2005 eight seasonal cases)

    - Steady State Power Flow Base Cases 2005 Data Set B (2006-2010 cases)

    - System Protection Short Circuit Data

    - TNT Cost Benefit Study Data

    - Transmission Project & Information Tracking (TPIT)

    - Voltage Security Study of ERCOT System

    - Wind Stability Modeling ERCOT Project