1	Purpose	1

2	Transition Planning Principles	2

3	Transition Plan Management	3

4	Initial Timeline	4

5	Transition Plan Tracks	4

5.1	Systems Specification, Procurement and Development Track – ERCOT	5

5.2	System Procurement and Development Track – Market Participant	6

5.3	Market Training Track	6

5.4	System Testing and Nodal Market Implementation Track	8

5.4.1	Data and Telemetry Testing Requirements	8

5.4.2	State Estimator Implementation	10

5.4.3	Real-Time Network Security Analysis Implementation	11

5.4.4	Security Constrained Economic Dispatch	11

5.4.5	Trial Operation of Congestion Revenue Rights Auction	12

5.4.6	Trial Operation of Day Ahead Market	12

5.4.7	Trial Operation of Reliability Unit Commitment	13

5.4.8	Load Frequency Control Testing	13

5.4.9	168 Hour Test and Trial Real Time Settlement	13

5.4.10	Transmission Element and Resource Outages	14

5.4.11	Real Time Operation and Settlement	14

5.4.12	Day-Ahead Market and Reliability Unit Commitment Start-Up	Error! Bookmark not defined.

5.4.13	Performance Measurement Systems	15

5.4.14	Market Information Systems	15

5.4.15	Supplemental Ancillary Services Market	15

6	Market Readiness	15

6.1	Market Readiness Criteria	15

6.2	Market Participant and ERCOT Personnel Training	16

6.3	Market Readiness Declaration	16

# 1	Purpose

(1)	The purpose of this document is to describe and outline the  transition from the current ERCOT zonal wholesale market structure to the ERCOT nodal wholesale market structure.  This document sets forth principles that should be applied throughout the transition process by ERCOT and the Market Participants, and it identifies the roles and responsibilities of ERCOT and Market Participants during the transition process.  The term “Market Participants” includes:  QSEs, LSEs, Resource Entities, TSPs, DSPs, TDSPs, OPC and any other Entities engaged in any activities governed by the ERCOT Protocols.  This document also divides the tasks and subtasks necessary to a successful transition to the nodal market into four major tracks. Additionally, this document develops an initial timeline for each of the four major tracks.  These timelines, which may be adjusted in the early planning stages of the transition process, include major milestones, including input opportunities and deadlines for Market Participants and deadlines for ERCOT.  This document does not address any interim changes to the current system.

- This document also addresses the development of the Market Readiness Criteria that must be satisfied before the nodal market is implemented for operational and settlement purposes.  This document  incorporates by reference all the concepts in the System Migration white paper.  In the event that there is a conflict with the System Migration white paper, this document controls.

(3)	This plan is intended to assist in an orderly transition that provides:

a. Certainty about market structure details at the earliest possible time; 
b. Assurance of  execution of the market transition on time and within budget.

# 2	Transition Planning Principles

The Transition Plan must incorporate the following principles:

(a)	Market Participants must have the opportunity to review and comment on documents at  critical points in the transition process. ERCOT must consider, but is not required to accept, those comments. ERCOT will make the  final decision on the documents, subject to the TAC Transition Plan Task Force (TPTF) approval of Requirement documents as required in the next paragraph.  [Somewhat awkward, not sure what this is trying to say.]  After the TPTF approves Requirements, Market Coordination Teams (MCT) will be formed by ERCOT to give Market Participants the opportunity to review and comment on Conceptual and Detail System Design documents, develop Readiness Criteria, MP test scenarios, and certify market readiness.  Each MCT would consist of ERCOT and key Market Participant business and technical experts.  ERCOT would chair the group.  Each MCT may be asked to co-locate with ERCOT staff during critical development activities.

(b)	The TPTF has the right to approve or reject any documents or activities in the transition process that raise issues of compliance with the nodal Protocols.

(c)	No part of the nodal operations may start until (a) the appropriate MCT has certified the completion of the Market Readiness Criteria related to that part of nodal market operations and (b) cutover for that part of nodal operations has been approved by both the TAC and ERCOT Board.

(d)	Market Participant knowledge of the status of the transition process is very important, and ERCOT shall establish a process for providing that information to Market Participants.

(e)	Market Participant training is very important, and ERCOT shall establish early and comprehensive training programs for Market Participants that will be completed in a timely manner.

(f)	ERCOT shall provide Market Participants with the specifications needed for systems interfaces, as soon as they are available.

# 3	Transition Plan Management

(1)	ERCOT Staff has the overall responsibility to carry out the transition from the current zonal market to the nodal market, including the project budget and timeline.

(2)	Each Market Participant has the responsibility to carry out its functions in the Transition Plan and to provide ERCOT with timely information about the status of its efforts.

(3)	ERCOT shall create a Project Plan that follows an Outline approved by TAC that includes more detail about systems procurement and development, Market Participant trainingand an ERCOT and Market Participant testing plan. The Project Plan shall identify major milestones and the timeframes affecting system development by ERCOT and by Market Participants.

(4)	Market Participant input to the Business Requirements phase of the Project Plan will be provided through the TPTF.  The Texas Nodal Team, upon completion of its tasks and the filing of the Protocols with the Public Utility Commission of Texas, shall be dissolved.  The primary mission of the TPTF is to assist ERCOT and serve as a subject matter resource to help ERCOT ensure consistency between  the requirements of the nodal Protocols and system design and implementation.

(a)	The TPTF will consist of market participants from each of the seven market segments and an ERCOT representative. Each market participant will acknowledge its willingness to participate in the TPTF prior to the first TPTF meeting.  TPTF members are expected to be present at each TPTF meeting.  To be eligible to review requirements and design documents, each member of the TPTF may be required to sign nondisclosure agreements with ERCOT to the extent required by the vendor/s.

(b)	ERCOT shall chair and provide administrative and technical support to, the TPTF.

(c)	The TPTF shall meet as needed. Meetings are open to all of the following:

(i)	ERCOT corporate members;

(ii)	PUCT Staff;

(iii)	the Independent Market Monitor (IMM)

- (iv)	OPC Staff; and

(v)	TAC Residential Consumer members

(d)	Attendance at sessions involving confidential or proprietary information will be limited 	to those who have signed an appropriate nondisclosure agreement.

- (e)	Option 1 (Calpine): The passage of any voting matters before the TPTF  must be by two-thirds or more of the sum of all fractional votes cast.  A quorum consists of four segments and is required for decision-making.

Option 2 (ERCOT): A quorum of the TPTF consists of representation by at least four market segments and is required for decision-making.

Each market segment shall have one vote.  Except for the Consumer segment, the fractional vote for each Member shall be equal to one divided by the number of Members present and voting in their segment. For example, if a segment has ten Members present and voting, then each Member would have a fractional vote equal to one-tenth.

The Consumer segment will be grouped into three sub-segments - Residential, Commercial and Industrial. Members in each sub-segment shall have fractional votes adding up to one divided by the number of sub-segments present and voting. The fractional vote for each Member shall be based on the number of Members present and voting in their sub-segment. For example, if all three sub-segments are present and voting and if a sub-segment has three Members present and voting, then each Member of that sub-segment would have a fractional vote equal to one-ninth.

Decisions of the TPTF must be by two-thirds or more of the sum of all fractional votes.   If the TPTF cannot reach the required passing vote of the members present on any issue voted on, then the TPTF will send the issue to TAC for resolution.  If  a timely answer is not received from TAC, then ERCOT Staff will determine how to proceed.  All decisions of the TPTF may be appealed to TAC.

(f)	The TPTF shall provide the TAC with a report of its activities at each regularly-scheduled TAC meeting.  ERCOT must sponsor routine information sharing meetings open to all Market Participants to report the progress of, and changes to, the Project Plan.

# 4	Initial Timeline

The period of time beginning with a decision to proceed, until a yet to be determined date following the start of nodal market operations and settlement.

# 5	Transition Plan Tracks

The Transition Plan must include the following tracks:

- Systems Specification, Procurement and Development – ERCOT

- Systems Procurement and Development – Market Participant

- Market Training – ERCOT and Market Participant

- Systems Testing and Nodal Market Implementation

## 5.1	Systems Specification, Procurement and Development Track – ERCOT

(1)	This track includes tasks related to systems specification, procurement, and development of RFPs, subsequent statements of work, design documents, standards for interface with Market Participants, and building the systems.  ERCOT shall manage this track, including without limitation the RFP process, vendor selection, contract management, financial settlement with vendors, the development and specification of communications interfaces and communication protocols, the development of data dictionaries, and the designation of digital certificates.  ERCOT shall encourage vendors to identify design requirements that create feasibility or cost issues (value engineering).

- Throughout the planning phase of the transition process, Market Participants, PUCT staff, the IMM, OPUC Staff, and TAC Residential Consumer members may review and provide input on the documents specified below:

(a)	Business Requirements – Document that describes the goals, assumptions, user functionality and business rules needed to accomplish the business functionality. This document is the basis for creating conceptual design, functional testing and training documents.  The final version of each requirements document, before it is used, must be approved by the TPTF as being in compliance with applicable protocols.

(b)	Conceptual System Design document – Document that describes the method of accomplishing the requirements, including user interaction with the system and interfaces within the system itself. This document is the basis for creating the detail design document.  The appropriate MCT will review these documents, whether developed in-house by ERCOT or through an RFP.

(c)	Detail System Design document – Document that provides the full details of the components in the system and how they interact with each other to implement the conceptual design.  The appropriate MCT will review these documents, whether developed in-house by ERCOT or through an RFP.

Wouldn’t this be covered in (a), (b), and (c) above?

(d)	ERCOT/Market Participant interface standards – the design of interfaces between ERCOT and Market Participants for the relevant systems, whether developed in-house by ERCOT or through a RFP.

(e)	Value engineering - suggestions made by each vendor or system developer that may be based upon technical feasibility, cost-effectiveness, or prior market experience.  ERCOT will review such suggestions with the appropriate MCT.  Approval of the vendor suggestions must be based on compliance with the applicable Protocols.

SHOULD (3) and (4) be moved to the System Testing and Nodal Market Implementation track?

(3)	ERCOT and TSPs shall establish the network model to be used for initial testing of the new systems.  ERCOT will make the network model available, consistent with applicable security and confidentiality policies, to Market Participants for testing. This network model should include a working and stable State Estimator that provides estimates of all loads where nodal prices will be calculated for at least six months before the nodal market testing period begins for at least six months.  After testing, the network model and the State Estimator must be approved by the appropriate MCT before initial nodal price testing for the settlements process.

(4)	As early as practical, ERCOT shall begin posting LMPs to Market Participants based on test Resource offer curves submitted to ERCOT by the QSEs to measure the accuracy and stability of the SCED.  The minimum time for this posting should be at least six months but may be longer as approved by the appropriate MCT.

SHOULD (5) and (6) be moved to a different track?

(5)	The appropriate MCT shall communicate the plan for settlement of nodal testing periods and submit Protocol Revision Requests needed to support that settlement before implementation of the nodal market and Protocols.

(6)	It is anticipated that the current zonal market settlement process will be required beyond the implementation of the nodal market to support Invoices and open disputes.  ERCOT shall develop a plan to address the issues that arise because there will be one nodal settlements process in production and a legacy settlements process preserved for the purpose of dealing with former market design true-ups and dispute resolution.

Could this be addressed in the Market Training Track?

(2)	The appropriate MCT shall establish a technical forum for QSE system development and implementation.

Could this be addressed in the Testing Track?

(3)	Using the ERCOT/Market Participant interface documents, each Market Participant shall develop systems necessary to operate in the new nodal market, in accordance with the milestone dates for such development in the Project Plan.  Each Market Participant must be able to demonstrate the ability to operate its systems effectively in the old zonal market and its systems in the new nodal market at the same time, with the ability to switch back and forth between the two when requested by ERCOT without negative impact to the market at large. Each Market Participant must give ERCOT, upon request or on a schedule promulgated by ERCOT, a status report on the Market Participant’s progress in developing its nodal market systems.

## 5.3	Market Training Track

(1)	(covered below?).

(2)	As soon as practical after approval of the nodal Protocols by the PUCT, ERCOT shall develop and conduct a training program for Market Participants, open to any interested party, which explains how the nodal market will work under the approved nodal Protocols.

(3)	As soon as practical after development of the nodal system specifications, ERCOT shall develop a comprehensive program of training requirements covering both Market Participant and ERCOT staff roles in the nodal market.  These activities should be timed for delivery in conjunction with the System Testing and Nodal Market Implementation Track.  All training sequences are to be offered in sufficient number and on a schedule to facilitate Market Participant and ERCOT staff attendance prior to any test sequence implementation that requires working knowledge of the training subject matter.  The overall training program shall consist of mandatory, highly recommended, and recommended subject matter modules that, when fully developed, will be repeatable.  ERCOT shall strive to clearly define the applicable market participant role targeted by the training modules.  ERCOT’s development of the training subject matter shall attempt to leverage, as much as possible, the technical delivery systems ERCOT currently uses such as web casting and conference bridging.

(4)	Each Market Participant has the responsibility to ensure that appropriate personnel complete applicable training programs offered by ERCOT. ERCOT may require that Market Participant entities complete certain training modules to participate in the nodal market.

Each training module shall follow a standard format consisting of a minimum of:

- Introduction

- Objectives

- Materials, Pre-requisites  and Competencies Required

- Course Material

- Self Quiz or Proctored Interactive Quiz to Measure Achievement of Objectives with feedback

- Method for Recording Participation and Completion

Should this be in the Market Readiness Track?

(5)	ERCOT shall keep a running inventory of each Market Participant’s training progress and shall post for the information of the market at large by segment to show the status of the ERCOT market’s readiness for cutover.

(5)	ERCOT shall keep a running inventory of each Market Participant’s training progress and shall post for the information of the market at large by segment to show the status of the ERCOT market’s readiness for cutover.

(6)	The following Table 1 - ERCOT Texas Nodal Training Program, contains samples of training curricula to be developed by ERCOT and provided to interested Market Participants, PUCT staff, and ERCOT employees. Specific courses may be completed in less than one day or last up to 5 days of classroom instruction to assure complete coverage of the subject.  All course curricula shall be reviewed by the TFPT for completeness and applicability.

| Table 1 - ERCOT Texas Nodal Training Program Sample M = Mandatory; HR = Highly Recommended; R = Recommended |
| --- |
| Typical Courses | Web Training Materials | Virtual w/live Instruction | In-Person Classroom | QSE | LSE | PM/Trader | TSPs & DSPs | General Knowledge |
| ERCOT 101: The Basics |  |  |  | M | M | M | M | M |
| NOIE QSE Operations |  |  |  | R | R | R | R | R |
| Basic Training Program |  |  |  | M | R | R | M |  |
| Extended Training Class System Dynamics |  |  |  | HR |  |  | HR |  |
| LMP 101 |  |  |  | HR | HR | HR | E | HR |
| Start-up Testing |  |  |  | M | M | HR | M | HR |
| Market Settlements 301 |  |  |  | R | R | R |  |  |
| Load Serving Entity 201 |  |  |  | R | M | M |  | R |
| Generation 101 |  |  |  | M |  | R | R |  |
| Generation 201 |  |  |  | M |  |  | R |  |
| Generation 301 |  |  |  | M | HR |  | R |  |
| Real Time Operations 101 |  |  |  | M | R | HR | M |  |
| System Operator Seminar |  |  |  | M | R |  | M |  |
| Transmission 101 |  |  |  | HR |  | R | M |  |
| Scenario-Based Training for Generation Owners |  |  |  | M |  | HR |  |  |
| Scenario-Based Training for Load Serving Entities |  |  |  |  | M | HR |  |  |
| Scenario-Based Training for TSPs and DSPs |  |  |  |  | M | HR |  |  |
| Transactions 201 |  |  |  |  |  | M |  |  |
| CRRs, PCRRs, and Supply Hedging |  |  |  | M | M | M | HR | HR |
| ERCOT 101 for Wind Generation |  |  |  | M |  | M |  | R |

## 5.4	System Testing and Nodal Market Implementation Track

This track includes tasks related to the testing and startup of Real-Time Network Security Analysis, the Day-Ahead Market (DAM), and Reliability Unit Commitment (RUC) including the settlement systems affected by those processes.  The Real-Time Network Security Analysis, the DAM, and the RUC are all described in detail in the nodal Protocols.

### 5.4.1	Data and Telemetry Testing Requirements

- As early as practical, the appropriate TAC subcommittee shall establish a task force to develop a set of Telemetry Criteria.  To support ERCOT SCADA and ERCOT Network Model database development and data acquisition field testing, ERCOT should  investigate the feasibility to deliver and configure a test computer system hardware and software Early Delivery System (EDS) such that ERCOT may generate test databases, build and verify computer graphic displays of all substations and transmission lines, build and verify displays of all Resources, and verify actual telemetry from TSPs and QSEs, similar to Figure 1, Dual System Configuration Concept.  ERCOT shall strive to complete these efforts before the testing of other systems begins.

(2)	ERCOT shall develop procedures for setup and data implementation requirements applicable to TSPs and QSEs.  ERCOT shall with the assistance of TSPs and QSEs:

(a)	Verify that all data and telemetry requirements specified in the nodal Protocols Section 3.10, Network Operations Modeling and Telemetry, have been met and that all data submittals are complete and represent an accurate model of the ERCOT System;

(b)	Review and check for accuracy all constraints on transmission elements;

(c)	Verify that TSP calculations are according to the Nodal Protocols for any transmission constraints likely to be binding in the SCED;

(d)	Verify the operability of the redundant communications systems required in the nodal Protocols.  ERCOT shall develop a detailed test to test systems and data telemetry to assure that each data element that ERCOT receives from a TSP or QSE is accurately represented in all ERCOT systems and graphical displays;

(e)	Verify that all telemetry meets the update performance requirements specified in the nodal Protocols;

(f)	Verify that all alarm processors operate properly when used to provide notice to ERCOT operators for changes in status of any transmission element, generator or load including the change in Resource Status made by a QSE;

(g)	Verify that all alarm processors used to provide notice to ERCOT operators for limit violations (overload, voltage high/low, tap position limit, etc.) operate properly, including limit change notices for Resources;

(h)	Verify functions of the Outage Scheduler for functional and accurate operation;

(i)	Verify that ERCOT operators are able to determine whether an Outage of a Transmission Facility shown in Real Time had been scheduled in the Outage Scheduler or whether such outage is a Forced Outage;

(j)	Verify that the acquisition of real-time weather information needed to support the Dynamic Rating Processor works properly; and

(k)	The appropriate MCT shall verify that all telemetry meets the criteria required in the nodal Protocols in Section 3.10.7.4, Telemetry Criteria.

### 5.4.2	State Estimator Implementation

(1)	As early as practical, the appropriate TAC subcommittee shall establish a task force to develop a State Estimator Performance Standard.  ERCOT shall verify that the requirements developed under Section 3.10.9, State Estimator Performance Standard, are sufficient.  ERCOT may define additional input data requirements for the necessary level of State Estimator performance.  This could be in the form of redundancy, defined locally as well as globally, redundancy of the communication system to ensure acceptable State Estimator availability, etc.

(2)	ERCOT shall require the vendor to add hardware and software to the EDS as early in the project delivery as possible to support trial operation of the State Estimator. ERCOT shall require the vendor to supply the Network Topology Builder and the Bus Load Forecast functions and to assist ERCOT in the startup of the State Estimator.  ERCOT shall begin trial operation of the State Estimator as early in the transition process as possible. Trial operation should be based on input data from the live data acquisition processes and calculated data as necessary.  ERCOT will work with TSP’s and QSE’s dedicated personnel to tune the State Estimator, correct data acquisition errors, calibrate field measurements, and correct network modeling parameters until the State Estimator reliably meets the performance criteria specified in the nodal Protocols, Section 3.10.9, State Estimator Performance Standard.

(3)	On stable operation of the State Estimator, as determined by ERCOT, ERCOT shall begin trial operation of the Topology Consistency Analyzer to verify that TSPs and QSEs are in compliance with Section 3.10.7.4.1, Continuous Telemetry of the Status of Breakers and Switches, of the nodal Protocols.

(4)	Once the accuracy and reliability criteria for the State Estimator have been met, ERCOT will begin continuous operation of data acquisition and State Estimator in parallel with all other existing ERCOT wholesale market systems.  ERCOT shall post information required in Section 6.3.2, Activities for Real-Time Operations, of the nodal Protocols to the extent that information and data is available and shall clearly indicate the source of the test information.

### 5.4.3	Real-Time Network Security Analysis Implementation

(1)	On satisfactory completion of testing and verification of stability and accuracy of the State Estimator, ERCOT shall begin preparation for trial operation of Network Security Analysis.  ERCOT shall develop a test list of transmission contingencies initially limited to major transmission elements.  The vendor shall configure the EDS to provide a test environment for the Network Security Analysis sequence.  Such configurations shall be designed to represent as closely as possible the expected operations environment of the real time sequence executing in the final state of ERCOT’s energy management system.

(2)	ERCOT operations staff shall compare the trial Network Security Analysis results to results from other ERCOT real-time computations. As testing proceeds, additional contingencies will be added to the Contingency List and the Contingency Screening application will be enabled. Additionally, the Dynamic Ratings Processor will be enabled and verified for proper operation.

(3)	ERCOT will continuously monitor the EDS during normal working hours Monday thru Friday.  ERCOT shall involve system operators in the EDS process for training purposes when practical.  As the Network Security Analysis process identifies constraints, ERCOT will begin performing the functions of transmission constraint management as described in nodal Protocols, Section 6.5.7.1.11, Transmission Constraint Management.

### 5.4.4	Security Constrained Economic Dispatch

(1)	ERCOT, the IMM, and Market Participants shall, through the appropriate MCT, develop a method for Market Participants to create and provide individual Resource offer curves for use in SCED.

(2)	To support trial operation of the SCED on the EDS, to ensure that the pre-requisite component relationships are working, as well as to evaluate the quality of the LMPs produced, ERCOT shall implement the capability for QSEs to enter individual Resource offer curves for use in SCED.

(3)	The vendor shall configure as necessary, the EDS to provide a test environment for the SCED.  ERCOT shall verify that the information and telemetry specified in Nodal Protocols, Section 6.5.7.1.12 Resource Limits and Section 6.5.7.1.13, Data Inputs and Outputs for the Real-Time Sequence and SCED, are available. Once QSEs are providing sufficient information, ERCOT shall begin trial operation of SCED and calculation of Resource Base Points.  The LMPs calculated by SCED shall be verified for reasonability.  Once general reasonability has been achieved as determined by ERCOT, ERCOT shall begin posting LMPs and other data available on the EDS if such posting is required in Nodal Protocols, Section 6.3.2, Activities for Real-Time Operations.

(4)	The Site-Acceptance Test will be performed by ERCOT.  Any revised design documentation resulting from Site Acceptance Test will be provided to the appropriate MCT.

(5)	On completion of the vendor ERCOT Site Acceptance Testing required  by the RFP, the vendor shall re-configure the EDS into the final environment, Texas Energy Management and Control System (TXMACS), to support all remaining functions required to meet the requirements of the Nodal Protocols.  SCADA, Network Security Analysis, Transmission Constraint Management and SCED will be retested in this final configuration

### 5.4.5	Trial Operation of Congestion Revenue Rights Auction

(1)	The appropriate MCT shall provide potential CRR auction Market Participants with a detailed test plan describing each step of trial operation testing.  This plan will initially require authorized Market Participants to create test bids for CRRs on Transmission Elements.  ERCOT shall execute a trial auction of monthly, seasonal and annual CRRs.  Market Participants shall be assigned test CRRs/PCRRs to be used for trial operation of DAM and trial operations testing of the settlement systems.

(2)	Any CRRs or PCRRs that may have been auctioned to Market Participants for periods of time prior to completion of start-up may be subject to refund to the Market Participants.  [Note: should we consider some verbiage that addresses the disposition of the current market design’s TCRs and PCRs that may not expire coincident with the date of the nodal start-up?]

### 5.4.6	Trial Operation of Day Ahead Market

(1)	The appropriate MCT shall provide Market Participants with a detailed test plan describing each step of trial DAM operation testing. This plan will initially require authorized Market Participants to create offers for physical Resources and bids for Load based on their best estimate of anticipated physical demand that can be used by ERCOT in testing DAM.  After convergence of DAM using physical bids and offers, ERCOT shall expand testing to allow Market Participants to submit virtual offers and bids for any settlement point on the ERCOT Transmission Grid.

(2)	ERCOT shall test the operation of DAM to procure Ancillary Services according to the protocols using test offers from Market Participants.

(3)	DAM trial operation testing shall continue for seven consecutive Operating Days.  On detection of any significant error of DAM, ERCOT and the Vendor will correct the problem and re-start the DAM trial operations test.  These resets of DAM performance will continue as needed until DAM operates properly for seven consecutive days.

(4)	ERCOT shall provide QSEs with test DAM settlement statements for the seven consecutive Operating Days.  The test DAM settlement statements will use calculated LMPs and MCPCs from the DAM and to the extent possible, show the effect of real time operations simulation from TXMACS.  QSEs shall review the test settlement statements for errors and provide feedback to ERCOT for resolution.

### 5.4.7	Trial Operation of Reliability Unit Commitment

(1)	Following a declaration by each MCT, QSEs and ERCOT shall begin market trials for RUC in parallel with the DAM testing.  Such testing shall initially include using test offers for Resources from the DAM.

(2)	Each MCT shall provide Market Participants with a detailed test plan describing each step of trial operation testing. This plan will initially require authorized Market Participants to create offers for physical off-line Resources that can be used by ERCOT in testing RUC.

(3)	ERCOT shall provide QSEs with test settlement statements for the Operating Day.  The test settlement statements will include commitments of Resources from RUC, including to the extent possible, statements showing the effect of real time operations from TXMACS.   QSEs shall review the test settlement statements for errors and provide feedback to ERCOT for resolution.

### 5.4.8	Load Frequency Control Testing

(1)	ERCOT shall verify all data requirements of Section 6.5.7.6, Load Frequency Control, have been met for each QSE that is qualified to provide either Reg-Up, Reg-Down, or Responsive Reserve Services. On completion of all communication systems testing, ERCOT shall verify the proper operation of the Load Frequency Control functions.

(2)	The calculation of Area Control Error on the TXMACS and the existing control systems shall be continuously compared for accuracy for several days.  After accuracy has been verified, ERCOT shall begin testing of individual QSEs to provide Regulation control and Dispatch Instructions for manual Responsive Reserve deployment dispatch through actual deployment of regulation energy.  Such test deployments shall be considered Dispatch Instructions and not subject the QSE to any performance charges.  Responsive Reserve deployment energy will be limited to a minimum to verify proper operation.  QSEs will only be required to accept control signals at any one time from either the existing control system or the TXMACS.

(3)	ERCOT shall test one QSE at a time verifying proper operation of each QSE.  ERCOT shall also verify the QSE’s ability to operate on constant frequency as required under Protocol Section 8.1.2.2.2, Regulation Service.

(4)	On reasonable completion of trial operations testing of DAM and RUC, and a majority of QSEs completing testing of (1), (2), and (3) above, each MCT may declare the system ready for the 168 Hour Test.

### 5.4.9	168 Hour Test and Trial Real Time Settlement

(1)	The appropriate MCT shall develop real time dispatch market readiness criteria that will include a systems stability test.  The systems stability test generally will require the real time systems performing SCADA, Network Security Analysis, Transmission Constraint Management, SCED and LFC to operate without significant error for at least 168 continuous hours.  On detection of any significant error of the operations systems (non-settlement), ERCOT and the Vendor will correct the problem and re-start the 168 Hour Test.

(2)	On completion of the 168 Hour Test, ERCOT shall provide QSEs with test settlement statements for each Operating Day of the 168 Hour Test.  The test settlement statements for each Operating Day will use calculated dispatches and LMPs from SCED and actual meter data.  QSEs shall review the test settlement statements for errors and provide feedback to ERCOT for resolution.    ERCOT will work with Market Participants to resolve any settlements issues identified during the 168 Hour Test prior to beginning Real-Time Operations.

### 5.4.10	Transmission Element and Resource Outages

(1)	ERCOT shall develop a plan, approved by TAC, to limit planned or emergency Transmission Element outages during the initial operation of Real-Time systems to only those necessary to maintain reliability.

(2)	The ERCOT plan to limit transmission element outages shall consider allowances for long term construction schedules requiring outages with limitations placed on switching equipment in and out of service.  Limitations may also restrict high risk (as determined by ERCOT) outages entirely.

(3)	ERCOT, TSPs and QSEs shall synchronize use of the Outage Scheduler for Transmission Elements and Resource outages, described in Protocols Section 3.1, to schedule outages such that both the existing outage scheduling tools and the TXMACS systems are properly updated.

### 5.4.11	Real Time Operation and Settlement

(1)	Once reasonable assurance of stable and accurate operation of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared. The appropriate MCT with the concurrence of the ERCOT Board, shall appoint a time and date for either start-up of Real-Time operations, or start-up of Real-Time operations and RUC or start-up of Real-Time operations including DAM and RUC and settlement of all systems. Cutover shall begin at a predefined time by enabling all QSEs to take control actions from the TXMACS simultaneously.  For start-up of Real-Time operations alone, Ancillary Services shall be provided by QSEs who self-scheduled or were awarded supply obligations from the existing zonal market systems.

(2)	ERCOT may judge TXMACS to be unstable or not performing properly and instruct QSEs to return control functions to the existing computer control system until problems with TXMACS real time functions can be corrected.

(3)	ERCOT shall continuously provide notice and computer systems status information to all Market Participants on the MIS Secure Area.  Once reasonable stability of TXMACS has occurred and been declared, ERCOT should not switch control back to its existing control systems, except in circumstances where ERCOT determines that system stability may be compromised.

### 5.4.12	Performance and Compliance Measurement

ERCOT shall develop a detailed plan to test the monitoring of the performance of TDSPs, QSEs and its own operations according to the requirements of Section 8, Performance Monitoring and Compliance.  Sample performance and compliance reports shall be provided to Market Participants for review and comment.

### 5.4.13	Market Information Systems

ERCOT shall develop a detailed plan to demonstrate its compliance with the requirements of the MIS.

### 5.4.14	Supplemental Ancillary Services Market

The appropriate MCT shall develop and conduct procedures to test the SASM systems.

### 5.4.15	Daylight Savings Time

The appropriate MCT shall develop and conduct procedures to test for the proper transition of systems to and from Daylight Savings Time.

# 6	Market Readiness

# 6.1	Market Readiness Criteria

MCTs shall develop detailed Market Readiness Criteria that must include at least the following:

(a)	LMPs calculated and disseminated according to plan;

(b)	Ancillary Services deployment tested successfully live;

(c)	Base Points tested successfully live (SCED);

(d)	RUC tested successfully live;

(e)	Network model tested successfully and delivered;

(f)	Training complete for ERCOT and Market Participants according to Section 6.2;

(g)	Settlement testing successfully completed;

(h)	DAM testing successfully completed;

(i)	TCR to CRR transition plan implemented;

(j)	Zonal and nodal coordinated settlements implemented;

(k)	New combined QSE/CRR Account Holder agreements signed;

(l)	Credit calculations of credit exposure tested successfully and ready. The calculation of credit exposure is intended to use information from market settlement systems both before and after the Texas Nodal Market Implementation Date, regardless of how information is included on an Invoice.  Invoices from the “old” market (before the Texas Nodal Market Implementation Date) will be used to calculate EAL until an Invoice that includes Initial Settlement Statements for a full seven days is generated under the “new” market (after the Texas Nodal Market Implementation Date).  ERCOT shall base resettlement credit exposure on estimates from both settlement systems and shall take into consideration how much credit exposure is expected under each system.   Notwithstanding the above, Financial Security required from each Counter-Party for the first six weeks from the date of conversion to the “new” market is equal to or greater may not be less than the Financial Security held on behalf of any Counter-Party at the date of conversion to the “new” market.

# 6.2	Market Participant and ERCOT Personnel Readiness

Each MCT shall develop a set of criteria to evaluate market participant and ERCOT personnel readiness that gauges both market systems and personnel training completion.  Each MCT shall advise the market of the criteria developed and appraise the market on a regular basis of the market’s achievements.

# 6.3	Market Readiness Declaration

On completion of all testing, including those tests specifically required of this section and testing of ERCOT’s compliance with the requirements of the then established Protocols, Each MCT shall make a public declaration to describe the operational readiness of its systems to perform according to the protocols.  Any systems not meeting the requirements of the protocols as determined by the MCT shall be clearly delineated in the declaration.

Additional PUCT Comments/Thoughts:

- The process to identify and address areas where the design contemplated by the protocols is not feasible, cost effective, or the most effective needs to be delineated in a manner that is transparent and that allows the protocols to be amended to obtain the optimal design.

- The process to incorporate protocol revisions into the nodal design needs to be addressed.

- PUCT staff assumes that WMO’s advisors, Shmuel Oren and David Patton, would be able to review the same material PUCT staff reviews to assist with comments and suggestions that PUCT staff may have during the nodal transition.

- The Independent Market Monitor should participate along with ERCOT and market participants in Section 5, Transition Plan Tracks, and Section 6.2, Market Participant and ERCOT Personnel Readiness.

- As described in Chairman Hudson’s July 28th memo on wholesale market design in Project 28500, have a requirement in the transition plan that generators submit cost-based offer curves into ERCOT day-ahead and real-time markets for the first few months after the nodal market opens.  MISO used a similar approach in its implementation of a nodal market design.