## CBA_Dtl
Project Cost / Benefit Analysis Detail Worksheet
Project Information | [6 empty] | ß |  |  | Market: Enter source document for request (PRR or SCR)
PRR / SCR / PR / "New": | SCR 738 | [8 empty] | ERCOT: Enter "New" if requesting a new ER number
Project Title: | Enhancement to FasTrak -- PR50007
Sponsor's Name: | Richard Gruber | Estimator: | Project Team | Estimate Date: | 2005-05-25
Senate Bill 7 Requirements
Indicate percentage that this project supports SB7 requirements:
Pct
| Access to transmission and distribution systems |  |  | 0%
| Reliability and adequacy of electrical network |  |  | 0%
| Customer choice of REP |  |  | 50%
| Accounting accuracy |  |  | 50%
|  | Total (Maximum 100%) |  | 100%
ERCOT Corporate Goals
Indicate percentage that this project supports each ERCOT corporate goal:
Pct
| 1 - Reliability and Congestion Management |  |  | 0%
| 2 - Retail Transaction Processing Success |  |  | 35%
| 3 - Wholesale Access, Settlement and Billing |  |  | 15%
| 4 - Management Systems and Business Practices |  |  | 0%
| 5 - Financial Management and Cost Effectiveness |  |  | 15%
| 6 - External and Stakeholder Affairs |  |  | 35%
| 7 - Organizational Readiness |  |  | 0%
|  | Total (Maximum 100%) |  | 100%
Assumptions
Assumptions Relevant to the Cost / Benefit Analysis of this Proposed Project
1 | Over 50 MPs currently use the FasTrak tool, over 100 MPs in retail market, assume all will use the tool for Retail issue management. Assume growth of 10 MPs for the Retail area per year | [5 empty] | ß |  |  | Prioritize these by putting the most important at the top
2 | Calendar year 2004 over 40,000 issues were submitted to the tool. Each issue could have 1 or more ESIIDs tied to it. Assume growth of issues to be 25% per year | [8 empty] | The top 4 will be displayed on the summary page
3 | Assume with the new solution working FT issues will become more efficient for MPs and ERCOT
4 | Assume new solution will have the ability to provide significantly more trends and metrics around issues.
5 | Assume new solution will have the ability to better manage individual user issues for MPs and ERCOT
6 | Assume new solution will have security standards that meet ERCOT goals.
7 | Assume new FT solution will be the primary tool used by all MPs and ERCOT for retail issue management
8
ERCOT Cost / Benefit Detail
ERCOT Internal Cost |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | OPTIONAL WORKSHEET FOR CALCULATING COSTS - STAFFING
Implementation Cost | Cost to Implement: | 1252386 | 0 | 0 | 0 |  |  | NPV = | 0
[10 empty] | Task / Item | FTE Cost ($/hour) | Number of FTE Hours Per Workday | Total FTE Hours per year | Estimated Cost ($/yr) = Total FTE Hours * FTE Cost | Workdays Per Year
Ongoing Cost (O&M) | Staffing: |  | 33800 | 33800 | 33800 |  |  | NPV = | 90347.8039 | Admin for new tool | 65 | 0.25 | 520 | 33800 | 260
| Hardware: |  |  | 0 | 0 |  |  | NPV = | 0 | Intenal Training | 65 | 50 | 1200 | 78000 | 3
| Software: | 0 | 8400 | 12600 | 12600 |  |  | NPV = | 29717.6864 | External Training | 65 | 4 | 512 | 33280 | 16
| Infrastructure | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 260
| Internal Training | 78000 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 260
| External Training | 33280 | 3328 | 3328 | 3328 |  |  | NPV = | 8895.7838 |  | 0 | 0 | 0 | 0 | 260
| Total ERCOT Implementation Cost: | 1252386 | [10 empty] | Total | 145080
| Present Value of ERCOT O&M Cost: | 240241.2741
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
ERCOT Internal Benefit |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | Task / Item | FTE Cost ($/hour) | Number of FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Benefit ($/yr) = Total FTE Hours * FTE Cost | Workdays Per Year
[10 empty] | EDIM Inadvertent Switch/Cancel Time Savings | 65 | 6 | 3900 | 253500 | 260
Direct Cost Savings | Staffing: | 135200 | 135200 | 135200 | 135200 |  |  | NPV = | 361391.2156 | RCS efficiency increases | 65 | 6 | 390 | 25350 | 260
| Hardware: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | EDIM efficiency increases for Reports | 65 | 4 | 3120 | 202800 | 260
| Software: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | Other EDIM efficiency increases | 65 | 12 | 1560 | 101400 | 260
| Infrastructure: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 260
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | Direct Labor Savings | 65 | 1 | 2080 | 135200 | 260
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0
Productivity Increases | Time Savings: | 583050 | 583050 | 583050 | 583050 |  |  | NPV = | 1558499.6171 |  |  |  | Total | 718250 |  | MARKET COST
| Other Increased Efficiencies: | 0 | 58305 | 58305 | 58305 |  |  | NPV = | 155849.9617 | [6 empty] | Categories | Number in Mkt | Implementation Cost compared to ERCOT cost | Total Implementation Cost | On-going cost per MP | Total On-going cost
| Feasibility | 100000 | 100000 | 100000 | 100000 |  |  | NPV = | 267301.1949 | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER | [5 empty] | High CR | 5 | 1001908.8 | 5009544 | 65975 | 329875
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | [6 empty] | Med CR | 10 | 250477.2 | 2504772 | 32987.5 | 329875
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | License fees/seats | 25 seats cost $4200 |  |  | 0 |  | Low CR | 35 | 12523.86 | 438335.1 | 0 | 0
Other Benefits | Cost Avoidance: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | Feasibility benefits | Assume $100,000 benefit for new functionality |  |  | 0 |  | Total CR |  |  | 7952651.1 |  | 659750
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0 |  | TDSP | 6 | 1001908.8 | 6011452.8 |  | 395850
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0 |  | Total TDSP |  |  | 6011452.8 |  | 395850
[16 empty] | Overall Total |  |  | 13964103.9 |  | 1055600
| Present Value of Internal ERCOT Benefit: | 3161291.9894
Market Cost / Benefit Detail
Market Cost |  | Estimated Market Cost | Market Segment | Number Impacted | Market Implementation Complexity | [10 empty] | MARKET BENEFIT | [5 empty] | MARKET Additional Benefits
[16 empty] | Categories |  | Direct Labor Savings | Time Efficiencies Savings | Feasibility Savings | Summary | Automated Savings | Transcation benefits | Consumer Savings | Cost Avoidance
Implementation Cost |  | 0 | QSE | 0 | No Impact |  | ß |  |  | ERCOT Implementation Cost * Number Impacted * Complexity | [5 empty] | High CR | 5 | 1319500 | 676000 | 500000 | 2495500
(Based on ERCOT cost) |  | 8000000 | CR | 50 | No Impact | [10 empty] | Med CR | 10 | 1319500 | 338000 | 500000 | 2157500
|  | 6000000 | TDSP | 6 | No Impact | [10 empty] | Low CR | 35 | 1154562.5 | 591500 | 0 | 1746062.5
|  | 0 | Resource | 0 | No Impact | [10 empty] | Total CR |  | 3793562.5 | 1605500 | 1000000 | 6399062.5
| Market Implementation Cost: | 14000000 | [13 empty] | TDSP | 6 | 791700 | 1622400 | 600000 | 3014100
[16 empty] | Total TDSP |  | 791700 | 1622400 | 600000 | 3014100
Ongoing Cost |  | Year 1 | Year 2 | Year 3 | Year 4 | [10 empty] | Overall Total |  | 4585262.5 | 3227900 | 1600000 | 9413162.5
| QSE | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| CR | 660000 | 660000 | 660000 | 660000 |  |  | NPV = | 1764187.8866
| TDSP | 400000 | 400000 | 400000 | 400000 |  |  | NPV = | 1069204.7798
| Resource | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Present Value of Ongoing Market Cost: | 3893392.6664
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
Market Benefit | Impacted Market Segments | Direct Cost Savings - Per MP | Elimination of Manual Effort - Per MP | Feasibility(Per MP) | Other:(Per MP) |  |  |  |  | Task / Item | FTE Cost ($/hour) | Number of FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Cost Savings = Total FTE Hours * FTE Cost | Workdays Per Year
[11 empty] | 0 | 0 | 0 | 0 | 260
Benefits Quantified | QSE | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 260
by Participant | CR | 3800000 | 1600000 | 1000000 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 260
Direct Benefit | TDSP | 800000 | 1600000 | 600000 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 260
| Resource | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 260
[11 empty] | 0 | 0 | 0 | 0 | 260
|  | Year 1 | Year 2 | Year 3 | Year 4 | [5 empty] | 0 | 0 | 0 | 0 | 260
| Direct Cost Savings: | 4600000 | 4600000 | 4600000 | 4600000 |  |  | NPV = | 12295854.9675 |  | 0 | 0 | 0 | 0 | 260
| Efficiencies | 3200000 | 3200000 | 3200000 | 3200000 |  |  | NPV = | 8553638.2383 |  | 0 | 0 | 0 | 0 | 260
| Feasibility | 1600000 | 1600000 | 1600000 | 1600000 |  |  | NPV = | 4276819.1191 |  | 0 | 0 | 0 | 0 | 260
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 260
| Present Value of Individual MP Benefit: | 34526312.3249 | [10 empty] | Total | 0
Benefits for Market |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER
Additional Benefits | Automation Savings | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Consumer Savings: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | Item | Comment |  |  | Amount
| Transaction Cost: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
0
| Present Value of Market Benefit: | 0
| Total Present Value of Market Benefit: | 34526312.3249
Total Cost | 19386019.9405 |  | Net (Benefit - Cost) ($) |  | 18300000
Total Benefit | 37687604.3143 |  | Net Benefit / Cost (Ratio) |  | 1.9441 |  | ß |  |  | Greater than 1 is desirable
Objectives Detail
Score
IMPLEMENTATION REQUIREMENT: Is the project required to support a PUCT rulemaking or government requirement? Is the project required by an ERCOT committee? |  |  | 2 - Does not have a defined implementation date |  |  |  | ß | 2 |  | Select from dropdowns for each category
RELIABILITY: Does the project improve ERCOT's reliability performance? Is there a significant operational need for the project? |  |  | 3 - Addresses existing, moderate level issue |  |  |  | ß | 3 |  | Select from dropdowns for each category
SECURITY: Does the project improve ERCOT's security? Is there a physical security, cyber security or safety issue that is addressed by this effort? |  |  | 1 - Nice to have but not a necessity |  |  |  | ß | 1 |  | Select from dropdowns for each category
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market? |  |  | 3 - Addresses existing, moderate level issue |  |  |  | ß | 3 |  | Select from dropdowns for each category
EFFICIENCY: Does the project improve the efficiency/effectiveness of ERCOT? Does the project automate, improve and/or streamline a necessary function? |  |  | 3 - Spans multiple areas and partially addresses the function |  |  |  | ß | 3 |  | Select from dropdowns for each category
REQUIREMENTS: Are the high level requirements clearly defined? How complex are the potential solutions? Can the project be broken down into smaller sections or delivered in stages to reduce risk? |  |  | 2 - Requirements are complex but clearly defined, potential to deploy in phases to mitigate risk |  |  |  | ß | 2 |  | Select from dropdowns for each category
INVESTMENT OR BASELINE: Is this project an investment in new capability or does it support the baseline architecture that delivers current services? |  |  | 4 - Baseline |  |  |  | ß | 4 |  | Select from dropdowns for each category
RISK REDUCTION: Refer to Risk Reduction Section below |  |  | 2 - Some risk reduction |  |  |  | ß | 2 |  | Select from dropdowns for each category
TOTAL SCORE |  |  | Maximum Score = 30 |  |  | 20
[5 empty] | Regulatory Requirement |  |  | Q1 | 0 - No regulatory requirement
1 - Nice to have but not a necessity
2 - Does not have a defined implementation date
3 - Upon system implementation
4 - Has a defined implementation date
[5 empty] | Reliability |  |  | Q2 | 0 - No impact on reliability
1 - Nice to have but not a necessity
2 - Addresses existing, low impact issue
3 - Addresses existing, moderate level issue
4 - Addresses existing, high level issue
[5 empty] | Security |  |  | Q3 | 0 - No impact on security
1 - Nice to have but not a necessity
2 - Upon review of audit results, a breach was not discovered but suggestions were made to improve current policies/procedures
3 - Upon review of audit results, issues were discovered and recommendations were made to improve security/safety issues that required response prior to the next audit
4 - Without immediate attention, data privacy/integrity would be jeopardized that could have widespread market impacts
[5 empty] | Data Management |  |  | Q4 | 0 - No impact on this dimension
1 - Nice to have but not a necessity
2 - Addresses existing, low impact issue
3 - Addresses existing, moderate level issue
4 - Addresses existing, high level issue
[5 empty] | Efficiency |  |  | Q5 | 0 - No impact on this dimension
1 - Contained within one area and partially addresses the function
2 - Contained within one area and addresses the function 100%
3 - Spans multiple areas and partially addresses the function
4 - Spans multiple areas and addresses the function 100%
[5 empty] | Requirements |  |  | Q6 | 0 - Requirements are extremely complex, cannot be broken into phases and there is only one deployment recommendation
1 - Requirements are relatively easy but cannot be broken into phases and there is only one deployment recommendation
2 - Requirements are complex but clearly defined, potential to deploy in phases to mitigate risk
3 - Requirements are relatively easy and clearly defined, potential to deploy in phases to mitigate risk
[5 empty] | Investment/Baseline |  |  | Q7 | 0 - Investment
4 - Baseline
[5 empty] | Risk Reduction |  |  | Q8 | 0 - No significant risk reduction identified
1 - Nominal risk reduction
2 - Some risk reduction
3 - Significant risk reduction
Intangible Benefits
| Area | Comments (include reason why benefit cannot be quantified)
1 |  | Current tool has extremely limited reporting capabilities |  |  |  |  | ß |  |  | Prioritize these by putting the most important at the top
2 |  | Current tool has significant performance issues | [7 empty] | The top 4 will be displayed on the summary page
3 |  | Current tool does not have ability to create API
4 |  | Current tool has no management capabilities
5 |  | Current system can not be modified without significant risk
6 |  | Increase consumer satisfication due to new tool efficiencies
7 |  | Potentially CRs that use Service providers would have a cost savings due to increased efficiencies with the tool
8
9
10
11
12
Risk Reduction
| Risk Description | Mitigation Percentage (degree of reduction of risk) | Probability of Risk Condition happening (in a year) | Approximate cost of risk during risk period | Expected risk-cost/year = Probability of risk * Cost of risk * Mitigation %
1 | Data is currently not archived. If data corrupted or lost no recovery | 100% | 25% | 25000 | 6250 |  | ß |  |  | Prioritize these by putting the most important at the top
2 | Security risk with current tool due to non-encripted data transfer | 100% | 25% | 50000 | 12500 |  |  |  |  | The top 4 will be displayed on the summary page
3 | Data Security risk due to monitoring limitation | 100% | 10% | 50000 | 5000
4 | Current platform is not supported by IT | 100% | 100% | 100000 | 100000
5 |  | 0% | 0% | 0 | 0
6 |  | 0% | 0% | 0 | 0
7 |  | 0% | 0% | 0 | 0
8 |  | 0% | 0% | 0 | 0
Alternatives | [6 empty] | ß |  |  | Document costs and other impacts of not executing the project
[7 empty] | ß |  |  | Document other alternatives considered
Alternatives (Cost of Not Doing Project, Manual Workaround Options, etc.)
1 | Keep using current tool with the MPs.
2 | Phone and emails from MPs to ERCOT
3
4
Note on A91: Raj Chudgar: refer to cells T75
Note on A108: Raj Chudgar: Refer to T89
Note on C54: rchudgar: 2005 PPL value
Note on D56: rchudgar: Minor increase in admin for new application solution
Note on D58: rchudgar: Potentially additional license costs (8400 based on 50 additional seats)
Note on D76: rchudgar: Efficiency savings incurred due to not having to add staff
Note on V91: Raj Chudgar: $65/hr*1hr/day*4 people per staff*number of participants
Note on V92: Raj Chudgar: $65/hr*1hr/day*4 people per staff*number of participants
Note on W91: Raj Chudgar: $65/hr*260 days/yr*4hours/day*4staff/MP*number of MPs

## CBA_Sum
Project Cost / Benefit Analysis Summary
Project Information
PRR / SCR / PR / "New": | SCR 738
Project Title: | Enhancement to FasTrak -- PR50007 |  |  | Sponsor's Name: |  | Richard Gruber
Estimator's Name: | Project Team |  |  | Estimate Date: |  | 2005-05-25
ERCOT Corporate Goals |  |  |  | Senate Bill 7 Requirements |  |  |  | ß | Market: SB7 required; ERCOT Goals optional
Indicate percentage that this project supports each corporate goal: |  |  |  | Indicate percentage that this project supports SB7 requirements: |  |  |  |  | ERCOT: Both ERCOT Goals and SB7 required
|  | Pct |  |  |  |  | Pct
Goal 1 - Reliability & Congestion Management |  | 0% |  | Access to transmission & dist systems |  |  | 0%
Goal 2 - Retail Transaction Processing Success |  | 35% |  | Reliability & adequacy of electrical network |  |  | 0%
Goal 3 - Wholesale Access, Settlement & Billing |  | 15% |  | Customer choice of REP |  |  | 50%
Goal 4 - Management Systems & Business Practices |  | 0% |  | Accounting accuracy |  |  | 50%
Goal 5 - Financial Management and Cost Effectiveness |  | 15%
Goal 6 - External & Stakeholder Affairs |  | 35%
Goal 7 - Organizational Readiness |  | 0%
Total (Maximum of 100%) |  | 100% |  | Total (Maximum of 100%) |  |  | 100%
Cost / Benefit Summary
Project Cost | ERCOT Implementation Cost | 1252386
| Market Implementation Cost | 14000000
| Total Implementation Cost |  | 15252386
| ERCOT O&M Cost | 240241.2741
| Market Ongoing Cost | 3893392.6664
| Total Ongoing Cost |  | 4133633.9405
[5 empty] | 19386019.9405 |  | Total Cost
Project Benefit | ERCOT Benefit | 3161291.9894
| Market Benefit | 34526312.3249
[5 empty] | 37687604.3143 |  | Total Benefit
|  | Net (Cost) / Benefit |  |  | 18301584.3738
Objectives Summary
Enhancement to FasTrak -- PR50007 | [6 empty] | Score
IMPLEMENTATION REQUIREMENT | [6 empty] | 2
RELIABILITY | [6 empty] | 3
SECURITY | [6 empty] | 1
DATA MANAGEMENT | [6 empty] | 3
EFFICIENCY | [6 empty] | 3
REQUIREMENTS | [6 empty] | 2
INVESTMENT OR BASELINE | [6 empty] | 4
RISK REDUCTION | [6 empty] | 2
TOTAL SCORE |  |  | Maximum Score = 30 |  |  |  | 20
Intangible Benefit Summary
| Area | Comments
1 |  | Current tool has extremely limited reporting capabilities
2 |  | Current tool has significant performance issues
3 |  | Current tool does not have ability to create API
4 |  | Current tool has no management capabilities
Risk Reduction Summary
| Risk Description | [5 empty] | Risk/Year
1 | Data is currently not archived. If data corrupted or lost no recovery | [5 empty] | 6250
2 | Security risk with current tool due to non-encripted data transfer | [5 empty] | 12500
3 | Data Security risk due to monitoring limitation | [5 empty] | 5000
4 | Current platform is not supported by IT | [5 empty] | 100000
Assumptions Summary
Assumptions
1 | Over 50 MPs currently use the FasTrak tool, over 100 MPs in retail market, assume all will use the tool for Retail issue management. Assume growth of 10 MPs for the Retail area per year
2 | Calendar year 2004 over 40,000 issues were submitted to the tool. Each issue could have 1 or more ESIIDs tied to it. Assume growth of issues to be 25% per year
3 | Assume with the new solution working FT issues will become more efficient for MPs and ERCOT
4 | Assume new solution will have the ability to provide significantly more trends and metrics around issues.
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | 50
| Impacted Number of TDSPs |  |  | 6
| Impacted Number of Resources |  |  | 0
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## Instructions
Cost / Benefit Analysis Worksheet Instructions
General Information
Fields highlighted in yellow are to be entered by the person completing the CBA
Fields highlighted in turquoise are section headings or important subtotals
All data entry takes place on the "CBA_Dtl" tab
"CBA_Sum" provides a 2 page summary of the 5 page detail section
"CBA_Dtl" contains several optional worksheets to the right of the main CBA sections
These optional worksheets are not included in the default print range
CBA_Dtl Tabl
Project Information
|  | PRR / SCR / PR / "New" |  | Enter the source document number for this project - if none exists,
enter "New"
|  | Project Title |  | Name of project
|  | Sponsor's Title |  | Project sponsor
|  | Estimator |  | Person completing the CBA
|  | Estimate Date |  | Date the CBA is completed
| Senate Bill 7 Requirements |  |  | Enter percent of each SB7 requirement the project supports
Total should not exceed 100%
| ERCOT Corporate Goals |  |  | Enter percent of each ERCOT corporate goal the project supports
Total should not exceed 100%
Assumptions
|  | Assumptions |  | Document assumptions that are made in the evaluation of the project
ERCOT Internal Cost
Implementation Cost
|  |  | Cost to Implement | For a project requested by ERCOT this number comes from the Time and Cost Estimate worksheet
For a project requested by the market, this number is the mid-point of the Impact Analysis cost range
All project costs are to be included in this value
Ongoing Cost (O&M)
|  |  | Staffing | ERCOT staffing increases due to the implementation of this project
|  |  | Hardware | Hardware additions required after project implementation
|  |  | Software | Software costs required after implementation (ex: yearly licensing)
|  |  | Infrastructure | Other costs relating to the physical or computing infrastructure
|  |  | Other | Use these 2 fields to capture other cost categories
|  |  | Other | Change the "Other" headings to the name of the new cost categories
ERCOT Internal Benefit
Direct Cost Savings
|  |  | Staffing | ERCOT staffing savings due to project
|  |  | Hardware | Hardware savings due to project
|  |  | Software | Software savings due to project
|  |  | Infrastructure | Infrastructure savings due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Productivity Increases
|  |  | Time Savings | Value of hours saved due to project deliverables
|  |  | Other Increased Efficiencies | Value of hours saved due to project deliverables
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Other Benefits
|  |  | Cost Avoidance | Costs avoided due to implementation of project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Market Cost
|  | Implementation Cost |  | Market implementation cost is derived from ERCOT implementation cost
|  |  | Estimated Market Cost | Calculated by multiplying ERCOT implementation cost by the selected market impact percentage (from the Parameters section) and the number of impacted market participants (from the Parameters section)
|  |  | Impacted Market Segments | These fields allow the requester to customize the cost/benefit
calculations by declaring the number of market participants are
impacted by segment - this is used in both the Market Cost and
Market Benefit sections
|  |  | Market Implementation Complexity | "High/Medium/Low/No Impact" - indicates the impact percentage for a market segment
|  | Ongoing Cost |  | Ongoing costs required of market participants upon implementation of project (totals by market segment)
Market Benefit
Benefits by Participant
|  |  | Direct Cost Savings | Direct savings per market participant in each market segment
|  |  | Elimination of Manual Effort | Elimination of manual effort per market participant in each market segment
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Benefits for Market
|  |  | Reduced Congestion Cost | Expected congestion cost savings in market
|  |  | Consumer Savings | Expected savings that are likely to benefit consumers - be sure not to double count savings to market participants that are likely to pass through to consumers
|  |  | Transaction Cost | Expected reductions in transaction costs due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Project Objectives Detail
|  | Implementation Requirement |  | Project score indicating implementation timing requirements and/or governing body requirements (PUCT, market committee, etc.)
|  | Reliability |  | Project score indicating impact on overall ERCOT system reliability (all systems to be considered)
|  | Security |  | Project score indicating impact on physical or cyber security
|  | Data Management |  | Project score indicating the impact on data accuracy, timeliness and/or transparency
|  | Efficiency |  | Project score indicating efficiency gains that would be realized
|  | Requirements |  | Project score indicating the completeness of the requirements and the likelihood that delivery risk can be reduced by breaking the project into smaller deliverables
|  | Investment or Baseline |  | Project score indicating whether the project provides additional functionality (investment) or supports the existing system architecture
|  | Risk Reduction |  | Project score indicating overall risk reduction that can be achieved at implementation
Intangible Benefits
|  | Area / Comments |  | Document benefits here that cannot be quantified but should be considered in the overall prioritization of the project
Risk Reduction
|  | Risk Description |  | Description of risk item
|  | Mitigation Percentage |  | Percent of the risk that the project would eliminate if implemented
|  | Probability of Risk Occurring |  | Probably of the risk occurring in a given year
|  | Approximate Cost of Risk |  | Estimated cost if the risk occurred
|  | Expected Risk Cost/Year |  | Risk probability * Approximate Cost of Risk * Mitigation Percentage
Alternatives
|  | Alternatives |  | Document alternatives that were considered or are available
Ex: comments about manual workarounds (amount of effort and cost) or other implementation options that were considered
CBA_Sum Tab
| Cost / Benefit Summary |  |  | Summary from CBA_Dtl tab
| Objectives Summary |  |  | Summary from CBA_Dtl tab
| Intangible Benefit Summary |  |  | Summary from CBA_Dtl tab
| Risk Reduction Summary |  |  | Summary from CBA_Dtl tab
| Assumptions Summary |  |  | Summary from CBA_Dtl tab
Calculation Parameters
Market Cost
|  |  | Impacted # of QSEs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of CRs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of TDSPs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of Resources | Source for this data is in the Market Cost section of CBA_Dtl
|  | Present Value Interest Rate |  | Percentage used to value future cash flows in the CBA
This value was suggested by the ERCOT Accounting Dept.; it should not be changed