## Slide 1: Project Updates to DEWG
ERCOT
September 15, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Project Updates
PR 40106 - ERCOT.com
PR 50007 - FasTrak
PR 50024 - Enhancements to SCR 727 (SCR 740 Web Service for ESIID data)
PR 40007 - SCR727 move from Data Archive to ODS
PR 40042_06 – Lodestar Batch Extracts
PR 30026 - EPS Meter Data Extract/Resource ID Extract
PR 50023 - Potential Load Loss
2005 Upcoming Projects
SCR 743 with BOD approval
PRR 577 with BOD approval
Necessary Project Updates?
TBD
Projects
ERCOT Project Updates
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
PR-40106 ERCOT.com
Execution Phase
Received positive feedback on site’s look & feel from Executive Committee
Continue to work on migrating documents to the new site
  About ERCOT 90%
  Market Rules 80%
  Committee & Groups – 80%
  Issue Tracking – 80%
Met with Meeting Managers to introduce the Issue Tracking tool
Dependencies – none at this time
Next Steps:
  Continue to work on migrating documents to the new site
    Services – Began on 9/1/05
    Market Operations – Began on 9/1/05
    System Operations – Begin on 9/15/05
  Work with Corporate Communications on final communication plan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
PR-50007 Enhancements to FasTrak
Execution Phase
Executive Committee update/endorsement on product selection/purchase
Board of Director approval of project to move forward
Serena Team Track training for business and IT held August 29th to September 2nd
Serena contract negotiations underway
Review/revision of project schedule given current scope, delivery approach, testing requirements, and resource availability
Dependencies:
  Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak – Removed
  SOA Integration - dependent on SOA MID project for integration framework components needed by API
Next Steps:
  Finalize contract with vendor
  Human Factors staff to work with business and IT on screen designs
  Business to create DRAFT work flows
  IT to create conceptual system design
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
PR-50024 Enhancements to SCR 727
Execution phase
Technical design and development ongoing
Product Testing to begin 11/2005
Implementation date: 1st Quarter 2006
Dependencies:
  Lodestar ODS interval data parsing
  Timing logic to determine point in time implemented and captured in Lodestar ODS
Next Steps:
  Will present further XML and technical design to DEWG in October
  Developing test scenarios for Product Test
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
PR-30026 EPS Meter Data Extract/Resource ID Extract
PR-40007 SCR 727 Phase 2
PR-40042_06 Lodestar Batch Extracts
All projects in Execution phase
Finalize test plan for technical testing and UAT testing for all projects for each environment
PR-30026 in PTEST and going to ITEST late 09/2005
PR-40007 in unit testing and going to PTEST late 09/2005
PR-40042_06 in PTEST and going to ITEST early 10/2005
Dependencies:
  Completed development and testing of timing logic for when to run and what timestamp data range to include in each extract
    Implemented into production on 8/31/2005
    Signoff on production verification week of 9/19/2005
  Interval data parser in Lodestar ODS to parse the BLOB interval data into VARCHAR2 for easy accessibility for business analysis and for extracts and reports
    Went to ITEST 08/22/05 and is back in PTEST for modifications
    Will be back in ITEST next week
Next Steps:
  Determine remaining project dates for all projects
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
PR-50023 Potential Load Loss
Planning phase
  Scheduled for completion on 10/17/2005
Prepared and submitted Project Charter for internal review
Drafted detailed business requirements
Dependencies:
  PR-40034 TX SET 2.1 implementation
  PR-50121_03 MID implementation
  PR-50121_07 TIBCO implementation
Next Steps:
  Finalize Project Charter
  Complete detailed business requirements
Notes: <number>
<footer>
<header>
<date/time>