## CO Staffing Plan
2005-10-03 | Planning |  |  | PM Staffing Plan and Cash Flow for CO
Execution
PR Nbr | PR Name | 2005 Total Project Budget | Proj Size | Current PM | Proposed PM | % Time on Proj | Status | Start Date | % Complete | CART | Need Staffing | Forecast End | Aug YTD | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
50017 | Collateral Calculation | 217000 | M | Buckley | Buckley | 20% | Planning | 2005-06-06 | 42% | CO | Y | 2005-12-31 | 9 | 30 | 62 | 62 | 54 | [6 empty] | 217000
50132 | Network Intrusion Detection and Protection System | 588000 | M | Pena | Pena | 30% | Execution | 2005-05-23 | 45% | CO | Y | 2005-12-31 | 7 | 10 | 170 | 351 | 50 | [6 empty] | 588000
50140 | Log and Event Management | 752000 | L | Pena | Pena | 30% | Planning | 2005-07-15 | 15% | CO | Y | 2005-01-30 |  | 5 | 35 | 390 | 222 | 100 | [5 empty] | 752000
50141 | Secure Email | 263000 | M | Pena | Pena | 30% | Planning | 2005-07-15 | 15% | CO | Y | 2005-12-31 |  | 3 | 52 | 153 | 55 | [6 empty] | 263000
50123 | Document Managemet | 762000 | L | Duncan | New FTE PM | 50% | Initiation | 2005-09-21 | 8% | CO | Y | 2006-04-30 |  | 3 | 95 | 400 | 53 | 53 | 53 | 53 | 52 |  |  | 762000
50015_01 | Lawson SIR Enhancements - Time Tracking | 435000 | M | Pena | New FTE PM | 30% | Execution | 2005-06-13 | 45% | CO | Y | 2005-11-30 | 10 | 69 | 150 | 114 | 47 | 45 | [5 empty] | 435000
50148 | Intranet Document Manager (IDM) Enhancements | 34000 |  | McDonald |  |  | Initiation | 2005-09-05 | 10% |  |  | 2005-12-31 |  | 5 | 12 | 12 | 5 | [6 empty] | 34000
50149 | Computer Aided Facilities Management (CAPM) | 65000 |  | McDonald |  |  | Initiation | 2005-09-05 | 10% |  |  | 2005-12-31 |  | 10 | 25 | 25 | 5 | [6 empty] | 65000
|  | 3116000 | [10 empty] | 26 | 135 | 601 | 1507 | 491 | 198 | 53 | 53 | 52 | 0 | 0 | 3116000

## IO PM Staffing Plan
2005-10-03 | Planning |  |  | PM Staffing Plan and Cash Flow for IO & CO
| Execution | [11 empty] | Forcasted Dollars in 000's
PR Nbr | PR Name | Total Project Budget | Proj Size | Current PM | Proposed PM | % Time on Proj | Status | Start Date | % Complete | CART | Need Staffing | Forecast End | Aug (YTD Totals) | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
50001_02 | Price Spike Analysis | 53000 | S | Jirasek | Jirasek | 10% | Cancelled | 2005-07-12 | -- | IO | Y | -- | Cancelled | [10 empty] | 0 | bar: Sep to Dec
50005 | EDW EMMS Reports | 327000 | M | Jirasek | Jirasek | 20% | Execution | 2005-01-24 | 59% | IO | Y | 2005-12-31 | 85 | Sep: 62; Oct: 60; Nov: 60; Dec: 60 | 327000
50022 | Infrastructure for 05 Capital Projects | 276000 | M | McLain | McLain | 10% | Execution | 2005-02-14 | 76% | IO | Y | 2005-08-22 | 36 | Sep: 240 | 276000
50125 | 2005 Storage to Support Operations | 988000 | L | McLain | McLain | 20% | Execution | 2005-02-14 | 73% | IO | Y | 2006-02-10 | 174 | Sep: 214; Oct: 200; Nov: 200; Dec: 200 | 988000
40042_06 | EDW EMMS ODS | 510000 | M | Buckley | Buckley | 20% | Execution | 2004-06-01 | 73% | IO | Y | 2005-12-15 | 298 | Sep: 52; Oct: 60; Nov: 50; Dec: 50 | 510000
40042_07 | EDW EMMS ODS | 288000 | M | Jirasek | Jirasek | 20% | Closed | 2004-06-03 | 95% | IO | Y | 2005-09-30 | 263 | Sep: 25 | 288000
50027 | Disk Based Backup * | 631000 | L | McLain | Cons PM TBD | 20% | Initiation | 2005-08-09 | 0% | IO | Y | 2006-03-31 | TBD | [10 empty] | 0
50028 | Altiris DC Implementation | 511000 | M | McLain | Booker | 20% | Initiation | 2005-02-14 | 7% | IO | Y | 2006-03-31 |  | 30 | 60 | 100 | 100 | 100 | 100 | 21 |  |  |  | 511000
50034 | User Provisioning | 336000 | M | McLain | Booker | 20% | Initiation | 2005-07-25 | 0% | IO | Y | 2006-03-31 |  | 10 | 100 | 100 | 50 | 50 | 17 | 9 |  |  |  | 336000
50078 | SBC Network Replacement | 731511 |  | Booker | Cons PM | 20% | Initiation | 2005-08-29 | 1% | IO |  | 2006-05-30 | [11 empty] | 0 | bar: Sep to Nov
50138 | EMMS Dev Environment | 300000 | M | McLain | McLain | 20% | Initiation | 2005-08-09 | 0% | IO | Y | 2006-01-31 |  | Sep: 15; Oct: 20; Nov: 200; Dec: 45; Jan: 20 | 300000
50143 | IPC Line Networking | 127000 | S | Booker | Cons PM | 20% | Initiation | 2005-08-22 | 3% | IO | Y | 2005-12-31 |  | Sep: 7; Oct: 7; Nov: 100; Dec: 13 | 127000
50144 | PBX Upgrade | 163800 |  | Booker | Cons PM | 20% | Initiation | 2005-08-22 | 8% | IO |  | 2005-10-31 |  | Sep: 10; Oct: 45; Nov: 60; Dec: 48 | 163000
50146 | Network Anlysis | 455884 |  | Booker | Cons PM | 20% | Initiation | 2005-08-29 | 1% | IO |  | 2005-12-31 |  | Sep: 10; Oct: 25; Nov: 385; Dec: 35 | 455000
50147 | Domain Restructuring * | 176000 | M | McLain | Cons PM TBD | 20% | Initiation | 2005-08-29 | 0% | IO | Y | 2006-05-31 | TBD | Sep: 10; Oct: 30; Nov: 80; Dec: 56 | 176000
not yet asgn | Firewall Modules | 124000 | M | McLain | Assoc PM | 10% | Initiation | -- | -- | IO | Y | -- | TBD | Sep: 5; Oct: 7; Nov: 100; Dec: 12 | 124000
not yet asgn | System Map * | 96000 | S | McLain | Assoc PM | 10% | Initiation | -- | -- | IO | Y | -- | TBD |  | 5 | 10 | 24 | 24 | 24 | 9 |  |  |  | 96000
50004 | EDW Business intelligence Reporting Tool | 439000 | S | Buckley | Buckley | 20% | Execution | 2005-06-06 | 26% | IO | Y | 2006-02-07 | 8 | 72 | 72 | 72 | 73 | 73 | 69 |  |  |  |  | 439000
50013 | Capacity True-up * | 964000 | L | McLain | McLain | 20% | Planning | 2005-06-20 | 47% | IO | Y | 2005-12-31 | 15 | Sep: 10; Oct: 906; Nov: 23; Dec: 10 | 964000
50049 | TCC II Completion | 550000 | M | McLain | Assoc PM | 20% | Planning | 2005-07-18 | 3% | IO | Y | 2005-12-31 |  | Sep: 275; Oct: 275 | 550000
50145 | ACC DataCenter Power & Cooling * | 329859 |  | McLain | Assoc PM | 5% | Planning | 2005-08-22 | 0% | IO |  | 2005-12-30 | TBD | [10 empty] | 0 | bar: Sep to Nov
50030 | LodeStar Decommission | 180000 | M | Jirasek | Buckley | 20% | Not Started | -- | -- | IO | Y | 2005-12-31 | 0 | Oct: 30; Nov: 50; Dec: 50; Jan: 50 | 180000
50031 | EMMS Decommission | 167000 | M | Jirasek | Jirasek | 10% | Not Started | -- | -- | IO | Y | 2006-02-28 | 0 |  | 30 | 30 | 27 | 27 | 27 | 26 |  |  |  | 167000
50001_03 | Replacmt Reserves Mrkt Ad Hoc Rpting | 49500 | S | Jirasek | Jirasek | 20% | Initiation | 2005-09-26 | 1% | IO | Y | 2005-12-31 | 0 | Oct: 8; Nov: 21; Dec: 21 | 50000
50001_04 | Ad Hoc Access QSE Down-Bal Compliance Report | 69500 | S | Jirasek | Jirasek | 10% | Initiation | 2005-09-26 | 1% | IO | Y | 2005-12-31 | 0 | Oct: 9; Nov: 30; Dec: 30 | 69000
40070 | Austin QA Buildout * | 434000 | M | McLain | McLain | 10% | On Hold | -- |  | IO | Y | 2006-05-31 | 164 |  | 50 | 100 | 100 | 120 | 120 | 100 | 100 | 100 |  | 954000
Support all IO & CO Projects |  | 9201054 |  |  | Totals | [6 empty] | Totals | 1043 | 1047 | 1999 | 1771 | 1004 | 464 | 357 | 165 | 100 | 100 | 0 | 8050000
Moved since last Review

## RO Staffing Plan
Cash Flow for RO - August YTD Actuals / Projections Through EOY | [18 empty] | 2005-10-03
Planning
Execution
PR Nbr | PR Name | Total Project Budget (2005) | Proj Size | Status | Start Date | % Complete (Current Phase) | Forecast End | Aug YTD | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Projected Spend 2005/2006
40034 | TX Set 2.1 | $500k-$1M | M | Execution | 2005-01-03 | 55% | 2005-12-01 | 316 | 90 | 80 | 70 | 50 | 5 | [5 empty] | 611000
50007 | Enhancements to FasTrak Tools | $1M-$3M | L | Planning | 2005-01-03 | 10% | 2006-03-01 | 160 | 200 | 200 | 200 | 200 | 100 | 100 | 100 | 100 | 50 |  | 1410000
50023 | Potential Load Loss | $100k-$500k | M | Planning | 2005-08-12 | 7% | 2005-12-01 | 4 | 5 | 40 | 40 | 20 | [6 empty] | 109000
50026 | 2005 SIR Enhancements | $500k-$1M | S-M | Planning | 2005-08-10 | 6% | 2006-01-01 | 1 | 20 | 150 | 150 | 100 | 5 | [5 empty] | 426000
50121_02 | TIBCO Hawk Implementation | $100k-$500k | M | Initiation | 2005-09-06 | 0% | 2005-12-01 |  | 35 | 34 | 23 | 23 | [6 empty] | 115000
50121_03 | Market Information Distribution | $100k-$500k | M | Execution | 2005-02-07 | 70% | 2005-11-12 | 180 | 65 | 65 | 31 | 2 | [6 empty] | 343000
50121_04 | Framework Services | $100k-$500k | M | Closing | 2005-03-21 | 100% | 2006-03-31 | 20 | 39 | [9 empty] | 59000
50121_06 | Endpoint Services (Phase 1) | $100k-$500k | M | Planning | 2005-08-15 | 5% | 2005-12-07 | 5 | 75 | 30 | 45 | 20 | [6 empty] | 175000
50121_07 | Retail Business Processes | $100k-$500k | M | Planning | 2005-06-01 | 10% | 2006-03-01 | 27 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 25 |  | 802000
40019 | Retail Testing Website | $100k-$500k | M | Closing | 2004-12-01 | 99% | 2005-09-01 | 120 | 30 | 2 | [8 empty] | 152000
40106 | ERCOT.com | $1M-$3M | L | Execution | 2004-09-01 | 70% | 2005-11-01 | 565 | 160 | 160 | 10 | [7 empty] | 895000
| 2005 PPL Approved Budget | 5634010 |  | 2005 Projected Cash Flow |  |  | 4212000 | 1398 | 769 | 861 | 669 | 515 | 210 | 200 | 200 | 200 | 75 | 0 | 5097000
Note on E11: dtroxtell: Combined with 50121_07

## MO PM Staffing
2005-10-03 | Planning |  |  | PM Staffing Plan and Cash Flow for MO
Execution
PR Nbr | PR Name | Total Project Budget (2005) | Proj Size | Current PM | Proposed PM | % Time on Proj | Status | Start Date | % Complete | CART | Forecast End | Aug YTD | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
40107 | VeriSign | 206070 | S-M | Segovia | Segovia | 15% | Execution | 2005-01-17 | 40% | IO | 2006-01-06 | 39 | 55 | 25 | 47 | 30 | 6 | [5 empty] | 202000
40093 | RMR Automation | 104000 | S | Chudgar | Assoc PM | 10% | Execution | 2004-07-01 | 80% | MO | 2005-10-12 | 44 | 20 | 10 | 4 | [7 empty] | 78000
50010 | SIR Enhancements R2 | 92000 | S | Chudgar | Assoc PM | 10% | Execution | 2005-01-03 | 60% | MO | 2005-10-14 | 36 | 12 | 12 | [8 empty] | 60000
50011 | SIR Enhancements R3 | 50000 | S | Troxtell | Assoc PM | 10% | Not Started | n/a | n/a | MO | 2005-10-01 |  |  | 10 | 20 | 20 | [6 empty] | 50000
50012 | SIR Enhancements R4 | 50000 | S | Troxtell | Assoc PM | 10% | Not Started | n/a | n/a | MO | 2005-12-01 |  |  | 10 | 20 | 20 | [6 empty] | 50000
50128 | Settlement Mismatched Inter-QSE Sched | 50000 | S | Chudgar | Assoc PM | 10% | Planning | 2005-06-01 | 11% | MO | 2005-12-01 | 2 | 10 | 10 | 10 | 10 | [6 empty] | 42000
50129 | Revision to Bal. Energy Pmts from Specific Res. | 50000 | S | Chudgar | Assoc PM | 10% | Planning | 2005-06-01 | 8% | MO | 2005-12-01 | 2 | 10 | 10 | 10 | 10 | [6 empty] | 42000
50133 | iTEST Server Sync | 51500 | S | Chudgar | Assoc PM | 5% | Execution | 2005-07-18 | 50% | MO | 2005-11-04 | 17 | 10 | 10 | 7 | [7 empty] | 44000
50033_02 | MV90 Upgrade Software | 65000 | S | Troxtell | Assoc PM | 5% | Planning | 2005-07-01 | 5% | MO | 2005-12-01 |  | 2 | 2 | 40 | 20 | [6 empty] | 64000
40104 | Zero Charge Enhancement | 0 | S | Chudgar | Chudgar | 5% | Cancelled |  |  | MO | 2005-10-03 | 5 | [10 empty] | 5000
40108 | Disclosure of Local Congestion | 86670 | S | Chudgar | Chudgar | 15% | Execution | 2005-01-02 | 50% | MO | 2005-10-06 | 25 | 30 | 15 | 5 | [7 empty] | 75000
40007 | SCR 727 Phase 2 | 429976 | M | Troxtell | Keith Haynes | 20% | Execution | 2005-01-03 | 50% | MO | 2005-12-01 | 180 | 37 | 62 | 55 | 20 | [6 empty] | 354000
50025 | Enhance ESI ID Look Up Function | 277777 | M | Haynes | Keith Haynes | 15% | Planning | 2005-08-12 | 10% | MO | 2005-12-01 | 2 | 25 | 100 | 100 | 50 | [6 empty] | 277000
50024_01 | Enhancements to SCR727 | 1116700 | L | Troxtell | Keith Haynes | 20% | Execution | 2005-01-03 | 15% | MO | 2006-03-01 | 111 | 165 | 218 | 123 | 131 | 140 | 70 | 26 | 23 |  |  | 1007000
50024_02 | Enhancements to SCR727 | 272186 | M-L | Troxtell | Keith Haynes | 20% | Not Started | n/a | n/a | MO | 2006-03-01 |  |  | 70 | 100 | 100 | 100 | 100 | 100 | 50 |  |  | 620000
40015 | TCR Enhancements | 65787 | S | Segovia | Segovia | 10% | Closed | 2004-05-07 | 100% | MO | 2005-09-01 | 35 | 1 | [9 empty] | 36000
50137 | Maestro Upgrade | 325000 | S | Troxtell | Segovia | 10% | Planning | 2005-06-01 | 10% | MO | 2005-12-01 | 0 | 25 | 350 | 75 | 25 | [6 empty] | 475000
40015_01 | TCR Enhancements | 146105 | S | Segovia | Segovia | 10% | Execution | 2005-06-13 | 10% | MO | 2005-11-30 | 10 | 50 | 45 | 30 | [7 empty] | 135000
30026 | EPS Meter Data Extracts | 46882 | S | Troxtell | Troxtell | 5% | Execution | 2003-07-14 | 75% | MO | 2005-11-01 | 9 | 15 | 10 | 5 | 3 | [6 empty] | 42000
40075_02 | Lodestar Enhancement SIRs | 10000 | S | Troxtell | Troxtell | 5% | Execution | n/a | 50% | MO | 2005-10-01 | 3 | 4 | 3 | [8 empty] | 10000
|  | 3495653 | [9 empty] | 520 | 471 | 972 | 651 | 439 | 246 | 170 | 126 | 73 | 0 | 0 | 3668000
Note on N17: dtroxtell: Includes ~ 100k s/w purchase
Note on O17: dtroxtell: will include 50,000 H/W purchase.

## SO PM Staffing
2005-10-03 | Planning |  |  | PM Staffing Plan and Cash Flow for SO
| Execution | [12 empty] | Forcasted Dollars in 000's
PR Nbr | PR Name | Total Project Budget | Proj Size | Current PM | Proposed PM | % Time on Proj | Status | Start Date | % Complete | CART | Need Staffing | Forecast End | Aug YTD | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
40112-05 | MOMS Phase 2 - ISR | 99430 | S | Diaz |  | 10% | Closing | 2005-01-01 | 100 | SO |  |  | 82 | [16 empty] | 82000
30144 | EMP 2.2 Upgrade | 176171 | M | Abad |  | 1% | Closing | 2004-08-01 | 100 | SO |  |  | 156 | 73 | [15 empty] | 229000
40100 | RTCA Archiving | 141316.0455 | M | Raina | Raina | 18% | Execution | 2004-02-01 | 57 | SO |  |  | 50 | 33 | 25 | 12 | 5 | [12 empty] | 125000
40113 | RAP-C Modeling Enhancements | 122052 | M | Massman | Massman | 15% | Execution | 2004-08-01 | 66 | SO |  |  | 42 | 25 | 28 | 21 | 3 | [12 empty] | 119000
40084 | Outage Scheduler Enhancements Phase II | 248121.5436 | M-L | Abad | Blatchford | 30% | Execution | 2004-07-01 | 79 | SO |  |  | 194 | 31 | 52 | 45 | 38 | 15 | 15 | 15 | [9 empty] | 405000
40101 | Daily Operations Report | 62508 | S | Abad | Blatchford | 15% | On Hold | 2004-08-01 | 3 | SO |  |  | -1 | 0 | 11 | 4 | 2 | [12 empty] | 16000
40086 | Incident Report | 89941 | S | Abad | Blatchford | 10% | Execution | 2005-04-01 | 49 | SO |  |  | 35 | 22 | 5 | 5 | 2 | [12 empty] | 69000
40098 | Perf Monitor SCADA/State Estimator | 69107.392 | M | Abad | Abad | 10% | Execution | 2004-09-01 | 72 | SO |  |  | 60 | 18 | 11 | 4 | 2 | [12 empty] | 95000
50002-01 | MOMS - ISR Enhancements | 363069.038 | M | Diaz | Diaz | 25% | Execution | 2005-01-01 | 44 | SO |  |  | 11 | 108 | 14 | 43 | 63 | 62 | 62 | [10 empty] | 363000
50003 | MOMS - Enhancements to AREVA Study Tools | 277874.422 | M | Diaz | Diaz | 15% | Planning | 2005-06-01 | 0 | SO |  |  |  |  | 15 | 27 | 81 | 28 | 16 | 55 | 55 | 55 | 55 | [6 empty] | 387000
30105 | Congestion Management Reports | 97499.7972 | S | Blatchford | L. Prince | 27% | Planning | 2005-02-01 | 46 | SO |  |  | 14 | 26 | 13 | 16 | 13 | [12 empty] | 82000
50044 | Near Miss Indicator IROL/SOL (Informational Reporting Indicator for IROL/SOL) | Bundled w/ above | S | Blatchford | L. Prince | Bundled w/ above | Planning | 2005-02-01 | 28 | SO | [19 empty] | 0
30029 | Overlimit Reports (O&M) | Bundled w/ above | S | Blatchford | L. Prince | Bundled w/ above | Planning | 2005-02-01 | 28 | SO | [19 empty] | 0
30028 | Overload Reports | Bundled w/ above | S | Blatchford | L. Prince | Bundled w/ above | Planning | 2005-02-01 | 28 | SO | [19 empty] | 0
50008 | Agg of Combined Cycle Units Providing RRS | 16249.9662 | S | Blatchford | Blatchford | 5% | Planning | 2005-02-01 | 69 | SO |  |  | 3 | 9 | 9 | [14 empty] | 21000
30183-01 | EMMS R4A | 3066325 | L | Robinson | Robinson | 24% | Execution | 2003-09-01 | 85 | SO |  |  | 2156 | 150 | 439 | 46 | 63 | [12 empty] | 2854000
40090-01 | Operator Train Simulator - OTS Center | 246864 | L | Raina | Raina | 36% | Execution | 2004-12-01 | 50 | SO |  |  | 24 | 13 | 9 | 132 | [13 empty] | 178000
40090-02 | Operator Train Simulator - OTS System | 261218 | L | Raina | Raina | 36% | Planning | 2004-12-01 | 48 |  |  |  | 119 | 22 | 10 | 12 | 12 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 334 | 4183000
30084 | CSC Thermal & Volt Limits Calculations/Posting | 153147.7487 | M | Massman | Massman | 20% | Execution | 2005-02-01 | 34 | SO |  |  | 42 | 25 | 14 | 12 | 12 | 37 | 22 | 18 | [9 empty] | 182000
50016 | AVR Validation | 19499.9594 | S | Blatchford | Blatchford | 5% | Initiation | 2005-06-01 | 0 | SO | [19 empty] | 0
50134 | DC Tie Automation and Scheduling | 206403 | M | Robinson | Robinson/Blatchford | 44% | Planning | 2005-06-01 | 16 | SO |  |  | 13 | 33 | 15 | 17 | 57 | 340 | 340 | 340 | 340 | 340 | 340 | [6 empty] | 2175000
50021 | Improve Reliability of Frequency Input to AGC | 12999.973 | S | Blatchford | Blatchford | 5% | Initiation | 2005-06-01 | 0 | SO | [19 empty] | 0
50136 | EMMS Software Upgrade - OSI PI and OAG | 173070 | M | Blatchford | Blatchford | 10% | Execution | 2005-07-01 | 20 | SO |  |  | 1 | 18 | 48 | 48 | 47 | [12 empty] | 162000
50050 | Satellite Comm for Black Start suppliers | 75600 | S | Blatchford | Blatchford | 5% | Planning | 2005-07-01 | 15 | SO |  |  | 1 | 6 | 29 | 29 | [13 empty] | 65000
30021 | Replace DSM6 and VGR Freq Recorders | 80663 | S | Blatchford | Blatchford | 5% | Planning | 2005-07-01 | 15 | SO |  |  | 0 | 34 | 34 | [14 empty] | 68000
50142 | Network Model Management System (NMMS) | 481000 | M | Massman | Massman | 23% | Planning | 2005-07-01 | 6 | SO |  |  | 0 | 96 | 96 | 96 | 97 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 163 | 2385000
50130 | SCE Performance and Monitoring | 300000 | M | Blatchford | L. Prince | 15% | Planning | 2005-07-01 | 34 | SO |  |  | 0 | 30 | 81 | 81 | 81 | [12 empty] | 273000
50131 | Market Notice of LaaR Proration | 300000 | M | Senters | L. Prince | 10% | Queued |  | 0 | SO | [5 empty] | 40 | 40 | 40 | 45 | 45 | 45 | 45 | [7 empty] | 300000
50029 | Improvements to VSA/DSA - Phase II | 140999.7067 | M | Massman | Massman | 17% | Queued |  | 0 | SO |  |  |  |  | 18 | 19 | 19 | 28 | 28 | 28 | [9 empty] | 140000
50135 | Topology Estimation System | 108000 | L | Robinson | Robinson/L. Prince | 13% | Planning | 2005-06-01 | 2 | SO |  |  | 0 | 22 | 21 | 22 | 22 | 96 | 96 | 96 | 96 | 96 | 96 | [6 empty] | 663000
50052 | Operations Support Study Environment/Disaster Recovery Test Environment | 894240 | M-L | Senters | L. Prince | 25% | 2006 |  | 0 | SO | [7 empty] | 7 | 7 | 7 | 291 | 291 | 291 | [6 empty] | 894000
0
[5 empty] | SO Totals | [7 empty] | 3002 | 794 | 997 | 731 | 659 | 1154 | 1132 | 1105 | 1328 | 1328 | 1283 | 501 | 501 | 501 | 501 | 501 | 497 | 16515000 | 16531515000