## Slide 1: TX SET V2.1 Market Coordination Team

## Slide 2
Business lead: Suzette Wilburn
Phone number: (512) 248-3991
Email address: swilburn@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 6 Program Area: RO
What prompted the project:
  MOU/EC Entrance to Texas Deregulated Market
  Market Efficiency
  Identified Transactional Gaps
Supporting business drivers:
  More efficient transaction processing
  Business process solidification
PR-40034/TX SET V2.1

## Slide 3
Objectives:
To implement all approved Change Controls as identified by the TX SET Working Group for market-wide use
Provide coordination, clarification of issues, and documentation for v2.1 Change Controls through the Market Coordination Team (MCT) efforts
Scope:
Support the MOU/EC entrance into the Texas deregulated market
Address Disconnect for Non-Pay processes
Communicate additional billing determinants to the Market
Dependencies:
Completion of Market Requirements from TX SET Working Group
PR-40034/TX SET V2.1

## Slide 4
Phase:
Initiation – Completed March 28th, 2005
Planning – Completed May 27th, 2005
Execution – Goal to complete December 4th, 2005
Closing – Goal to complete late December ‘05
Recent:
Submitted RMGRRs to RMS
Submitted PRRs to PRS
Flight 1005 Underway
Next steps:
Testing of Texas SET Version 2.1 in Flight 1005
Implementation Weekend – December 3rd
PR-40034/TX SET V2.1

## Slide 5
Requirements (pens down) – Completed April 7th, 2005
Design (internal document) – Completed May 27th, 2005
Build – Completed July 22nd, 2005
Internal Testing – Completed August 22nd, 2005
Internal Training – Completion goal of November 17th, 2005
Market Testing – Completion goal of November 23th, 2005
Production (Go live) – December 4th, 2005
PR-40034/TX SET V2.1

## Slide 6
Progress Update
Retail Market Guide Revisions
  RMGRR030 posted on September 27th, 2005
  RMS approved vote for Urgency Status on September 29th, 2005
  Revisions will be voted on at today’s RMS meeting
Protocol Revisions
  PRR636 and PRR637 posted on September 23rd, 2005
  Announce to PRS on September 29th, 2005
  Will be discussed at next PRS Meeting on October 20th, 2005
Flight 1005 Underway
  Further Texas SET Version 2.1 status provided in Flight Updates
V2.1 MCT Updates

## Slide 7
Next Steps
No October Meeting
Final Meeting in November
  Implementation Plan Review
  Conference Call Information Distributed
MCT Materials can be found on the ERCOT website
  www.ercot.com
  Select Market Participants & Stakeholders
  Select Texas Set
  Select Key Documents
  Select Related Working Groups
  Select Version 2.1 Market Coordination Team Documentation
V2.1 MCT Updates