| PRR Number | 627 | PRR Title | RMR Transmission Issues and RMR Contract Extension |
| --- | --- | --- | --- |
| Date |  | October 12, 2005 |  |
| Submitter’s Information |  |  |  |
| Name |  | Manny Munoz |  |
| E-mail Address |  | Manuel.munoz@centerpointenergy.com |  |
| Company |  | CenterPoint Energy |  |
| Company Address |  | 1111 Louisiana, Houston, Tx., 77002 |  |
| Phone Number |  | 713-207-5398 |  |
| Fax Number |  | 713-207-9270 |  |

ERCOT/Market Segment Impacts and Benefits

Instructions:  To allow for comprehensive PRR consideration, please fill out each block below completely, even if your response is “none,” “not known,” or “not applicable.”  Wherever possible, please include reasons, explanations, and cost/benefit analyses pertaining to the PRR.

|  | Impact |  | Benefit |
| --- | --- | --- | --- |
|  | Business | Computer Systems |  |
| ERCOT |  |  |  |
| MARKET SEGMENT |  |  |  |
| Consumer |  |  |  |
| LSE: General, Including NOIE |  |  |  |
| LSE: CR & REP |  |  |  |
| QSE |  |  |  |
| Resource |  |  |  |
| TDSP |  |  |  |

Comments

Currently there exists three separate means by which TDSP construction and outage information is conveyed to the public.  These are:

- The ERCOT Transmission Project Information Tracking system (TPIT).

- The ERCOT Outage Scheduler

- The PUCT Monthly Construction report.

Aside from the fact that most TDSPs are expending a significant amount of effort in providing this data, the information is being provided via parallel paths and there should be general concern regarding appropriate consistency and compatibility between these different mediums. Rather than developing yet one more information set, as proposed by PRR627, CenterPoint Energy believes that the data currently being provided should be fully evaluated so that the information being sought in PRR627 can be readily derived with the minimal amount of effort and possibility for discrepancy. Specifically, CenterPoint recommends that a working group be established to accomplish the following objectives:

- Define the minimum number of data entry points needed such that all TDSP information relevant to market operations and planning can be derived. (CenterPoint would postulate that only two are needed: TPIT and the Outage Scheduler.)

- Define the necessary cross-links between the data entry points derived in 1 such that upgrades and projects can be easily discerned.

- Determine what reports need to be generated so that the market gets the information it needs regarding planned transmission projects and outages.

- Develop the necessary SCRs and /or PRRs to accomplish 2 and 3 above.

CenterPoint agrees that some Protocol changes can be made now to better define the current TDSP obligations for reporting information to the MIS. Additionally, CenterPoint is recommending language to address the extension period issue. Thus, CenterPoint Energy offers the following redline edits to the PRR comments as submitted by TXU on October 3rd.

Revised Proposed Protocol Language

6.5.9.4	Transmission System Upgrades Associated with an RMR and/or MRA Exit Strategy

Once a suitable RMR or MRA exit strategy has been developed as defined in Section 6.5.9.2, Exit Strategy from an RMR Agreement, and the strategy has been approved by the ERCOT Board and the affected TDSP(s), :

(1)	ERCOT and the TDSP(s) responsible for constructing the applicable upgrades shall coordinate construction clearances necessary to allow timely completion of all planned Transmission Facilities upgrades.

(2)	The TDSP(s) responsible for constructing the applicable upgrades shall establish and forward to ERCOT estimated Outage information including completion dates and associated model information per Section 8.8, Coordination for System Topology Modifications.

(3)	The TDSP(s) responsible for the applicable upgrades shall also provide ERCOT with the corresponding upgrade requirements and any necessary updates before the next regularly scheduled T&D construction update as specified in Section 12.4, Market-Related Information. Subsequent updates will highlight any changes in the planned construction scheduled as well as the reasons for the change. As these upgrades near completion ERCOT and the TDSP will coordinate more timely updates if the timeline changes significantly.

(4)	Within ten (10) Business Days after completion of the Transmission Facilities upgrades that are part of an RMR or MRA exit strategy, ERCOT shall publish a Market Notice of such completion and the effective date of termination of the associated RMR or MRA Agreement.

6.5.9.5	RMR and/or MRA Contract Extension

(1)	Forty-five (45) days prior to the expiration or termination date of an existing RMR or MRA Agreement, ERCOT shall assess the likelihood of completion of the Transmission Facilities upgrade project(s) necessary to allow expiration or termination of an existing RMR or MRA Agreement based on the bi-weekly updates of project status provided by the TDSP(s).  If ERCOT determines that a delay in the termination or expiration date of the existing RMR or MRA Agreement is necessary to allow completion of the Transmission Facilities upgrade(s), it shall provide written notice to the Resource Entity that owns the RMR Unit or MRA Resource of its intent to execute an extension to the existing RMR or MRA Agreement no later than thirty (30) days prior to the planned expiration or termination date

(2)	ERCOT shall extend the existing RMR or MRA Agreement as necessary to allow completion of the Transmission Facilities upgrade(s), but in no event shall the extension last more than sixty (60) days from the date on which ERCOT provides notice of the extension to the Resource Entity that owns the RMR or MRA Resource.

(3)	If delay in the completion date of the transmission upgrades requires an extension of the existing RMR or MRA Agreement for more than sixty (60) days, ERCOT shall enter into negotiations with the Resource Entity that owns the RMR or MRA Resource to revise and extend the existing RMR or MRA Agreement to allow completion of the planned transmission upgrades, but in no case shall the extension be more than ninety (90) days.

(4)	If this extension period expires and ERCOT determines that the Generation Resource is still needed for System reliability, then the Generation Entity shall maintain the Resource so that it is available for OOM Dispatch Instructions until no longer required to do so pursuant to P. U. C. Subst. R. 25.502(f)(2).

Section 22 - Attachment F- Standard Form Reliability Must-Run Agreement

Section 3. Term, Extension, and Termination.

A.	Term.

(1)	This Agreement is effective beginning on the Effective Date.

(2)	The “Term” of this Agreement is a period of  ______ months; provided however, ERCOT, at its sole discretion, may terminate this Agreement prior to the end of the Term by giving 90 days advance written notice.

(3)	The period beginning on the Start Date and ending on the Stop Date is called the “Full Term” of this Agreement.

(4)	Any Initial Term that extends beyond one (1) calendar year requires ERCOT Board approval.

B.	Extension by ERCOT. ERCOT may, at its sole discretion, extend this Agreement for a period up to sixty (60) days, even if ERCOT has previously provided notice to Participant of future termination of the Agreement, by providing at least thirty (30) days advance written notice to Participant of the extension.

C.	Termination by Participant. Participant may, at its option, immediately terminate this Agreement upon the failure of ERCOT to continue to be certified by the PUCT as the Independent Organization under PURA §39.151 without the immediate certification of another Independent Organization under PURA §39.151.

D.	Effect of Termination and Survival of Terms. If this Agreement is terminated by a Party pursuant to the terms hereof, the rights and obligations of the Parties hereunder shall terminate, except that the rights and obligations of the Parties that have accrued under this Agreement prior to the date of termination shall survive.

12.4.4.2.2	TDSP Responsibility

TDSPs are required to provide market operation data to ERCOT including but not limited to:

(1)	Retail consumption data;

(2)	Transmission Outage requests;

(3)	Any system limitations information including but not limited to line limits;

(4)	Planned T&D construction information, including CCN application milestone dates if applicable, which shall be updated by the first Business Day of each calendar quarter.

(5)	New or updated Premise level (ESI ID) information;