## RO Staffing Plan
| Planning |  | Cash Flow for Retail Operations CART
| Execution | [10 empty] | 2006
PR Nbr | PR Name | Total Project Budget (2005) | Status | Start Date | % Complete | Forecast End | Actuals Sept YTD | Committed to date | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | TOTAL Project
40034 | TX Set 2.1 | $500k-$1M | Execution | 2005-01-03 | 75% | 2006-01-01 | 284 | 346 | Oct: 80; Nov: 70; Dec: 50; 2006 Jan: 25 | 571000
50007 | Enhancements to FasTrak Tools | $1M-$3M | Planning | 2005-01-03 | 25% | 2006-03-01 | 186 | 192 | Oct: 562; Nov: 200; Dec: 200; 2006 Jan: 75; 2006 Feb: 75; 2006 Mar: 75; 2006 Apr: 75; 2006 May: 75 | 1529000
50023 | Potential Load Loss | $100k-$500k | Planning | 2005-08-12 | 7% | 2005-12-01 | 5 | 11 | Oct: 15; Nov: 10; Dec: 18 | 54000
50026 | 2005 SIR Enhancements | $500k-$1M | Planning | 2005-08-10 | 6% | 2006-01-01 | 5 | 22 | Oct: 125; Nov: 190; Dec: 155; 2006 Jan: 50; 2006 Feb: 40 | 582000
50121_06 | Endpoint Services (Phase 1) | $100k-$500k | Planning | 2005-08-15 | 5% | 2005-12-07 | 5 | 18 | Oct: 30; Nov: 45; Dec: 20 | 113000
50121_07 | Retail Business Processes | $100k-$500k | Planning | 2005-06-01 | 10% | 2006-03-01 | 37 | 93 | Oct: 100; Nov: 100; Dec: 100; 2006 Jan: 100; 2006 Feb: 100; 2006 Mar: 100; 2006 Apr: 100; 2006 May: 25 | 818000
50121-02 | TIBCO Hawk Implementation | 0 | Closing | 2005-09-06 | 0% | 2005-12-01 | 0 | 0 | Oct: 0; Nov: 0; Dec: 0 | 0
50121-03 | Market Information Distribution | $100k-$500k | Execution | 2005-02-07 | 70% | 2005-11-12 | 70 | 294 | Oct: 95; Nov: 31; Dec: 2 | 422000
50121-04 | Framework Services | <$100k | Closing | 2005-03-21 | 100% | 2006-03-31 | 57 | 73 | [15 empty] | 73000
40019 | Retail Testing Website | $100k-$500k | Closing | 2004-12-01 | 93% | 2005-11-05 | 152 | 158 | Oct: 8; Nov: 2 | 168000
40106 | ERCOT.com | $1M-$3M | Execution | 2004-09-01 | 70% | 2005-12-05 | 588 | 615 | Oct: 125; Nov: 50; Dec: 5 | 795000
[7 empty] | 1389 | 1822 | 1140 | 698 | 550 | 250 | 215 | 175 | 175 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5125000
| 2005 PPL Approved Budget | 5634010 |  | 2005 Projected Cash Flow |  |  |  | 4210
|  |  |  | Total Project Cash Flow Estimate |  |  |  | 5125 | bar: Oct