## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of November 2, 2005
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb 2005
Planning – Target complete in Jan 2006
Execution/Implementation – Target complete in May 2006
Recent:
Market Meeting with FasTrak market group held on 10/21
  Product demo; bus. rules review; Mkt Detail Design template & content format review
Conceptual System Design document drafted; finalization underway
Market Detail Design document started (template comments from MPs due by 11/4)
Next steps:
Conduct MP visits to understand how users handle bulk issues with current toolset/workflows
  Visiting TXUED, TNMP, Centerpoint, Direct Energy, Green Mountain
Complete Workflow definitions for all “out of the box” items
API prototype complete and start building Market facing API
Digital Certificate/LDAP integration prototype
Complete Conceptual Design Document
Complete and deliver Market Detailed Design by 11//30
Schedule Market mtg to review Detailed Design week of 12/5
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of November 2, 2005
Page 2

## Slide 3
** All target dates will become firm after ERCOT design is complete and Execution plan finalized in January
Requirements complete – June 2005
Market Detailed Design published – November 30, 2005
ERCOT Detailed Design – January 15, 2006
Market Test Scripts target – March 2006
User Guides target – April 2006
Training Materials target – April 2006
Market Test target – May 2006
Production target (‘go live’ with GUI & API) – end of May 2006
High level timeline
PR-50007 Enhancements to FasTrak
As of November 2, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of November 2, 2005
Page 4