## Slide 1: Flight Update

## Slide 2: Flight 1005
Details
All Market Participants are testing for TX SET Version 2.1
Flight Kick-off Conference Call 10/21
Flight Began 10/24
Tx SET 2.1 portion of Flight ends Monday 11/21
Flight 1005 for new MPs and territories ends 12/16

## Slide 3: Flight 1005 Update
Flight manifest
6 TDSPs
76 Existing Market participants / umbrellas
149 Existing MP Relationships testing
2 New REPs – 9 New Relationships
0 New Umbrella DUNs
6 Existing REP testing in new territory – 11 New Relationships
0 Existing REP testing new functionalities
3 Existing REPs changing Service Providers
1 Existing REPs changing Banks
9829 Tasks total

## Slide 4: Flight 1005 Update
Progress
Connectivity complete
Flight started on time
As of 11/3/2005 9:00 am
  Day 9
    34.23% complete
    41.63% by end of today
    40 outstanding transactions for week 1
      2 inbound to ERCOT
      6 outbound from ERCOT
      32 Point to Point
    241 overdue transactions for week 2
      37 inbound to ERCOT
      41 outbound from ERCOT
      163 Point to Point