## Slide 1: Nodal Readiness Plan Update
Ron Hinsley
Update for TAC
November 3, 2005

## Slide 2: Deliverables
Processes Touched
Project Organization (HR Issues)
Facilities / Logistics /Security
Governance
Protocol Gap / Clarification Analysis
Updated Timeline and Cost Estimate
Notes: Want to Update our progress on ERCOT’s preparations for nodal implementation.

## Slide 3: Processes Touched
Notes: You saw this slide in earlier updates.
This captures the major processes impacted by Nodal.
We used it to identify “owners” of the major processes within ERCOT.
This is posted on the TPTF website on ERCOT.com.

## Slide 4: Finance/Training
Training of Market Participants and interested parties
Training of ERCOT Staff
Credit Monitor

## Slide 5: System Operations
Modeling
Telemetry
State estimator
Resource parameters
Current Operating Plan
Load / Renewable Production Potential forecast
Outage Coordination
Load Frequency Control
Ancillary Services
Day Ahead Market
Reliability Unit Commitment
Security Constrained Economic Dispatch
Congestion Revenue Rights

## Slide 6: Commercial Operations
Ancillary Services Settlement
Day Ahead Market Settlements
Reliability Unit Commitment Settlement
Real Time Settlement
CRR Auction Settlement
CRR Settlement
Section 9 rules
Notes: CRR - Congestion Revenue Rights
If asked, Section 9 defines invoicing rules

## Slide 7: Information Technology
Market Information System
Data Center (capacity)
Market Participant Interfaces
Extracts, reports, archives, data warehouse

## Slide 8: Organization Strawman
Notes: You saw this slide in earlier updates. It is now posted on ERCOT.com.
We have developed Job Descriptions for the IT Program Director, Program Director, and Business Director. ERCOT HR plans to have these positions posted by the end of this week. We plan an internal search and external search in parallel. Please let me know of any candidates you would recommend for these positions.
We also created an Organization Strawman for the entire project team but anticipate formalizing the remaining structure after the Director positions are filled.

## Slide 9: Facilities / Logistics /Security
Plan to co-locate business and IT resources as much as possible during design and development. Looking at space in TCC2 as an option.
Parallel operation of zonal and nodal systems during testing will require significant additional data center space, which must be addressed.
Included Ann Delenela, a Manager in Corporate Security, in project organization to assist with security issues.
Notes: We are preparing space for teams to sit.
We are studying Data Center impacts and solutions.
We have included Corporate Security in our project organization.

## Slide 10: Governance
Notes: This is the flow diagram we discussed with TAC in Transition Plan discussions. We hope it demonstrates ERCOT’s desire to work in partnership with Market Participants throughout the project.
We added the RFI and RFP processes. We also added a note confirming that decisions by the TPTF will be returned to the appropriate step in the process.
We are planning approvals of:
Requirements by the TPTF and TAC.
Conceptual Designs by the TPTF and TAC.
Market Readiness by TPTF, TAC, ERCOT Staff & Board
The TPTF will also be involved, as needed, throughout the process to address issues related to Protocol interpretations.
Meetings with stakeholders will be noticed and decisions will be documented and posted.

## Slide 11: Protocol Gap / Clarification Analysis
Approximately 30 ERCOT employees are preparing a list of gaps or issues within the nodal Protocols that require clarification.
The goal is to resolve as much ambiguity as possible prior to development of requirements.
List will be available at first TPTF meeting
Developing Standard Requirements Templates
Notes: Approximately 30 employees were assigned sections of the Nodal Protocols to review. They are preparing a list of questions to ensure clarity for presentation to the TPTF.
Comments are due today. Earlier this week we had already received over 200 questions from 8 reviewers.
This is an effort to familiarize employees with the Nodal Protocols, including many who were not able to actively participate in the TNT process. The group will review the consolidated list which should serve to further educate employees and refine the questions for the TPTF.
We are also developing Standard Requirements Templates as part of our Software Development Life Cycle efforts. We anticipate population of the Requirements Documents to begin in late November.

## Slide 12: Updated Timeline and Cost Estimate
Worked with KEMA to refine the timeline and cost estimate to include tasks associated with most processes touched, match the test sequence proposed in the TNT Transition Plan, account for the Contested Case, and validate test durations.
KEMA developed a “Scheduling Risk Analysis” of the timeline.
Plan to post KEMA’s Risk Analysis and the refined timeline by November 8
Notes: We refined the timeline originally prepared by KEMA to address requirements in the Transition Plan. We think this takes the timeline from 50,000 feet down to 30,000 feet but this is not a project execution level document.
Plan to post the KEMA Risk Analysis and timeline by November 8

## Slide 13: Questions
?