## Slide 1
Objectives:
Develop a daily extract of customer loss notifications from Siebel and Paperfree and make it available to CRs via the ERCOT TML
Enable CRs to modify their load profiles, purchasing power agreements and energy schedules for enhanced daily load forecasting
Scope/Why is this important?:
Extract would provide CRs timely notification of pending loss of customer load for appropriate adjustments to power purchases and scheduling
Dependencies:
Dependent on release of testing resources used for PR-40034 TX SET 2.1 implementation December 2005
Project Objectives / Scope / Dependencies
PR-50023 Potential Load Loss
As of November 3, 2005
Page 1

## Slide 2
Phase:
Initiation – completed August 1, 2005
Planning – completed October 17, 2005
Execution – to be completed December 3, 2005
Closing – TBD
Current project state: Execution phase
Requirements completed
Design documentation completed
System coding in progress
Testing cycle currently on schedule
Summary of Project Status
PR-50023 Potential Load Loss
As of November 3, 2005
Page 2

## Slide 3
Extract data fields identified in SCR 739:
ESI ID
CR DUNs Number
TDSP DUNs Number
Status Reason (See next slide for options)
Service Period End Date (SMRD)
Extract attributes defined in SCR 739:
Limit output to DUNs number of Losing CR
Include DDL for extract so CRs can discern extract contents
  Please Note: DDL will NOT be in file contents rather will be a supplemental item available with other DDLs on TML
Post output file in .csv format to Market Participant folder within Report Explorer on ERCOT TML
Project Requirements
PR-50023 Potential Load Loss
As of November 3, 2005
Page 3

## Slide 4
Recommended Approach - (Service Order Type)
Move In
Switch
Alternative 2 (Code for Service Order Type)
MVI (Move In)
SW (Switch)
Alternative 3 (Code in TxSET 814_06 REF~1P data element)
020 (Move In)
CHA (Switch)
Defining Values of Status Reason
PR-50023 Potential Load Loss
As of November 3, 2005
Page 4

## Slide 5
Bus Lead: Denise E. Taylor
phone number: 512-248-3932
e-mail: dtaylor@ercot.com
PPL: Source: Market Priority: 1.2 Rank: 32 Program Area: RO
What prompted the project: SCR 739 Pending Load Loss Reports for CRs
Supporting business drivers:
  Allow for more accurate and timely visibility into retail customer load changes
  Decrease time and cost incurred by CRs to adjust their power purchase forecasts and power schedules
Additional Information
PR-50023 Potential Load Loss
As of November 3, 2005
Page 5