## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of November 29, 2005
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb 2005
Planning – Complete in Nov 2006
Execution/Implementation – November 14, 2006
Recent:
Conducted MP visits to understand how users handle bulk issues with current toolset/workflows the week of November 14th
  Visited TXUED, TXUES, Centerpoint, Direct Energy
Conceptual System Design document completed
Market Detail Design document completed and made available to MPs on Nov. 30th
Market meeting scheduled for December 9th to review Market Detailed Design document
Next steps:
Continue development work – GUI and API
Continue work on Digital Certificate/LDAP integration prototype
Complete and deliver Detailed Design document January 2006
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of November 29, 2005
Page 2

## Slide 3
** All target dates will become firm after ERCOT design is complete and Execution plan finalized in January
Requirements complete – June 2005
Market Detailed Design published – November 30, 2005
ERCOT Detailed Design – January 2006
Market Test Scripts target – March 2006
User Guides target – April 2006
Training Materials target – April 2006
Market Test target – May 2006
Production target (‘go live’ with GUI & API) – end of May 2006
High level timeline
PR-50007 Enhancements to FasTrak
As of November 29, 2005
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of November 29, 2005
Page 4