- ERCOT Profiling Working Group (PWG) RMS Presentation Material

At the November 2005 RMS meeting, all working groups have been asked to provide a status on what was performed on the 2005 goals, what was done in addition of 2005 goals and

# PWG 2005 Goal Accomplishments

- Evaluate Profile ID assignment responsibilities – June / Status - pending

  - Two workshop days, 4 million estimate for total change, 1 million partial

  - Several conference calls

  - Oct. 14, 2005 conference call achieved consensus on option 2

  - Nov. 17, 2005 PWG to review option 2

- Annual Validation 2005 – make changes and complete – December / Status - on schedule

  - TDSPs and ERCOT instituted several algorithm changes per 2005 plan

  - Decision Tree updated

  - TDSPs and ERCOT completed up to all transactions (one TDSP yet pending)

  - RMS suspended Residential Transactions per ERCOT Residential Analysis

  - ERCOT conducted a Residential Survey

  - October 29, 2005 PWG recommends the flow of residential transactions.

- AV 2006 review of changes  – Business (June), cut point (Dec.) / Status - on schedule.

  - PWG has consensus on four changes for 2006

  - PWG to review specifics on the four decision tree changes for 2006

- Evaluate Lagged Dynamics – Dec. / Status – on schedule

  - Have had several discussions to educate and discuss possibility

- Bring Load Profiling Guides current – Dec. / Status - Pending

  - LPGRR005 Remove 1000 kw references approved.

  - LPGRR006 Retail Market Guide Reference - withdrawn

  - LPGRR007 IDR Requirement Changes pending approval of RMGRR

  - LPGRR008 Profile ID Assignment Effective Date approved by RMS 11/9

  - Additional drafts being written by PWG subteams

- Processing new requests – Oil & Gas, Convenience Store – Dec. / Status – pending LRS

- Collaboration with UFE TF – Dec. / Status – on schedule

  - 2003 UFE report by ERCOT staff issued

  - 2004 UFE report pending ERCOT resource allocation

- Writing PRRs as required – Dec. / Status – on schedule

  - PRR488 Weather Responsiveness Determination – Eff. 05

  - PRR514 Twelve Month Window for Non-IDR Scaling Eff. 05

  - PRR536 lower IDR Mandatory Installation Threshold Eff. 05

  - PRR544 12-Month Window for Scaling NIDR to IDR Eff 05

  - PRR565 Calculation of Losses for Settlement

  - PRR566 Implementation of IDR Optional Removal Threshold

  - PRR572 Weather sensitivity classification

  - PRR617 IDR Optional Removal

  - To review a draft of Historical Usage Requirement for Opt-In Entities

  - To discuss Transmission language for IDR Optional Removal

- Load Research Sample (LRS) selection round two – Dec. / Status – on schedule

  - Report on sample evaluation developed

  - Data review with TDSPs in process

  - 12 months of data for most meters as of October

- IDR Analysis – 2 issues left – Dec. / Status – Pending

  - Needs LRS project data analysis

- Agreement between decision tree language and LPG – Dec. / Status – on schedule

  - LPGRR discussed and draft in process on profile id assignment

# PWG 2006 Goals

Load Research Sample (LRS) project review new profile recommendation – June.

LRS second round of sample meters – Dec.

Evaluate Profile ID assignment responsibilities – April

Annual Validation 2006 – make changes and complete – Dec.

AV 2007 review of process and changes - Dec.

Evaluate improvements post Hurricane Rita affects – Dec.

Evaluate TDSP meter read estimation processes – Dec.

Evaluate Lagged Dynamics – Dec.

Processing new profile requests – Oil & Gas, Convenience Store – Dec

IDR Analysis – 2 issues left – Dec

Maintain Load Profiling Guides – Dec

Writing PRRs as required – Dec.

Collaboration with UFE TF – Dec.